DESIGN-BUILD CONTRACT
FOR THE

JEFFERSON & HOOD STREET SURFACE
WATER INTERCEPTOR PROJECT



between



THE CITY OF TACOMA

and



[NAME OF DESIGN-BUILDER]

Dated

[___________, 2017]

[This Page Intentionally Left Blank]

TABLE OF CONTENTS

Page

Article 1

DEFINITIONS AND INTERPRETATION

Section 1.1.	DEFINITIONS	3

Section 1.2.	INTERPRETATION	21

(A)	Gender and Plurality	21

(B)	Persons	21

(C)	Headings	21

(D)	References Hereto	21

(E)	References to Days and Time of Day	21

(F)	References to Including	21

(G)	References to Statutes	21

(H)	References to the City, Governmental Bodies and Private Persons	22

(I)	References to Documents and Standards	22

(J)	References to All Reasonable Efforts	22

(K)	Entire Agreement	22

(L)	Standards of Workmanship and Materials	22

(M)	Technical Standards and Codes	22

(N)	Causing Performance	23

(O)	Party Bearing Cost of Performance	23

(P)	Good Engineering and Construction Practice	23

(Q)	Interpretation of Contract Documents	23

(R)	Applicability, Stringency and Consistency of Contract Standards	23

(S)	Delivery of Documents in Digital Format	23

(T)	Severability	23

(U)	Drafting Responsibility	24

(V)	No Third-Party Rights	24

(W)	Acting Reasonably and in Good Faith; Discretion	24

(X)	Counterparts	24

(Y)	Governing Law	24

(Z)	Defined Terms	24

(AA)	Interpolation	24

(BB)	Accounting and Financial Terms	24

(CC)	References to Dollar Amounts	24

(DD)	Liquidated Damages	24

(EE)	Convenience Termination	25

Article 2

DESIGN-BUILDER REPRESENTATIONS AND WARRANTIES

Section 2.1.	REPRESENTATIONS AND WARRANTIES OF THE DESIGN-BUILDER	26

(A)	Existence and Powers	26

(B)	Due Authorization and Binding Obligation	26

(C)	No Conflict	26

(D)	No Commitments Limiting Ability to Perform Contract Obligations	26

(E)	No Approvals Required	26

(F)	Licensing and Registration Requirements	26

(G)	No Litigation	27

(H)	Claims and Demands	27

(I)	Applicable Law Compliance	27

(J)	Information Supplied by the Design-Builder	27

(K)	Intellectual Property	27

(L)	Practicability of Performance	27

(M)	Required Insurance	27

Article 3

TERM

Section 3.1.	EFFECTIVE DATE AND TERM	28

(A)	Term	28

(B)	Accrued Rights	28

Section 3.2.	SURVIVAL	28

Article 4

GENERAL PERFORMANCE REQUIREMENTS

Section 4.1.	PROJECT SCOPE AND PERSONNEL	30

(A)	Project Scope Generally	30

(B)	Pricing Established on the Contract Date	30

(C)	Pricing Established Subsequent to the Contract Date	30

(D)	Estimated Substantial Completion Date	30

Section 4.2.	DESIGN-BUILDER RESPONSIBILITIES GENERALLY	30

(A)	Reliance	30

(B)	Scope of the Contract Obligations	30

(C)	Cooperation	31

(D)	Responsibility for Personnel and Subcontractors	31

(E)	Stationing of Key Personnel	31

Section 4.3.	ENVIRONMENTAL REVIEW	31

(A)	SEPA	31

(B)	NEPA	31

Section 4.4.	ACCESS TO AND SUITABILITY OF THE PROJECT SITES	32

(A)	Familiarity with the Project Sites	32

(B)	Independent Verification of the City-Provided Project Sites Information	32

(C)	Access to the Project Sites	32

(D)	Surface Water Conveyance Pipeline Rights of Way	33

(E)	Project Sites Signage	33

Section 4.5.	INFORMATION PROVIDED BY OR ON BEHALF OF THE City	33

(A)	Generally	33

(B)	Limited Reliance by Design-Builder	33

Section 4.6.	COMPLIANCE WITH APPLICABLE LAW	34

(A)	Compliance with Applicable Law Generally	34

(B)	Compliance with Conditions in Governmental Approvals	34

(C)	Fines, Penalties and Remediation	34

Section 4.7.	ENGAGEMENT OF City REPRESENTATIVES	35

Section 4.8.	OWNERSHIP AND USE OF DOCUMENTS AND INFORMATION	36

Section 4.9.	MONTHLY PROGRESS REPORTS	36

Article 5

STAGE 1 PRELIMINARY SERVICES

Section 5.1.	SCOPE OF THE STAGE 1 PRELIMINARY SERVICES	37

(A)	Generally	37

(B)	Stage 1 Preliminary Services Tasks; Notice to Proceed	37

Section 5.2.	CHANGES TO THE SCOPE OF THE PRELIMINARY SERVICES	37

(A)	Generally	37

(B)	Additional Stage 1 Preliminary Services	37

(C)	Additional Stage 1 Preliminary Services Resulting From Delay	37

(D)	Exclusions from Additional Stage 1 Preliminary Services	38

(E)	Changes that Reduce the Scope of the Stage 1 Preliminary Services	38

Section 5.3.	PRELIMINARY SERVICES SCHEDULE	38

Section 5.4.	COORDINATION WITH CITY	38

(A)	Meetings and Reports Generally	38

(B)	Information Provided by the City	38

(C)	Required Design Information	39

(D)	Revisions to Drawings and Specifications	39

Section 5.5.	PROJECT DESIGN	39

(A)	Design Considerations	39

(B)	Design-Builder Assumption of Full Design Liability	40

Section 5.6.	EARLY WORK PACKAGES	40

(A)	Early Work Packages	40

(B)	Early Work Package Submittals	40

(C)	Early Work Package Submittal Revisions	41

(D)	Negotiation and Execution	41

(E)	Complete Early Design-Build Work Package Pricing	41

(F)	Compensation Payable in Connection With Early Work Packages	42

(G)	Design-Builder Representations in an Early Work Package Amendment	42

(H)	Limited Authorization to Proceed; Commencement of Early Work Package	42

Section 5.7.	GMP SUBMITTAL	42

(A)	Stage 1 Preliminary Services and GMP Submittal	42

(B)	Derivation of Proposed Base Guaranteed Maximum Price	44

(C)	Stage 1 Preliminary Services Fee, Design-Builder Fee and General Conditions Fee	44

(D)	Early GMP Submittal	44

Section 5.8.	GMP AMENDMENT	44

(A)	Non-Compliant GMP Submittal	44

(B)	Negotiation and Execution of the GMP Amendment	45

(C)	Base Guaranteed Maximum Price Negotiating Principles	45

(D)	Obligations of the Design-Builder Relating to the GMP Amendment	46

(E)	No Obligation of the City to Enter Into a GMP Amendment	46

(F)	Elective Continuance of the Project by the Parties on Other Bases	46

(G)	Elective Continuance of the Project by the City with Other Contractors; Project Documents	47

(H)	Design-Builder Representations in a GMP Amendment	47

(I)	Performance Bond and Payment Bond	48

Section 5.9.	APPROVALS REQUIRED PRIOR TO STAGE 2	48

Article 6

DESIGN-BUILD WORK

Section 6.1.	STAGE 2 DESIGN-BUILD WORK GENERALLY	49

(A)	Authorization to Proceed; Commencement and Completion of the Stage 2 Design-Build Work	49

(B)	Elements of the Stage 2 Design-Build Work	49

(C)	Sequencing and Staging of Stage 2 Design-Build Work	50

(D)	Construction Work Hours	50

(E)	Laydown Areas	50

(F)	Stage 2 Design-Build Work Schedule and Reports	50

(G)	On-Site Meetings and Design and Construction Review	50

(H)	Construction Utilities	50

(I)	Quality Assurance and Quality Control	50

(J)	Title and Risk of Loss	51

(K)	Encumbrances	51

(L)	Notice of Default	51

(M)	Required Project Manager Certification	51

(N)	Partnering Requirements	51

(O)	Temporary Project Sites Facilities	51

(P)	Sensitivity to Stakeholders	51

(Q)	Utility Coordination and Re-location	52

Section 6.2.	CONSTRUCTION COMMENCEMENT DATE	52

(A)	Construction Commencement Date Generally	52

(B)	Establishment of the Construction Commencement Date	53

(C)	Effect of the Establishment of the Construction Commencement Date	53

Section 6.3.	DIFFERING SITE CONDITIONS	53

(A)	Stage 1 Preliminary Services Relating to Differing Site Conditions	53

(B)	Commencing Subsurface Excavations	53

(C)	Discovery of Differing Site Conditions	54

(D)	Relief for Differing Site Conditions	54

Section 6.4.	REGULATED SITE CONDITIONS	54

(A)	Design-Builder Responsibilities	54

(B)	Cultural Resources	55

(C)	Endangered Species	55

(D)	Encountering of Regulated Substances	55

(E)	Uncontrollable Circumstance Relief	55

(F)	Generator Liability	55

Section 6.5.	PERMITTING RESPONSIBILITIES AND SCHEDULE	56

(A)	Design-Builder Governmental and Non-Governmental Approval Responsibility, Generally	56

(B)	Application Process	56

(C)	City Governmental Approval Responsibility	56

(D)	Design-Builder Responsibility For the City Managed Governmental Approvals	58

(E)	Schedule Adjustment Based on Delays Affecting Design-Builder Managed Governmental Approvals	58

(F)	Adjustment to Scheduled Substantial Completion Date Based on Delays in Obtaining City Managed Governmental Approvals	58

(G)	Relief Based on Certain Permitting Terms and Conditions	59

Section 6.6.	BNSF MASTER UTILITIES LICENSE AGREEMENT APPROVAL	59

Section 6.7.	FINAL DESIGN RESPONSIBILITIES AND RISK ASSUMPTION	59

(A)	Performance of the Design Work	59

(B)	Sole Responsibility and Liability	59

(C)	City Review and Comment on Stage 2 Design Documents	60

(D)	Documents at the Project Site	60

Section 6.8.	CHANGES TO THE BASELINE DESIGN DOCUMENTS AT DESIGN-BUILDER REQUEST	60

(A)	City Consent Required	60

(B)	Notice and Information as to Proposed Change	60

Section 6.9.	OTHER CHANGES TO THE BASELINE DESIGN DOCUMENTS	61

(A)	Changes Made Due to Uncontrollable Circumstances	61

(B)	Changes Required by Governmental Bodies	61

(C)	Changes Required by the City	61

Section 6.10.	CHANGE PROCEDURES	62

(A)	Generally	62

(B)	Design-Builder Change Order Proposal	62

(C)	Negotiation of Proposed Change Order	62

(D)	Effect of Design-Builder’s Signature	62

Section 6.11.	WORK CHANGE DIRECTIVES	63

(A)	City Right to Issue	63

(B)	Disagreement with Terms of a Work Change Directive	63

Section 6.12.	STAGE 2 DESIGN-BUILD WORK DELIVERABLE MATERIAL	64

Section 6.13.	INTERFACE AND COORDINATION	64

(A)	Maintenance of Operations During Construction	64

(B)	Related Projects Generally	64

(C)	Interrelated Work	64

(D)	Disputes Associated with Separate Work	65

Section 6.14.	SUSPENSION OF WORK	65

Section 6.15.	CONSTRUCTION PRACTICE	65

(A)	Exclusive Responsibility of Design-Builder	65

(B)	Project Sites Debris, Trash and Waste	66

Section 6.16.	RESPONSIBILITY FOR SAFETY AND SECURITY	66

(A)	Safety Manager	66

(B)	Precautions and Protection; Project Sites Security	66

(C)	Health and Safety Inspections and Meetings	67

(D)	Health and Safety Compliance Requirements	67

(E)	Emergencies	67

(F)	Traffic Control	68

Section 6.17.	CONSTRUCTION MONITORING, OBSERVATIONS, TESTING AND UNCOVERING OF WORK	68

(A)	Observations and Design-Build Work Review Protocol	68

(B)	Factory Fabrication, Inspection and Testing	68

(C)	Design-Builder Tests	68

(D)	Certificates and Reports	69

(E)	City Tests, Observations and Inspections	69

(F)	Notice of Covering Design-Build Work	69

Section 6.18.	CORRECTION OF WORK	70

(A)	Correction of Non-Conforming Design-Build Work	70

(B)	Election to Accept Non-Conforming Design-Build Work	70

(C)	Relation to Other Obligations	70

Section 6.19.	PROPERTY DAMAGE DURING THE DESIGN-BUILD PERIOD	70

(A)	Damage Prevention	70

(B)	Restoration	70

(C)	Notice and Reports	71

(D)	Insurance and Other Third-Party Payments	71

(E)	Payment for Restoration Work and Uninsured Costs	71

(F)	Repair of the City and Private Property	71

Section 6.20.	PUNCH LIST ITEMS	72

(A)	Punch List Requirements	72

(B)	Completion of Punch List Items	72

Article 7

MANAGEMENT, LABOR AND SUBCONTRACTORS

Section 7.1.	MANAGEMENT	73

(A)	Project Manager	73

(B)	City Rights With Respect to Key Personnel	73

Section 7.2.	LABOR	74

(A)	Personnel Performance	74

(B)	Training of Design-Builder and Subcontractor Employees	74

(C)	Labor Relations	74

(D)	Notice of Labor Disputes	74

(E)	Prevailing Wages	74

(F)	Labor Compliance	75

(G)	Non-Discrimination	75

(H)	Drug-Free Workplace	75

Section 7.3.	SUBCONTRACTING GENERALLY	75

(A)	Right to Subcontract	75

(B)	Approval Required	76

(C)	Performance Failure	76

(D)	Restricted Persons	76

(E)	Subcontractor Licensing	76

(F)	Availability of Subcontractors and Key Personnel	76

(G)	Assignability	77

(H)	Prompt Payment	77

(I)	Subcontractor Claims	77

(J)	Design-Builder Employee Claims	77

Section 7.4.	SELF-PERFORMANCE AND SUBCONTRACTOR SELECTION	77

(A)	Self-Performed Construction Work Generally	77

(B)	Subcontractor Selection Generally	78

(C)	Subcontracting Plan	78

(D)	Division of Work	78

(E)	Pre-Bid Conferences	78

(F)	Competitive Procedures for Construction Work	78

(G)	Alternative Procedures for Construction Work	79

(H)	Procurement of Subcontractors Prior to the GMP Amendment Date	79

(I)	Security for Construction Subcontractor Performance	79

Section 7.5.	TERMINATION, AMENDMENT, ASSIGNMENT AND REPLACEMENT OF MATERIAL SUBCONTRACTS	80

(A)	Termination, Amendment and Assignment	80

(B)	Replacement	80

Article 8

SUBSTANTIAL COMPLETION AND FINAL COMPLETION

Section 8.1.	SUBSTANTIAL COMPLETION DATE CONDITIONS	81

Section 8.2.	CONCURRENCE OR DISAGREEMENT WITH SUBSTANTIAL COMPLETION DATE	82

(A)	Substantial Completion Date Concurrence	82

(B)	Substantial Completion Date Disagreement	82

Section 8.3.	EFFECT OF UNEXCUSED DELAY; EXTENSION PERIOD	82

(A)	Schedule for Completing the Design-Build Work	82

(B)	Unexcused Delay	82

(C)	Delay Liquidated Damages	82

(D)	Failure to Achieve Substantial Completion by End of Extension Period	83

Section 8.4.	FINAL COMPLETION	83

(A)	Requirements	83

(B)	Notice and Report of Final Completion	83

(C)	Achievement of Final Completion	83

Article 9

CONTRACT COMPENSATION

Section 9.1.	COMPENSATION FOR STAGE 1 PRELIMINARY SERVICES	85

(A)	Compensation for Base Stage 1 Preliminary Services	85

(B)	Compensation for Additional Stage 1 Preliminary Services	85

(C)	Payment Requests and Payment	85

(D)	Non-Compliant Stage 1 Preliminary Services	85

(E)	Billing Statement Disputes	85

Section 9.2.	STAGE 2 DESIGN-BUILD PRICE	86

Section 9.3.	STAGE 2 DESIGN-BUILD PRICE PAYMENT PROCEDURE	86

(A)	Payments	86

(B)	Payment Request	86

(C)	City CPMS Project Management System	87

(D)	Review and Payment	87

(E)	Payment Dispute Procedures	88

(F)	Retainage	88

(G)	Cost Control and Reporting	88

(H)	Certification of Amounts Due	89

Section 9.4.	PERMISSIBLE WITHHOLDINGS	89

Section 9.5.	PAYMENT UPON FINAL COMPLETION	90

(A)	Final Completion Payment Request	90

(B)	Final Completion Payment	90

(C)	Final Determination and Approval of Stage 2 Design-Build Price	91

(D)	Completion of Stage 2 Design-Build Work	91

Section 9.6.	NO SUBSTANTIAL COMPLETION, WAIVER OR RELEASE	91

Section 9.7.	CHANGES IN STAGE 2 DESIGN-BUILD PRICE	92

(A)	Determination of Base Guaranteed Maximum Price Adjustment	92

(B)	Design Professional Services	92

(C)	Construction Subcontractor’s Maximum Mark-Up on Subcontracted Construction Work	93

Section 9.8.	COST SUBSTANTIATION	93

(A)	Required Substantiation	93

(B)	Cost Substantiation Certificate	93

Section 9.9.	INTEREST ON OVERDUE OBLIGATIONS	93

Section 9.10.	RETENTION AND AUDIT OF BOOKS AND RECORDS	94

(A)	Books and Records	94

(B)	City Rights to Audit and Examine Payments	94

(C)	Notice and Process	94

(D)	Selection of Auditor or Examiner and Determination of Scope	94

(E)	Preservation of Books and Records	94

(F)	Overpayment	95

Article 10

PROJECT WARRANTIES

Section 10.1.	PROJECT WARRANTIES	96

(A)	Project Warranties Defined	96

(B)	Term of the Project Warranties	96

Section 10.2.	WARRANTY WORK	96

(A)	“Call-Back” Obligations	96

(B)	Right of the City to Proceed with Corrective Action; Design-Builder Liability	96

(C)	No Period of Limitation on Other Obligations	97

(D)	Extension of Warranties	97

(E)	Manufacturers’ Warranties	97

(F)	Performance of Warranty Work	97

(G)	Responsibility for Costs	97

Section 10.3.	PROJECT WARRANTIES NOT EXCLUSIVE	97

Section 10.4.	MANUFACTURERS’ WARRANTIES	98

(A)	Manufacturers’ Warranties Generally	98

(B)	No Limitation on Third Party Warranties	98

Article 11

DISPUTE RESOLUTION

Section 11.1.	DISPUTE RESOLUTION PROCEDURES	99

(A)	Generally	99

(B)	Informal Negotiations	99

(C)	City Contract Representative’s Final Decision	99

(D)	Rights to Request and Decline Non-Binding Mediation	100

(E)	Procedure	100

(F)	Non-Binding Effect	100

(G)	Relation to Judicial Legal Proceedings	100

Section 11.2.	FORUM FOR DISPUTE RESOLUTION	100

Section 11.3.	CONTINUANCE OF PERFORMANCE DURING DISPUTE	100

Article 12

BREACH, DEFAULT, REMEDIES AND TERMINATION

Section 12.1.	REMEDIES FOR BREACH	101

(A)	Generally	101

(B)	No Effect On Contract Obligations	101

(C)	No Duplicative Recovery; Express Remedies	101

Section 12.2.	EVENTS OF DEFAULT BY THE DESIGN-BUILDER	101

(A)	Events of Default Not Requiring Previous Notice or Cure Opportunity for Termination	101

(B)	Events of Default Requiring Previous Notice and Cure Opportunity for Termination	102

(C)	Notice and Cure Opportunity	102

(D)	Other Remedies Upon Design-Builder Event of Default	103

(E)	Relationship to Liquidated Damages	103

Section 12.3.	LIMITATION ON DESIGN-BUILDER LIABILITY	103

(A)	Design-Builder Liability Limit	103

(B)	Liquidated Damages Sub-Limit	104

Section 12.4.	APPLICABILITY AND INTERPRETATION OF THE LIMITATION ON LIABILITY	104

Section 12.5.	EVENTS OF DEFAULT BY THE CITY	104

(A)	Events of Default Permitting Termination	104

(B)	Notice and Cure Opportunity	104

(C)	Other City Breaches Constituting Uncontrollable Circumstances	105

(D)	Effect of Termination	105

Section 12.6.	CITY CONVENIENCE TERMINATION RIGHTS	105

(A)	Convenience Termination Right and Payment	105

(B)	Convenience Termination Payment for Stage 1 Preliminary Services	105

(C)	Convenience Termination Payment for Stage 2 Design-Build Work	105

(D)	Early Work Packages	106

(E)	Settlement of Subcontracts	106

(F)	Payment of Amounts Due as a Result of Convenience Termination	106

(G)	Completion or Continuance by the City	107

(H)	Convenience Termination Rights as Consideration	107

Section 12.7.	OBLIGATIONS OF THE DESIGN-BUILDER UPON TERMINATION	107

Section 12.8.	NO WAIVERS	109

Section 12.9.	WAIVER OF CONSEQUENTIAL AND PUNITIVE DAMAGES	109

Article 13

INSURANCE

Section 13.1.	INSURANCE	110

(A)	Required Insurance	110

(B)	Insurers, Deductibles and the City Rights	110

(C)	Certificates, Policies and Notice	110

(D)	Subcontractors	111

(E)	Maintenance of Insurance Coverage	111

(F)	Compliance with Insurer Requirements	111

(G)	Reductions for Insurance Proceeds	112

Article 14

UNCONTROLLABLE CIRCUMSTANCES

Section 14.1.	UNCONTROLLABLE CIRCUMSTANCES GENERALLY	113

(A)	Extent of Relief Available to the Design-Builder	113

(B)	Mitigation Given Effect	113

(C)	Applicable Law Compliance	113

(D)	Contract Obligations Not Affected; Resumption of Performance	113

Section 14.2.	UNCONTROLLABLE CIRCUMSTANCE CLAIM PROCEDURES	113

(A)	Notice and Written Report	113

(B)	Updates	113

(C)	Submittal of Relief Request	114

(D)	Delay in Notification	114

(E)	Multiple and Overlapping Claims	114

(F)	Burden of Proof and Mitigation	114

(G)	City Response	114

(H)	Agreement or Dispute	114

(I)	Certifications	114

Section 14.3.	UNCONTROLLABLE CIRCUMSTANCES RELIEF	115

Section 14.4.	SCHEDULE RELIEF AND RELATED PRICE RELIEF	115

(A)	Conditions to Schedule Relief	115

(B)	Compensable Uncontrollable Circumstance Delay	116

(C)	Concurrent Delay	116

Section 14.5.	UNUSUALLY SEVERE AND ABNORMAL CLIMACTIC EVENTS	116

Section 14.6.	RELEASE	116

Section 14.7.	UNIT PRICING	116

Article 15

INDEMNIFICATION

Section 15.1.	DESIGN-BUILDER’S OBLIGATION TO INDEMNIFY	117

Section 15.2.	INDEMNIFICATION PROCEDURES	118

(A)	Notice	118

(B)	Consolidation of Claims	118

(C)	Design-Builder Right to Dispute Claim	118

(D)	Rights and Duties of the Parties	118

(E)	The City Indemnitee Rights to Conduct Defense	118

(F)	Transfer of Conduct of Claim to the City Indemnitee	119

(G)	Design-Builder Responsibility for Costs	119

Article 16

SECURITY FOR PERFORMANCE

Section 16.1.	BONDS	120

(A)	Performance and Payment Bonds	120

(B)	Bond Forms	121

(C)	Payment Bond Information	121

(D)	Delivery of Bonds	121

(E)	Surety Requirements	121

(F)	Monitoring of Sureties	122

(G)	Completion of Work	122

Article 17

MISCELLANEOUS PROVISIONS

Section 17.1.	OWNERSHIP OF THE PROJECT	136

Section 17.2.	RELATIONSHIP OF THE PARTIES	136

Section 17.3.	AFFILIATE TRANSACTIONS	136

Section 17.4.	CONTRACT ADMINISTRATION	136

(A)	Administrative Communications	136

(B)	Contract Administration Memoranda	136

(C)	Procedure	137

(D)	Effect	137

Section 17.5.	CONTRACT AMENDMENTS	137

(A)	Amendments Generally	137

(B)	Procedure	137

Section 17.6.	CONTRACT REPRESENTATIVES	137

(A)	Design-Builder Contract Representative and Senior Supervisors	137

(B)	City Contract Representative	138

(C)	City Approvals and Consents	138

Section 17.7.	PROPERTY RIGHTS	138

(A)	Protection from Infringement	138

(B)	Substitutes for Deliverable Material, Process or Equipment	139

(C)	Exceptions to Infringement Protection	139

(D)	Pre-Existing Intellectual Property	139

(E)	Protection of Proprietary Rights of the City	139

Section 17.8.	SBE/LEAP REQUIREMENTS	140

(A)	Small Business Enterprise (SBE)	140

(B)	Local Employment and Apprenticeship Training Program  (LEAP)	140

Section 17.9.	AFFIRMATIVE ACTION REQUIREMENTS	140

(B)	Affirmative Action Statement	140

(C)	Subcontracts	141

Section 17.10.	GENERAL DUTY TO MITIGATE	141

(A)	Mitigation by the Design-Builder	141

(B)	Mitigation by the City	141

Section 17.11.	ASSIGNMENT OF ANTI-TRUST CLAIMS	141

Section 17.12.	ACTIONS OF CITY IN ITS GOVERNMENTAL CAPACITY	141

Section 17.13.	ASSIGNMENT	142

(A)	By the Design-Builder	142

(B)	By the City	142

Section 17.14.	CONFIDENTIALITY	142

(A)	Confidential Nature of Information	142

(B)	Limitation on Use and Disclosure	143

Section 17.15.	LIMITED RECOURSE TO CITY	143

Section 17.16.	BINDING EFFECT	143

Section 17.17.	AMENDMENT AND WAIVER	143

(A)	Contract Amendments	143

(B)	Waiver	143

Section 17.18.	NOTICES	143

(A)	Procedure	143

(B)	City Notice Address	144

(C)	Design-Builder Notice Address	144

Section 17.19.	NOTICE OF LITIGATION	144

Section 17.20.	FURTHER ASSURANCES	145

APPENDICES

- Project and Project Sites

- Stage 1 Preliminary Services

Attachment 2A – Stage 1 Preliminary Services Schedule

- Governmental and Non-Governmental Approvals

- Baseline Design Documents

- General Design-Build Work Requirements

- Design-Build Quality Assurance and Quality Control Requirements

- Design-Build Work Review Procedures

- Stage 2 Design-Build Price

Attachment 8A - Description of General Conditions Costs

Attachment 8B – Stage 2 Design-Builder Personnel Cost Schedule

Attachment 8C - Anticipated Stage 2 Design-Build Cost Schedule

and Design-Builder Contingency

- Substantial Completion and Final Completion

- Insurance Requirements

- Key Personnel and Approved Subcontractors

- Attachment 11A – Key Personnel Organization Chart

- Attachment 11B – Key Personnel Roles

- TRANSACTION FORMS

A.	[Reserved]

B.	Form of Performance Bond (Early Work Package Amendment)

C.	Form of Payment Bond

D.	Form of Performance Bond (GMP Amendment)

[This Page Intentionally Left Blank]

DESIGN-BUILD CONTRACT 
FOR THE

JEFFERSON & HOOD STREET SURFACE
WATER INTERCEPTOR PROJECT

THIS DESIGN-BUILD CONTRACT (“Design-Build Contract”) is entered into on [________, 2017] between the City of Tacoma Washington (the “City”) and [NAME OF DESIGN-BUILDER], a [corporation] organized and existing under the laws of the State of [STATE OF FORMATION] (the “Design-Builder”).

RECITALS

WHEREAS, the existing surface water system in the City’s downtown core does not have sufficient capacity to convey the runoff generated from significant rain events and that improvements are necessary to provide additional surface water capacity to help address flooding in the lower downtown area and to provide additional capacity for growth.  The City plans to construct a new surface water interceptor as well as constructing a new outfall to the Thea Foss Waterway, or possibly upsizing the existing outfall and potentially to construct certain water and/or wastewater pipelines [Note: The decision as to whether to include water and/or wastewater pipelines to be addressed in the GMP Amendment] (the “Project”);

WHEREAS, the City has determined that it is in the City’s best interests to contract with a private entity to design and construct the Project using the progressive design-build project delivery method in accordance with Revised Code of Washington (“RCW”) Chapter 39.10; (the “Enabling Law”);

WHEREAS, pursuant to the Enabling Law, the City issued a Request for Qualifications, Jefferson & Hood Street Surface Water Interceptor, Specification No. ES17-0269F on July 12, 2017 (as amended by addenda issued on July 13, 2017, August 3, 2017 and August 15, 2017 (the “RFQ”), in order to short-list the design-build entities whose proposals would be evaluated, selected or rejected on a best value basis;

WHEREAS, statements of qualifications submitted in response to the RFQ were received on August 29, 2017, from four entities;

WHEREAS, the City, in accordance with the requirements and evaluation criteria set forth in the RFQ, selected three entities (including the Design-Builder) to participate in the second phase of the procurement process;

WHEREAS, pursuant to the Enabling Law, the City undertook the second phase of the competitive process by issuing a Request for Proposals, Jefferson and Hood Street Surface Water Interceptor Specification No. ES17-0269F on October 23, 2017 as amended by addenda issued on [______________] (the “RFP”);

WHEREAS, proposals submitted in response to the RFP were received on December [__], 2017, from [___] entities, including the Design-Builder;

WHEREAS, the City’s selection committee engaged in a comprehensive evaluation of the competing proposals in accordance with the evaluation factors and selection criteria set forth in the RFP;

WHEREAS, the City’s selection committee determined that the proposal submitted by the Design-Builder was the most advantageous to the City considering the evaluation factors set forth in the RFP, subject to the negotiation of an acceptable contract;

WHEREAS, in January 2017], negotiations were initiated with the Design-Builder, which negotiations have concluded with this Design-Build Contract;

WHEREAS, on [________, 2018], the City Council adopted Resolution Number [______] authorizing the execution and delivery of this Design-Build Contract;

WHEREAS, the Project will be designed and constructed by the Design-Builder pursuant to the terms of this Design-Build Contract and the appendices attached hereto; and

WHEREAS, the City desires to receive, and the Design-Builder desires to provide design and construction services under the terms of this Design-Build Contract.

NOW, THEREFORE, in consideration of the mutual covenants herein contained, the parties hereto, intending to be legally bound, agree as follows:

# DEFINITIONS AND INTERPRETATION

## DEFINITIONS.

As used in this Design-Build Contract, the following terms shall have the meanings set forth below:

“Additional Stage 1 Preliminary Services” has the meaning specified in (B).

“Affiliate” means any person directly or indirectly controlling or controlled by another person, corporation or other entity or under direct or indirect common control with such person, corporation or other entity.

“Anticipated Stage 2 Design-Build Cost Estimate” means the detailed, itemized list of prices and costs that establishes the value of each part or component of the Stage 2 Design-Build Work, to be developed by the Design-Builder in accordance with the Contract Standards, and to serve as the basis for tracking contingency and line item savings of the Stage 2 Design-Build Price during the Stage 2 Design-Build Period.

“Appendix” means any of the Appendices and, as applicable, any attachments thereto, that are appended to this Design-Build Contract and identified as such in the table of contents to this Design-Build Contract.

“Applicable Law” means:

###### Any federal, state, City or local law, statute, ordinance, code, rule or regulation;

###### Any formally adopted and generally applicable rule, requirement, determination, standard, policy, implementation schedule, or other order of any Governmental Body having appropriate jurisdiction;

###### Any established interpretation of law or regulation utilized by an appropriate Governmental Body if such interpretation is documented by such Governmental Body and generally applicable;

###### Any Governmental Approval; and

###### Any consent order or decree, settlement agreement or similar agreement between the City and any Governmental Body;

in each case having the force of law and applicable from time to time, over the Project, the Contract Obligations or any other transaction contemplated hereby.

“Approved Subcontractors” means the subcontractors identified in Appendix 11.

“Base Guaranteed Maximum Price” means the initial amount approved by the City as the Guaranteed Maximum Price pursuant to Appendix 8.

“Base Guaranteed Maximum Price Adjustment” means an adjustment to the Base Guaranteed Maximum Price made in accordance with and subject to the terms and conditions of Appendix 8.

“Base Stage 1 Preliminary Services” means those services designated as Base Stage 1 Preliminary Services in Appendix 2.

“Baseline Date” means the Contract Date; except that:

###### With respect to any Design-Build Work authorized pursuant to an Early Work Package Amendment, the Baseline Date shall mean the Early Work Package Amendment Date; and

###### Upon the execution and delivery of a GMP Amendment, the Baseline Date shall mean the GMP Amendment Date.

“Baseline Design Documents” means the Specifications, Drawings, and other technical requirements for the performance of the Design-Build Work developed by or on behalf of the Design-Builder through the performance of the Stage 1 Preliminary Services and established in any Early Work Package Amendment or GMP Amendment, as applicable and including the Technical Standards set forth in Appendix 4 hereto.

“Baseline Design Requirements Change” means a change to the Baseline Design Documents made by a Change Order pursuant to Section 6.8, Section 6.9 or a Work Change Directive pursuant to Section 6.11:

###### As a result of a Design-Builder request agreed to by the City;

###### Due to Uncontrollable Circumstances;

###### As a result of a term or condition imposed by a Governmental Body; or

###### At the direction of the City.

“Basis of Design Report” or “BDR” means the report so designated to be prepared by the Design-Builder pursuant to the Preliminary Services set forth in Appendix 2.

“Bankruptcy Law” means the United States Bankruptcy Code, 11 U.S.C. 101 et seq., as amended from time to time and any successor statute thereto.  “Bankruptcy Law” shall also include any similar state law relating to bankruptcy, insolvency, the rights and remedies of creditors, the appointment of receivers or the liquidation of companies and estates that are unable to pay their debts when due.

“BNSF” means the BNSF Railway Company.

“BNSF Approval” means the approval required to be granted by BNSF regarding construction of the Project in the BNSF right of way.

“BNSF Requirements” means the written and oral requirements of BNSF relating to the Design-Build Work to be performed near, next to or under the railway owned by BNSF.

“Books and Records” has the meaning specified in (A).

“Business Day” means a day other than a Saturday, Sunday or an official the City holiday.

“CERCLA” means the Comprehensive Environmental Response, Compensation, and Liability Act, 42 U.S.C. 9601 et seq., and applicable regulations promulgated thereunder, each as amended from time to time.

“Change in Law” means any of the following acts, events or circumstances to the extent that compliance with the change materially expands the scope, interferes with, delays or increases the cost of performing the obligations of the Design-Builder:

###### Except as provided below with respect to the exclusions from the definition of “Change in Law”, the adoption, amendment, promulgation, issuance, modification, repeal or written change in administrative or judicial interpretation of any Applicable Law on or after the Baseline Date, unless such Applicable Law was on or prior to the Baseline Date duly adopted, promulgated, issued or otherwise officially modified or changed in interpretation, in each case in final form, to become effective without any further action by any Governmental Body;

###### Except as provided below with respect to the exclusions from the definition of “Change in Law”, the order or judgment of any Governmental Body issued on or after the Baseline Date (unless such order or judgment is issued to enforce compliance with Applicable Law which was effective as of the Baseline Date) to the extent such order or judgment is not the result of willful or negligent action, error or omission or lack of reasonable diligence of the Design-Builder; provided, however, that the contesting in good faith or the failure in good faith to contest any such order or judgment shall not constitute or be construed as such a willful or negligent action, error or omission or lack of reasonable diligence; or

###### Except as provided below with respect to the exclusions from the definition of “Change in Law”, the denial of an application for, a delay in review, issuance or renewal of, or the suspension, termination or interruption of any Governmental Approvals, or the imposition of a term, condition or requirement on or after the Baseline Date in connection with the issuance, renewal or failure of issuance or renewal of any Governmental Approval, to the extent such occurrence is not the result of willful or negligent action, error or omission or a lack of reasonable diligence of the Design-Builder; provided, however, that the contesting in good faith or the failure in good faith to contest any such occurrence shall not be construed as such a willful or negligent action or lace of reasonable diligence.

It is specifically understood, however, that none of the following shall constitute a “Change in Law”:

###### Acts, events and circumstances with respect to Governmental Approvals to the extent the Design-Builder has assumed the permitting risk under Section 6.5;

###### Any Change in Law relating to Taxes other than a change in law pertaining to State sales Taxes;

###### A change in the nature or severity of the actions typically taken by a Governmental Body to enforce compliance with Applicable Law that was in effect as of the Contract Date;

###### Any increase in any fines or penalties provided for under Applicable Law in effect as of the Baseline Date;

###### Any Change in Law (including the enactment of any statute, or the promulgation of any regulation) the terms and conditions of which do not impose more stringent or burdensome requirements on the Design-Builder than are imposed by the Contract Standards in effect as of the Baseline Date;

###### The formal adoption by the City of Washington State Department of Transportation specifications; or

###### Any event that affects generally applicable working conditions or standards that is not specific to the water pipeline construction industry or the Project.

“Change Order” means a written order issued by the City and agreed to in writing by the Design-Builder prior to Final Completion making a Baseline Design Requirements Change, a Base Guaranteed Maximum Price Adjustment, adjustment to the Scheduled Substantial Completion Date or any other change to the terms and conditions of the Contract Documents.  A Change Order shall be deemed to constitute a Contract Amendment.

“City” means the City of Tacoma, Washington, a municipal corporation organized and existing and by virtue of the laws of the State.

“City Contract Representative” has the meaning specified in subsection 17.6(B).

“City Fault” means any breach (including the untruth or breach at the time made of any City representation or warranty herein set forth), failure, non-performance or non-compliance by the City under this Design-Build Contract with respect to its obligations and responsibilities under this Design-Build Contract to the extent not directly attributable to any Uncontrollable Circumstance and which materially and adversely affects the Design-Builder’s rights, obligations or ability or costs to perform under this Design-Build Contract.

“City Indemnitee” has the meaning specified in Section 15.1.

“City Managed Governmental Approvals” means those Governmental Approvals for which the City is the application manager, as designated in Appendix 3.

“City Property” means any structures, improvements, equipment, or other real or personal property owned, leased, operated, maintained, or occupied by the City.

“Construction” means that part of the Design-Build Work consisting of the construction of the Project as required by the Contract Documents, including furnishing, installing or incorporating Supplies into the Project.

“Construction Commencement Date” means the date, following satisfaction of the Construction Commencement Date Conditions by the Design-Builder, upon which the Design-Builder shall have the right to proceed with the Construction of the Project, as determined in accordance with subsection 6.1(A).

“Construction Commencement Date Conditions” has the meaning specified in (A).

“Construction Phasing Plan” means the Design-Builder’s plan for Construction sequencing site access, to be developed as part of the Stage 1 Preliminary Services in accordance with the requirements set forth in Appendix 2.

“Contaminated Media Management Plan” means the Design-Builder’s plan for the management of contaminated soils and groundwater, to be developed as part of the Stage 1 Preliminary Services in accordance with the requirements set forth in Appendix 5.

“Contract Administration Memorandum” has the meaning specified in (B).

“Contract Amendment” has the meaning specified in (A).

“Contract Compensation” means the Stage 1 Preliminary Services Fee and the Stage 2 Design-Build Price.

“Contract Date” means the date this Design-Build Contract is executed and delivered by the parties hereto.

“Contract Documents” means:

###### This Design-Build Contract and all Appendices;

###### Any amendments to the Design-Build Contract including the GMP Amendment and any Early Work Package Amendment;

###### The Baseline Design Documents;

###### Any Change Order, Work Change Directive or other Contract Amendment;

###### Any Notice to Proceed;

###### Any Contract Administration Memoranda; and

###### The Issued for Construction Drawings and Specifications.

“Contract Obligations” means everything required to be furnished and done for and relating to the Design-Build Work and the Warranty Work pursuant to the Contract Documents.

“Contract Standards” means the standards, terms, conditions, methods, techniques and practices imposed or required by:

###### Applicable Law;

###### The Baseline Design Documents;

###### The Substantial Completion Standards;

###### Good Engineering and Construction Practice;

###### The Insurance Requirements’

###### All plans required to be developed by the Design-Builder pursuant to the requirements of this Design-Build Contract;

###### Applicable BNSF Requirements;

###### Applicable Washington State Department of Transportation Requirements;

###### Applicable Federal Highway Administration (“FHWA”) Requirements; and

###### Any other standard, term, condition or requirement specifically provided in the Contract Documents to be observed by the Design-Builder.

Section 1.2(R) shall govern issues of interpretation related to the applicability, stringency and consistency of the Contract Standards.

“Cost Substantiation” means the process of providing evidence of actual costs in accordance with Section 9.8.

“Deliverable Material” means the Stage 1 Preliminary Services Deliverable Material and the Stage 2 Design-Build Work Deliverable Material.

“Design-Build Contract” means this Design-Build Contract for the Jefferson & Hood Street Surface Water Interceptor Project between the Design-Builder and the City, including the Appendices and all other Contract Documents, as the same may be amended or modified from time to time in accordance herewith.

“Project Manager” has the meaning specified in (A).

“Design-Build Work” means everything required to be furnished and done for and relating to the design and construction of the Project pursuant to the Contract Documents.  Design-Build Work includes the employment and furnishing of all labor, materials, equipment, supplies, tools, scaffolding, transportation, Utilities, insurance, temporary facilities and other things and services of every kind whatsoever necessary for the full performance and completion of the Design-Builder’s design, engineering, permitting, procurement, construction, , Testing, and related obligations with respect to the construction of the Project under the Contract Documents, including all completed structures, assemblies, fabrications, acquisitions and installations, all testing, and all of the Design-Builder’s administrative, accounting, recordkeeping, notification and similar responsibilities of every kind whatsoever under the Contract Documents pertaining to such obligations. Design-Build Work includes the Stage 1 Preliminary Services, all work performed pursuant to Early Work Package Amendments, the Stage 2 Design-Build Work and the Warranty Work.  A reference to Design-Build Work shall mean any part and all of the Design-Build Work unless the context otherwise requires, and shall include all Design-Build Work authorized by Change Order or Work Change Directive.

“Design-Builder” means [NAME OF DESIGN-BUILDER], a [TYPE OF ENTITY] organized and existing under the laws of [JURISDICTION WHERE ORGANIZED], and its permitted successors and assigns.

“Design-Builder Contingency” has the meaning specified in Appendix 8.

“Design-Builder Contract Representative” has the meaning specified in (A).

“Design-Builder Fault” means:

###### A breach by the Design-Builder of any of its obligations under this Design-Build Contract;

###### A breach of any representation or warranty made by the Design-Builder under this Design-Build Contract;

###### Willful misconduct of the Design-Builder or any other Design-Builder Person; or

###### A negligent act or omission of the Design-Builder or any other Design-Builder Person.

“Design-Builder Fee” has the meaning specified in Appendix 8.

“Design-Builder Person” means each of the following:

###### The Design-Builder;

###### Any director, officer, employee or agent of the Design-Builder in each case acting as such;

###### Any Subcontractor and any representative, advisor (including any legal and financial advisor) of the Design-Builder, in any such person’s capacity as a provider of services directly or indirectly to the Design-Builder in connection with the Project; and

###### Anyone for whose acts any of the foregoing may be legally or contractually liable in connection with this Design-Build Contract, including officers, directors, employees, representatives, agents, consultants, and contractors.

“Design Professional Services” means that part of the Design-Build Work consisting of the preparation of plans, drawings and specifications for the Project by licensed professional engineering, architectural and land surveying firms, as well as all other services required to be performed by licensed design professionals as part of the Design-Build Work for the design and engineering of the Project, including professional engineering, architectural and land surveying services.

“Design Professional Services Firm” means any person providing Design Professional Services.

“Differing Site Conditions” means (a) actual subsurface or latent physical subsurface conditions along the Surface Water Conveyance Pipeline Rights of Way or at the Outfall that differ materially from those indicated in the Reference Documents or those documents prepared by the Design-Builder as part of the Stage 1 Preliminary Services, or (b) unknown physical subsurface conditions at the of an unusual nature, which differ materially from those ordinarily encountered and generally recognized as inherent in work of the character required herein; provided, however, that the term “Differing Site Conditions” excludes: (1) conditions of which the Design-Builder had actual or constructive knowledge as of the Baseline Date (including through review of the Reference Documents and those documents prepared by the Design-Builder as part of the Stage 1 Preliminary Services as well as conditions that are evident from the location, topography and nature of the Project Sites); and (2) conditions that should have been discovered through a reasonable investigation performed prior to the Baseline Date and through the geotechnical, hydrogeology, and contaminated soil and water management work required to be performed by the Design-Builder as part of the Stage 1 Preliminary Services.

“Drawings” means drawings, diagrams, illustrations, schedules and other data that show the scope, extent, and character of the Design-Build Work, as prepared by or on behalf of the Design-Builder.

“Early Work Package” has the meaning specified in (A).

“Early Work Package Amendment” has the meaning specified in (A).

“Early Work Package Amendment Date” means the date that an Early Work Package Amendment is executed and delivered by the parties.

“Early Work Package Price” means the price established in any Early Work Package for the portion of the Design-Build Work to be performed thereunder.

“Early Work Package Submittal” has the meaning specified in (A).

“Encumbrances” means any Lien, lease, mortgage, security interest, charge, judgment, judicial award, attachment or encumbrance of any kind with respect to the Project.

“Engineer-of-Record” means the professional engineer licensed in the State in good standing who is designated by the Design-Builder and acceptable to the City, acting reasonably, as the engineer responsible for the preparation, signing, dating, sealing and issuing of the engineering documents relating to all or a portion of the Design-Build Work.

“EPA” means the United States Environmental Protection Agency and any successor agency.

“Environmental Mitigation Measures” means any environmental mitigation measures set forth in, or required in connection with, a Governmental Approval.

“Event of Default” means, with respect to the Design-Builder, those items specified in Section 12.2 and, with respect to the City, those items specified in Section 12.5.

“Existing Outfall” means the City of Tacoma’s existing outfall number 230.

“Expiration Date” means the last day of the Warranty Period.

“Extension Period” means 60 days following the Scheduled Substantial Completion Date.

“Fees and Costs” means reasonable fees and expenses of employees, attorneys, architects, engineers, expert witnesses, contractors, consultants and other persons, and costs of transcripts, printing of briefs and records on appeal, copying and other reimbursed expenses, and expenses reasonably incurred in connection with investigating, preparing for, defending or otherwise appropriately responding to any Legal Proceeding.

“Federal Highway Administration Requirements” means the written and oral requirements of Federal Highway Administration regarding construction of the Project below the elevated portion of I-705.

“Final Completion” means completion of the Design-Build Work, including all construction of the Project, in compliance with the Contract Documents and the requirements of Section 8.4.

“General Conditions Costs” has the meaning specified in Appendix 8.

“General Conditions Fee” has the meaning specified in Appendix 8.

“Geotechnical Baseline Report” means the report so designated to be prepared by the Design-Builder pursuant to Stage 1 Preliminary Services set forth in Appendix 2.

“Geotechnical Evaluation Report” means the report so designated to be prepared by the Design-Builder pursuant to Stage 1 Preliminary Services set forth in Appendix 2.

“GMP Amendment” has the meaning specified in (B).

“GMP Amendment Date” has the meaning specified in (B).

“GMP Submittal” has the meaning specified in Section 5.7.

“Good Engineering and Construction Practice” means those methods, techniques, standards and practices which, at the time they are to be employed and in light of the circumstances known or reasonably believed to exist at such time, are generally recognized and accepted as good design, engineering, equipping, installation, construction, commissioning and testing practices as observed for storm water pipelines and, as applicable, water and sewer pipelines, as followed in the State.

“Governmental Approval” means any permit, license, authorization, consent, certification, exemption, ruling, entitlement or approval issued by a Governmental Body of whatever kind and however described, which is required under Applicable Law to be obtained or maintained by any person with respect to the Design-Build Work, including any City Managed Governmental Approvals.

“Governmental Approval Application Date” means the applicable date set forth in the Governmental Approvals Schedule Table.

“Governmental and Non-Governmental Approvals Table” means Table A3-1 and A3-2 of Appendix 3.

“Governmental Body” means any federal, State, City, regional or local legislative, executive, judicial or other governmental board, department, agency, authority, commission, administration, court or other body (including the City, acting in its governmental capacity other than as a party to this Design-Build Contract), or any official thereof, having jurisdiction in any way over or in respect of any aspect of the performance of this Design-Build Contract or the Project.

“Guaranteed Maximum Price” has the meaning specified in Appendix 8.

“Hazardous Material” means any waste, substance, object or material deemed hazardous under Applicable Law including, without limitation, “hazardous substances” as defined under CERCLA and “hazardous waste” as defined under RCW.

“Intellectual Property” means any trade secrets, proprietary rights, patents, copyrights or trademarks recognized under Applicable Law.

“Insurance Requirement” means any rule, regulation, code, or requirement issued by any insurance company that has issued a policy of Required Insurance under this Design-Build Contract or by any insurance company that has issued a policy of insurance required to be obtained and maintained by the City in connection with this Design-Build Contract, compliance with which is a condition to the effectiveness of such policy.

“Issued for Construction Drawings and Specifications” means the Drawings and Specifications which have been accepted by the City as final Drawings and Specifications for the commencement of Construction of all or any portion of the Design-Build Work.

“Legal Proceeding” means every action, suit, litigation, arbitration, administrative proceeding, and other legal or equitable proceeding having a bearing upon this Design-Build Contract, and all appeals therefrom.

“Lien” means any and every lien against the Project or against any monies due or to become due from the City to the Design-Builder under this Design-Build Contract, for or on account of the Contract Obligations, including mechanics’, materialmen’s, laborers’ and lenders’ liens.

“Loss-and-Expense” means any and all actual loss, liability, forfeiture, obligation, damage, fine, penalty, judgment, Lien, deposit, Tax, charge, assessment, cost or expense, including all Fees and Costs, relating to third party claims for which the Design-Builder is obligated to indemnify the City Indemnitees pursuant to this Design-Build Contract.

“Mediator” means any person serving as a third-party mediator of disputes hereunder pursuant to Section 11.1.

“Monthly Progress Report” has the meaning specified in Section 4.9.

“Non-Binding Mediation” means the voluntary system of dispute resolution through third-party mediation established by Section 11.1 for the resolution of any dispute arising under this Design-Build Contract.

“Non-Governmental Approvals” means the BNSF Approval.

“Notice of Final Completion” has the meaning set forth in (B).

“Notice to Proceed” or “NTP” means a written notice issued by the City Contract Representative authorizing the Design-Builder to commence performing a portion of the Design-Build Work, as specified in the Notice to Proceed.

“OSHA” means the Occupational Safety and Health Act of 1970, 29 U.S.C. Section 650 et seq., including the applicable regulations promulgated thereunder, as amended or superseded from time to time.

“Outfall” means the portion of the Project where the stormwater will be discharged into the Thea Foss Waterway.

“Outfall Site” means the site where the Outfall will be located pursuant to the Baseline Design Documents.

“Overdue Rate” means the maximum rate of interest permitted by the laws of the State, if applicable, or the Prime Rate, whichever is lower.

“Owner Representative” means any individual or firm, or team of individuals or firms, under contract with the City, including subcontractors, and designated by the City from time to time as part of its management-consulting, engineering or construction management team for purposes of administering this Design-Build Contract on behalf of the City.

“Payment Bond” means the labor and materials payment bond provided by the Design-Builder as described in and maintained pursuant to this Design-Build Contract and in the form set forth in the Transaction Forms.

“Payment Request” means a written submission by the Design-Builder in the form approved by the City and accompanied by all required supporting documentation, requesting payment hereunder of any portion of the Contract Compensation.

“Performance Bond” means the performance bond provided by the Design-Builder as described in and maintained pursuant to this Design-Build Contract and in the form set forth in the Transaction Forms.

“Permitted Encumbrances” means, as of any particular time, any one or more of the following:

###### Encumbrances for utility charges, taxes, rates and assessments not yet delinquent or, if delinquent, the validity of which is being contested diligently and in good faith by the Design-Builder and against which the Design-Builder has established appropriate reserves in accordance with generally accepted accounting principles;

###### Any encumbrance arising out of any judgment rendered that is being contested diligently and in good faith by the Design-Builder, the execution of which has been stayed or against which a bond or bonds in the aggregate principal amount equal to such judgments shall have been posted with a financially-sound insurer and which does not have a material and adverse effect on (a) the ability of the Design-Builder to construct the Project in accordance with this Design-Build Contract or (b) the ability of the City to utilize the Project;

###### Any encumbrance arising in the ordinary course of business imposed by law dealing with materialmen’s, mechanics’, workmen’s, repairmen’s, warehousemen’s, landlords’, vendors’ or carriers’ encumbrances created by law, or deposits or pledges which are not yet due or, if due, the validity of which is being contested diligently and in good faith by the Design-Builder and against which the Design-Builder has established appropriate reserves or bonded against, at the City’s request;

###### Servitudes, licenses, leases, easements, restrictions, rights-of-way, rights in the nature of easements or similar items which shall not individually or in the aggregate materially and adversely impair (a) the construction of the Project by the Design-Builder in accordance with this Design-Build Contract or (b) the operation of the Project by the City;

###### Applicable zoning and building bylaws and ordinances, municipal bylaws and regulations, and restrictive covenants, which individually or in the aggregate do not materially interfere with and adversely affect (a) the construction of the Project by the Design-Builder in accordance with this Design-Build Contract or (b) the utilization of the Project by the City;

###### Encumbrances which are created on or before the Contract Date;

###### Encumbrances which are created by a Change in Law on or after the Contract Date; and

###### Any encumbrance created by the City.

“Preliminary Design Documents” means the Design-Builder’s plans, technical specifications, drawings and other documents prepared in connection with the Stage 1 Preliminary Services, including the Baseline Design Documents.

“Prime Rate” means the prime rate as published in The Wall Street Journal (Eastern Edition), or a mutually agreeable alternative source of the prime rate if it is no longer published in The Wall Street Journal (Eastern Edition) or the method of computation thereof is substantially modified.

“Project” means the Surface Water Conveyance Pipeline, the Outfall, [the Water Main,] the Surface Water Conveyance Pipeline Rights of Way, the Outfall Site and all Contract Obligations required to be performed under the Contract Documents.

“Project Schedule” means the Stage 1 Preliminary Services Schedule and the Stage 2 Design-Build Work Schedule.

“Project Sites” means the Outfall Site and the Surface Water Conveyance Pipeline Rights of Way.

“Project Warranties” has the meaning specified in (A).

“Proposal” means the proposal submitted by the Design-Builder on November __, 2017, in response to the RFP.

“Punch List” has the meaning specified in (A).

“RCRA” means the Resource Conservation and Recovery Act, 42 U.S.C.A. 6901 et seq., and applicable regulations promulgated thereunder, each as amended from time to time.

“Reference Documents” means the documents listed as reference documents in Appendix 1 Table A1-1 to this Design-Build Contract.

“Regulated Site Condition” means, and is limited to:

###### The presence or habitat of a species that is classified under Applicable Law as endangered, rare, threatened, of special concern, or similarly subject to the protections of Applicable Law;

###### The presence anywhere in, on or under the Project Sites of historical, archeological, religious architectural or other cultural artifacts, relics, vestiges, remains or objects of antiquity that are regulated by Applicable Law;

###### The presence anywhere in, on or under the Project Sites on the Baseline Date of wells or underground storage tanks for the storage of chemicals, petroleum products or Regulated Substances; and

###### The presence of Regulated Substances in environmental media anywhere in, on or under the Project Sites (including presence in surface water, groundwater, soils or subsurface strata), but not including Regulated Substances used, stored or otherwise brought to the Project Sites by the Design-Builder or any Subcontractor as provided in (A).

“Regulated Substance” means:

###### Any oil, petroleum or petroleum product; and

###### Any pollutant, contaminant, hazardous substance, hazardous material, toxic substance, toxic pollutant, solid waste, municipal waste, industrial waste or hazardous waste that is defined as such by and is subject to regulation under any Applicable Law.  Regulated Substances include Hazardous Materials.

“Related Projects” has the meaning specified in (B).

“Relief Request Notice” has the meaning specified in (C).

“Request for Proposals” or “RFP” means the City’s Request for Proposals, Jefferson & Hood Street Surface Water Interceptor Project, Specification  No. ES17-0269F, issued on October 23, 2017, as amended.

“Request for Qualifications” or “RFQ” means the City’s Request for Qualifications, Jefferson & Hood Street Surface Water Interceptor Project, Specification No. ES17-0269F, issued on July 12, 2017, as amended.

“Required Insurance” means the insurance policies and coverage required to be provided by the Design-Builder under this Design-Build Contract, as set forth in Section 13.1 and Appendix 10.

“Restricted Person” means any person who (or any member of a group of persons acting together, any one of which):

###### Is disbarred, suspended, or otherwise disqualified from federal, State, or City contracting for any services similar in nature to the Contract Obligations;

###### Was or is subject to any material claim of the United States, State, or City in any proceedings (including regulatory proceedings) which have been concluded or are pending at the time at which the determination of whether the person falls within this definition is being made, and which (in respect of any such pending claim, if it were to be successful) would, in the City’s view, in either case, be reasonably likely to materially affect the ability of the Design-Builder to perform its obligations under this Design-Build Contract;

###### In the case of an individual, he or she (or in the case of a legal entity, any of the members of the board of directors or its senior executive managers) has been sentenced to imprisonment or otherwise given a custodial sentence for any criminal offense (other than minor traffic offenses or misdemeanor) less than 5 years prior to the date at which the determination of whether the person falls within this definition is being made;

###### Has, directly or indirectly, its principal or controlling office in a country that is subject to any economic or political sanctions imposed by the United States for reasons other than its trade or economic policies; or

###### Has as its primary business the illegal manufacture, sale, distribution or promotion of narcotic substances or arms, or is or has been involved in terrorism.

“Safety Manager” has the meaning specified in (A).

“Scheduled Substantial Completion Date” means the date which is [__] days following the GMP Amendment Date, as such Scheduled Substantial Completion Date may be adjusted in accordance with Section 14.4.  [Note: To be negotiated as part of GMP Amendment.]

“Security Instruments” means the Performance Bond and the Payment Bond.

“Senior Supervisors” has the meaning specified in (A).

“Separate Contractor” means any person or entity under contract with the City for the performance of work associated with the Related Projects or under contract with a non-City owner to perform work at the Project Sites.

“Specifications” means the documents prepared by or on behalf of Design-Builder comprising written technical descriptions of materials, equipment, construction systems, standards, and workmanship for the Design-Build Work and certain administrative details applicable thereto.

“Stage 1 Preliminary Services Health and Safety Plan” means the Design-Builder’s plan for health and safety in implementing the Stage 1 Preliminary Services including related field work as set forth as an attachment to Appendix 2 hereto.

“Stage 1 Preliminary Services” means the Base Stage 1 Preliminary Services and the Additional Stage 1 Preliminary Services performed by the Design-Builder hereunder prior to the GMP Amendment Date.

“Stage 1 Preliminary Services Deliverable Material” means all documents, reports, studies, surveys, computer programs, warranties, manuals, submittals, licenses and other documents and materials required to be delivered by the Design-Builder to the City in the performance of the Stage 1 Preliminary Services pursuant to this Design-Build Contract, including the Preliminary Design Documents.

“Stage 1 Preliminary Services Fee” has the meaning specified in Section 9.1 and Appendix 2

“Stage 1 Preliminary Services Period” means the period between the Contract Date and the GMP Amendment Date.

“Stage 1 Preliminary Services Quality Management Plan” means the Design-Builder’s plan for quality assurance and quality control in implementing the Preliminary Services set forth as an attachment to Appendix 6.

“Stage 1 Preliminary Services Schedule” has the meaning specified in Section 5.3.

“Stage 1 Preliminary Services Tasks” means the tasks specified in Appendix 2.

“Stage 2 Design-Build Costs” has the meaning specified in Appendix 8.

“Stage 2 Design-Build Period” means the period between the GMP Amendment Date and through the date Final Completion is achieved.

“Stage 2 Design-Build Price” has the meaning specified in Appendix 8.

“Stage 2 Design Documents” means the Design-Builder’s plans, technical specifications, drawings, record drawings and other design documents prepared following the GMP Amendment Date (or in connection with any Early Work Package, the applicable Early Work Package Amendment Date) in connection with the Stage 2 Design-Build Work, including:

###### Specifications, Drawings and all other work product generated through the performance of the Design Professional Services following the establishment of the Baseline Design Documents; and

###### All technical criteria, written descriptions and design data necessary for obtaining Governmental Approvals and performing Construction, such as shop drawings, product data and samples whether or not such documents are required to be prepared by licensed design professionals.

“Stage 2 Design-Build Work” means all Design-Build Work performed by the Design-Builder hereunder on and after (1) the GMP Amendment Date and (2) the Early Work Package Amendment Date in connection with any Early Work Package.

“Stage 2 Design-Build Work Deliverable Material” means all documents, reports, studies, surveys, computer programs, warranties, manuals, submittals, licenses and other documents and materials required to be delivered by the Design-Builder to the City in the performance of the Stage 2 Design-Build Work pursuant to this Design-Build Contract, including the Stage 2 Design Documents.

“Stage 2 Design-Build Work Health and Safety Plan” means the Design-Builder’s plan for health and safety in implementing the Stage 2 Design-Build Work, to be developed as part of the Stage 1 Preliminary Services in accordance with the requirements set forth in Appendices 2 and 5.

“Stage 2 Design-Build Work Quality Management Plan” means the Design-Builder’s plan for quality assurance and quality control in implementing the Design-Build Work to be developed as a Preliminary Service pursuant to Appendix 2.

“Stage 2 Design-Build Period” means the period from and including the GMP Amendment Date (or with respect to any Design-Build Work authorized pursuant to an Early Work Package Amendment, the applicable Early Work Package Amendment Date) through the date Final Completion is achieved.

“Stage 2 Design-Build Work Schedule” means the Design-Builder’s critical path method completion schedule for the performance of the Stage 2 Design-Build Work, as set forth as an attachment to Appendix 5 on the GMP Amendment Date and as updated and maintained by the Design-Builder in accordance with (F).

“State” means the State of Washington.

“Subcontract” means any contract entered into by the Design-Builder, or a Subcontractor of the Design-Builder of any tier, with one or more persons in connection with the carrying out of the Design-Builder’s obligations under this Design-Build Contract, whether for the furnishing of labor, materials, equipment, supplies, services or otherwise, including  contracts for Construction, Design Professional Services and Supplies.

“Subcontracting Plan” means the Design-Builder’s plan for entering into Subcontracts, to be developed as part of the Stage 1 Preliminary Services in accordance with the requirements set forth in Appendix 2 and the attachment to Appendix 11 and finalized on the GMP Amendment Date in accordance with (C).

“Subcontractor” means any person, other than the Design-Builder, that enters into a Subcontract, including Construction Subcontractors, Design Professional Services Firms and Suppliers.

“Substantial Completion” means demonstration by the Design-Builder in accordance with Article 8 and Appendix 9 that the Project has met all of the Substantial Completion Conditions, as certified by the Design-Builder pursuant to Section 8.2 (E) and agreed to by the City pursuant to (A).

“Substantial Completion Date” means the date on which Substantial Completion of the Project occurs or is deemed to have occurred under Article 8.

“Substantial Completion Date Conditions” means the preconditions for the achievement of Substantial Completion by the Design-Builder, as set forth in Section 8.1.

“Supplier” means a manufacturer, distributor, materialman, fabricator, vendor or other supplier having a Subcontract to furnish Supplies.

“Supplies” means materials, equipment or other supplies furnished in connection with the Design-Build Work.

“Surety” means the surety company issuing the Performance Bond, the Payment Bond, as applicable.

“Surface Water Conveyance Pipeline” means the pipeline for the conveyance of surface water from the point of connection identified in Appendix 1 to and including the Outfall, including all related structures, pipes, valves and equipment; as generally described in Appendix 1 and more particularly described in the Baseline Design Documents, to be designed, constructed, and tested by the Design-Builder in accordance with the Contract Documents.

“Surface Water Conveyance Pipelines Rights of Way” means the right of access to the real property, as generally described in Appendix 1 and more particularly described in the Baseline Design Documents, on or under which the Surface Water Conveyance Pipelines are to be constructed by the Design-Builder.

“Tax” means any tax, fee, levy, duty, impost, charge, surcharge, assessment or withholding, or any payment-in-lieu thereof, and any related interest, penalty or addition to tax.

“Term” has the meaning set forth in Section 3.1.

“Termination Date” means the last day of this Design-Build Contract resulting from a termination under any provision hereof.

“Traffic Control Plan” means the Design-Builder’s plan for traffic control, to be developed as part of the Preliminary Services in accordance with the requirements set forth in Appendix 2.

“Transaction Form” means any of the transaction forms identified in the table of contents to this Design-Build Contract.

“Unallowable Costs” has the meaning specified in Appendix 8.

“Uncontrollable Circumstance” means any act, event or condition that (1) is beyond the reasonable control of the party relying on it as a justification for not performing an obligation or complying with any condition required of the party under this Design-Build Contract, and (2) materially expands the scope, interferes with, delays or increases the cost of performing the party’s obligations under this Design-Build Contract, to the extent that such act, event or condition is not the result of the willful or negligent act, error or omission, failure to exercise reasonable diligence, or breach of this Design-Build Contract on the part of the party claiming the occurrence of an Uncontrollable Circumstance.

(1)	Inclusions.  Subject to the foregoing, Uncontrollable Circumstances may include the following:

- A Change in Law;

- The existence of Differing Site Conditions, as and to the extent provided in Section 6.3;

- The existence of a Regulated Site Condition, as and to the extent provided in Section 6.4;

- Acts, events or circumstances associated with the Separate Contractors, as and to the extent provided in (C);

- Naturally occurring events, including unusually severe and abnormal climactic conditions (as determined in accordance with Section 14.5), landslides, underground movement, earthquakes, fires, tornadoes, hurricanes, floods, lightning, epidemics and other acts of God;

- Explosion, terrorism, sabotage or similar occurrence, acts of a declared public enemy, extortion, war, blockade or insurrection, riot or civil disturbance;

- Labor disputes or actions, except labor disputes or actions involving employees of the Design-Builder, its Affiliates, or Subcontractors, which affect the performance of the Design-Build Work (provided, however, that the Design-Builder shall be afforded schedule relief only for labor disputes affecting those Subcontractors which are equipment fabricators or transporters);

- The failure of any Subcontractor (other than the Design-Builder or any Affiliate of the Design-Builder) to furnish services, materials, chemicals or equipment on the dates agreed to, but only if such failure is the result of an event which would constitute an Uncontrollable Circumstance if it affected the Design-Builder directly, and the Design-Builder is not able after exercising all reasonable efforts to timely obtain replacements;

- The preemption, confiscation, diversion, destruction or other interference in possession or performance of materials or services by a Governmental Body in connection with a public emergency or any condemnation or other taking by eminent domain of any material portion of the Project;

- An act, event or circumstance occurring outside of the United States only to the extent that such act, event or circumstance (i) directly impacts the Design-Builder’s foreign suppliers or vendors with respect to the performance of the Design-Build Work, and (ii) would otherwise constitute an Uncontrollable Circumstance affecting the Design-Builder directly, as determined in accordance with Article 14;

- Failure of Utilities to perform any relocation work in a timely manner following reasonable notice provided that reasonable notice shall at a minimum be 90 days;

- With respect to the Design-Builder, any City Fault or a Change Order not made due to Design-Builder Fault;

- With respect to the City, any Design-Builder Fault; or

- Any other act, event or circumstance specifically identified herein as providing a basis for Uncontrollable Circumstance relief.

(2)	Exclusions.  It is specifically understood that, without limitation, none of the following acts, events or circumstances shall constitute Uncontrollable Circumstances:

- Any act, event or circumstance that would not have occurred but for the affected party’s failure to comply with its obligations hereunder;

- Changes in interest rates, inflation rates, wage rates, insurance premiums, commodity prices, labor availability, currency values, exchange rates or other economic conditions;

- Changes in the financial condition of the City, the Design-Builder or their Affiliates or Subcontractors affecting the ability to perform their respective obligations;

- The consequences of error, neglect or omissions by the Design-Builder, any Subcontractor, any of their Affiliates or any other person in the performance of the Design-Build Work;

- Union or labor work rules, requirements or demands which have the effect of increasing the number of employees employed at the Project or otherwise increasing the cost to the Design-Builder of performing the Design-Build Work;

- Except as specifically provided in the “Inclusions” section of this definition, strikes, labor disputes, work slowdowns, work stoppages, boycotts or other similar labor disruptions;

- Weather conditions that do not constitute unusually severe and abnormal climactic conditions (as determined in accordance with Section 14.5);

- Except as specifically provided in Section 6.3 and Section 6.4, any surface or subsurface conditions affecting the Project Sites during the Stage 2 Design-Build Work;

- Except as specifically provided in the “Inclusions” section of this definition, any act, event, circumstance or Change in Law occurring outside of the United States;

- Mechanical failure of equipment to the extent not resulting from a condition that is listed in the “Inclusions” section of this definition; or

- The failure of the Design-Builder to secure any patent or other Intellectual Property right which is or may be necessary for the performance of the Design-Build Work.

“Utilities” means any and all utility services and installations whatsoever (including gas, water, sewer, electricity, telephone, and telecommunications), and all piping, wiring, conduit, and other fixtures of every kind whatsoever related thereto or used in connection therewith.

“Warranty Period” has the meaning specified in (B).

“Warranty Work” means all work and services required to be performed or provided by the Design-Builder pursuant to the Project Warranties in accordance with Article 10.

“Washington State Department of Transportation Requirements” means the written and oral requirements of the Washington State Department of Transportation regarding construction of the Project below the elevated portion of I-705.

“Water Main” means [to be provided, if applicable.]

“Work Change Directive” has the meaning specified in Section 6.11.

## INTERPRETATION.

This Design-Build Contract shall be interpreted according to the following provisions, except to the extent the context or the express provisions of this Design-Build Contract otherwise require:

### Gender and Plurality.  Words of the masculine gender mean and include correlative words of the feminine and neuter genders and words importing the singular number mean and include the plural number and vice versa.

### Persons.  Words importing persons include firms, individuals, legal personal representatives, companies, associations, joint ventures, general partnerships, limited partnerships, limited liability corporations, trusts, business trusts, corporations, Governmental Bodies and other legal entities.

### Headings.  The table of contents and any headings preceding the text of the Articles, Sections and subsections of this Design-Build Contract shall be solely for convenience of reference and shall not affect its meaning, construction or effect.

### References Hereto.  The terms “hereto”, “hereby,” “hereof,” “herein,” “hereunder” and any similar terms refer to this Design-Build Contract.

### References to Days and Time of Day.  All references to days herein are references to calendar days, unless otherwise indicated, such as by reference to Business Days.  If the time for doing an act falls or expires on a day that is not a Business Day, the time for doing such act shall be extended to the next Business Day.  Each reference to time of day is a reference to Pacific Standard time or Pacific Daylight Saving time, as the case may be.

### References to Including.  The words “include,” “includes” and “including” are to be construed as meaning “include without limitation,” “includes without limitation” and “including without limitation,” respectively.

### References to Statutes.  Each reference to a statute or statutory provision includes any statute or statutory provision which amends, extends, consolidates or replaces the statute or statutory provision or which has been amended, extended, consolidated or replaced by the statute or statutory provision and includes any orders, regulations, by-laws, ordinances, codes of practice or instruments made under the relevant statute.

### References to the City, Governmental Bodies and Private Persons.  Each reference to the City or a Governmental Body is deemed to include a reference to any successor to the City or such Governmental Body or any organization or entity or organizations or entities which has or have taken over the functions or responsibilities of the City or such Governmental Body.  Each reference to a private person that is not an individual is deemed to include a reference to its successors and permitted assigns.

### References to Documents and Standards.  Each reference to an agreement, document, standard, principle or other instrument includes a reference to that agreement, document, standard, principle or instrument as amended, supplemented, substituted, innovated or assigned.

### References to All Reasonable Efforts.  The expression “all reasonable efforts” and expressions of like import, when used in connection with an obligation of either party, means taking in good faith and with due diligence all commercially reasonable steps to achieve the objective and to perform the obligation, including doing all that can reasonably be done in the circumstances taking into account each party’s obligations hereunder to mitigate delays and additional costs to the other party, and in any event taking no less steps and efforts than those that would be taken by a commercially reasonable and prudent person in comparable circumstances.

### Entire Agreement.  This Design-Build Contract contains the entire agreement between the parties hereto with respect to the transactions contemplated by this Design-Build Contract. Without limiting the generality of the foregoing, this Design-Build Contract shall completely and fully supersede all other understandings and agreements among the parties with respect to such transactions, including those contained in the RFQ, the submittal made by the Design-Builder in response thereto, the RFP, the Proposal, and any amendments or supplements to any such documents.

### Standards of Workmanship and Materials.  Any reference in the Contract Documents to materials, equipment, systems or supplies (whether such references are in lists, notes, specifications, schedules, or otherwise) shall be construed to require the Design-Builder to furnish the same in accordance with the grades and standards therefor indicated in the Contract Documents.  Where the Contract Documents do not specify any explicit quality or standard for construction materials or workmanship, the Design-Builder shall use only workmanship and new materials of a quality consistent with that of construction workmanship and materials that are specified elsewhere in the Contract Documents, and the Contract Documents are to be interpreted accordingly.

### Technical Standards and Codes.  References in the Contract Documents to all professional and technical standards, codes and specifications are to the most recently published professional and technical standards, codes and specifications of the institute, organization, association, authority or society specified, all as in effect as of the Baseline Date.  Unless otherwise specified to the contrary, (1) all such professional and technical standards, codes and specifications shall apply as if incorporated in the Baseline Design Documents, and (2) if any material revision occurs, to the Design-Builder’s actual knowledge, after the Baseline Date, and prior to completion of the applicable Design-Build Work, the Design-Builder shall notify the City.  If so directed by the City through a Work Change Directive or Change Order, the Design-Builder shall perform the applicable Design-Build Work in accordance with the revised professional and technical standard, code, or specification, subject to the Design-Builder’s rights under this Design-Build Contract with respect to Work Change Directives and Change Orders at the direction of the City.

### Causing Performance.  A party shall itself perform, or shall cause to be performed, subject to any limitations specifically imposed hereby with respect to Subcontractors or otherwise, the obligations affirmatively undertaken by such party under this Design-Build Contract.

### Party Bearing Cost of Performance.  All obligations undertaken by each party hereto shall be performed at the cost of the party undertaking the obligation or responsibility, unless the other party has explicitly agreed herein to bear all or a portion of the cost either directly, by reimbursement to the other party or through an adjustment to the Guaranteed Maximum Price.

### Good Engineering and Construction Practice.  Good Engineering and Construction Practice shall be utilized hereunder, among other things, to implement and in no event displace or lessen the stringency of, the Contract Standards.

### Interpretation of Contract Documents.  The Contract Documents are intended to be complementary, and what is set forth in any one document is as binding as if set forth in each document.  The parties recognize that Contract Amendments, Change Orders and Work Change Directives may provide for specific modification to the terms and conditions of other Contract Documents, in which case, the modified terms and conditions shall govern, as expressly set forth in the Contract Amendment, Change Order or Work Change Directive. However, all terms and conditions of such other Contract Documents that are not expressly modified or deleted by a Contract Amendment, Change Order or Work Change Directive shall remain in effect.  (R) shall govern matters of interpretation related to the applicability, stringency and consistency of the Contract Documents, the requirements of which are included among the Contract Standards.

### Applicability, Stringency and Consistency of Contract Standards.  The Design-Builder shall be obligated to comply only with those Contract Standards which are applicable in any particular case.  Where more than one Contract Standard applies to any particular performance obligation of the Design-Builder hereunder, each such applicable Contract Standard shall be complied with.  In the event there are different levels of stringency among such applicable Contract Standards, the most stringent of the applicable Contract Standards shall govern.  In the event of any inconsistency among the Contract Standards, the City’s determination, acting reasonably, as to the applicable standard shall be binding.

### Delivery of Documents in Digital Format.  In the Contract Documents, the Design-Builder is obligated to deliver reports, records, designs, plans, drawings, specifications, proposals and other documentary submittals in connection with the performance of its duties hereunder. The Design-Builder agrees that all such documents shall be submitted to the City both in printed form (in the number of copies indicated) and, at the City’s request, in digital form. Digital copies shall consist of computer readable data submitted in any standard interchange format which the City may reasonably request to facilitate the administration and enforcement of this Design-Build Contract.  In the event that a conflict exists between the signed or the signed and stamped hard copy of any document and the digital copy thereof, the signed or the signed and stamped hard copy shall govern.

### Severability.  Each provision of this Design-Build Contract shall be valid and enforceable to the fullest extent permitted by law. If any provision of this Design-Build Contract is held to be invalid, unenforceable or illegal to any extent, such provision shall be severed and such invalidity, unenforceability or illegality shall not prejudice or affect the validity, enforceability and legality of the remaining provisions of this Design-Build Contract, unless such continued effectiveness as modified would be contrary to the basic understandings and intentions of the parties as expressed herein. If any provision of this Design-Build Contract is held to be invalid, unenforceable or illegal, the parties will promptly endeavor in good faith to negotiate new provisions to eliminate such invalidity, unenforceability or illegality and to restore this Design-Build Contract as nearly as possible to its original intent and effect.

### Drafting Responsibility.  The parties waive the application of any rule of law which otherwise would be applicable in connection with the construction of this Design-Build Contract to the effect that ambiguous or conflicting terms or provisions should be construed against the party who (or whose counsel) prepared the executed agreement or any earlier draft of the same.

### No Third-Party Rights.  This Design-Build Contract is exclusively for the benefit of the City and the Design-Builder and, except with respect to the State of Washington and as specifically provided in Article 15 with respect to the City Indemnitees, shall not provide any third parties with any remedy, claim, liability, reimbursement, cause of action or other rights.

### Acting Reasonably and in Good Faith; Discretion.  Each party shall act reasonably and in good faith in the exercise of its rights hereunder, except where a party has the right to act in its “discretion” by the express terms hereof.  When a party has “discretion”, it means that party has the sole, absolute and unfettered discretion, with no requirement to act reasonably or provide reasons unless specifically required under the provisions of this Design-Build Contract.  When a party does not have “discretion” it means that the party shall act reasonably.

### Counterparts.  This Design-Build Contract may be executed in any number of original counterparts.  All such counterparts shall constitute but one and the same Design-Build Contract.

### Governing Law.  This Design-Build Contract shall be governed by and construed in accordance with the applicable laws of the State.

### Defined Terms.  The definitions set forth in Section 1.1 shall control in the event of any conflict with any definitions used in the recitals hereto.

### Interpolation.  If any calculation hereunder is to be made by reference to a chart or table of values, and the reference calculation falls between two stated values, the calculation shall be made on the basis of linear interpolation.

### Accounting and Financial Terms.  All accounting and financial terms used herein are, unless otherwise indicated, to be interpreted and applied in accordance with generally accepted accounting principles.

### References to Dollar Amounts.  All statements of, or references to, dollar amounts or money, including references to “$” and “dollars”, are to the lawful currency of the United States of America.  All payments required to be made by either party hereunder shall be made in dollars.

### Liquidated Damages.  This Design-Build Contract provides for the payment by the Design-Builder of liquidated damages in certain circumstances associated with unexcused delays in achieving Substantial Completion, as and to the extent provided in Section 8.3(C).  Each party agrees that the City’s actual damages in each such circumstance of replacement or unexcused delay would be difficult or impossible to ascertain, and that the liquidated damages provided for herein with respect to each such circumstance of unexcused delay are intended to place the City in the same economic position as it would have been in had the unexcused delay not occurred.  Such liquidated damages shall constitute the only damages payable by the Design-Builder to the City to compensate the City for such replacement or for unexcused delays in achieving Substantial Completion by the Scheduled Substantial Completion Date, as applicable, regardless of legal theory.  This limitation, however, is not intended to limit any of the other remedies for breach specifically provided for in this Design-Build Contract, including the City’s remedies associated with an Event of Default by the Design-Builder under Section 12.2.  The parties acknowledge and agree that the additional remedies specifically provided for in this Design-Build Contract are intended to address harms and damages which are separate and distinct from those which the liquidated damages are meant to remedy.  In addition, the parties agree as follows:

###### that the liquidated damages payable under this Design-Build Contract are not a penalty, and are fair and reasonable and such payment represents a reasonable estimate of fair compensation for the losses that may reasonably be anticipated from the circumstances of unexcused delay; and

###### that, in recognition of the acknowledgments above, the Design-Builder is expressly estopped from arguing, and waives any rights it may have to argue, that the liquidated damages provided for herein are a penalty and that they are not enforceable.

### Convenience Termination.  The City may exercise its right of convenience termination under this Design-Build Contract in its discretion.  The exercise by the City of its right of convenience termination under any provision of this Design-Build Contract shall not be deemed a breach of any implied duty of good faith dealing or a City Event of Default nor shall any damages be payable by the City on account thereof.  The only compensation payable by the City upon the exercise of its convenience termination option shall be any amounts specified in Section 12.6 in connection therewith.

# DESIGN-BUILDER REPRESENTATIONS AND WARRANTIES

## REPRESENTATIONS AND WARRANTIES OF THE DESIGN-BUILDER.

In addition to any other representations and warranties made by the Design-Builder in this Design-Build Contract, the Design-Builder represents and warrants that:

### Existence and Powers.  The Design-Builder is a [TYPE OF ENTITY], having its principal office at [ADDRESS].  Such [TYPE OF ENTITY] is duly organized, validly existing and in good standing under the laws of [JURISDICTION OF FORMATION] and has the authority to do business in the State and in any state in which it conducts its activities, with the full legal right, power and authority to enter into and perform its obligations under this Design-Build Contract.

### Due Authorization and Binding Obligation.  This Design-Build Contract has been duly authorized, executed and delivered by all necessary [corporate] action of the Design-Builder and constitutes a legal, valid and binding obligation of the Design-Builder, enforceable against the Design-Builder in accordance with its terms, except to the extent that its enforceability may be limited by the Bankruptcy Law or by equitable principles of general application.

### No Conflict.  Neither the execution nor delivery by the Design-Builder of this Design-Build Contract nor the performance by the Design-Builder of its obligations in connection with the transactions contemplated hereby nor the fulfillment by the Design-Builder of the terms or conditions hereof (1) conflicts with, violates or results in a breach of any constitution, law, governmental regulation, by-laws or certificates of incorporation applicable to the Design-Builder or (2) conflicts with, violates or results in a breach of any order, judgment or decree, or any contract, agreement or instrument to which the Design-Builder or any of its Affiliates is a party or by which the Design-Builder or any of its Affiliates or any of its properties or assets are bound, or constitutes a default under any of the foregoing.

### No Commitments Limiting Ability to Perform Contract Obligations.  The Design-Builder has no commitments, obligations, or impediments of any kind that would have a material and adverse impact on the ability of the Design-Builder to perform the Contract Obligations in accordance with the Contract Standards.  The Design-Builder covenants that it will not enter into any such commitment throughout the Term.

### No Approvals Required.  No approval, authorization, order or consent of, or declaration, registration or filing with, any Governmental Body is required for the valid execution and delivery of this Design-Build Contract by the Design-Builder except as such have been duly obtained or made.

### Licensing and Registration Requirements.  The Design-Builder possesses all licenses required under Applicable Law to perform all services required of the Design-Builder under this Design-Build Contract and is not in violation of any of the terms or conditions of such licenses.  The Design-Builder is registered with all appropriate Governmental Bodies to the extent necessary to perform all services required of the Design-Builder under this Design-Build Contract.

### No Litigation.  There is no legal proceeding, at law or in equity, before or by any court, arbitral tribunal or other Governmental Body pending or, to the best of the Design-Builder’s knowledge after due inquiry, overtly threatened or publicly announced against the Design-Builder, in which an unfavorable decision, ruling or finding could reasonably be expected to have a material and adverse effect on the execution and delivery of this Design-Build Contract by the Design-Builder or the validity, legality or enforceability of this Design-Build Contract against the Design-Builder, or any other agreement or instrument entered into by the Design-Builder in connection with the transactions contemplated hereby, or on the ability of the Design-Builder to perform its obligations hereunder or under any such other agreement or instrument.

### Claims and Demands.  There are no material and adverse claims or demands based in environmental, contract or tort law pending or threatened against the Design-Builder or any of its Affiliates with respect to any facilities designed or constructed by the Design-Builder or any of its Affiliates that would have a material and adverse effect upon the ability of the Design-Builder to perform the Contract Obligations.

### Applicable Law Compliance.  To the best of its knowledge after due inquiry, the Design-Builder and its Affiliates have no material violation of any law, order, rule or regulation with respect to any facilities designed or constructed by the Design-Builder or any of its Affiliates.

### Information Supplied by the Design-Builder.  The information supplied and representations and warranties made by the Design-Builder in all submittals made in response to the RFQ and RFP with respect to the Design-Builder (and to its knowledge after due inquiry, all information supplied in such submittals with respect to any Affiliate or Subcontractor) are true, correct and complete in all material respects.

### Intellectual Property.  The Design-Builder owns, or has sufficient rights to use, all Intellectual Property necessary for the Project without any material conflict with the rights of others.

### Practicability of Performance.  Subject to, and in accordance with, the terms of this Design-Build Contract, the Design-Builder assumes the risk of the practicability and possibility of performance of the Contract Obligations in compliance with the requirements of the Contract Standards on the scale, within the time for completion, and in the manner required hereunder, and agrees that sufficient consideration for the assumption of such risk is included in the Contract Compensation.

### Required Insurance.  Concurrently with the execution of this Design-Build Contract, the Design-Builder has provided the City with certificates of insurance for all Required Insurance specified in Appendix 10 to be in effect as of the Contract Date.  The Required Insurance is in compliance with the requirements of Section 13.1.

# TERM

## EFFECTIVE DATE AND TERM.

### Term.  This Design-Build Contract shall become effective, and the term hereof (the “Term”) shall commence, on the Contract Date.  The Term shall continue to the Expiration Date or, if this Design-Build Contract is earlier terminated by either party in accordance with their respective termination rights under Article 12, to the Termination Date.

### Accrued Rights.  No termination of this Design-Build Contract shall:

###### Limit or otherwise affect the respective rights and obligations of the parties hereto accrued prior to the date of such termination; or

###### Preclude either party from impleading the other party in any Legal Proceeding originated by a third-party as to any matter occurring during the Term.

## SURVIVAL.

Notwithstanding any other provision of this Design-Build Contract, this Section and the following provisions hereof shall survive the expiration or any earlier termination of this Design-Build Contract:

###### Article 2 (Design-Builder Representations and Warranties);

###### Section 4.8 (Ownership and Use of Documents and Information);

###### (F) (Elective Continuance of the Project by the Parties on Other Bases);

###### (G) (Elective Continuance of the Project by the City with Other Contractors; Project Documents);

###### (G); (Non-Discrimination)

###### Section 9.9 (Interest on Overdue Obligations);

###### Section 9.10 (Retention And Audit of Books and Records);

###### Section 10.3 (Project Warranties Not Exclusive);

###### Article 11 (Dispute Resolution);

###### Article 12, as applicable to the obligations of the parties following the Termination Date (Breach, Default, Remedies and Termination);

###### Article 15, including all of the indemnities, limitations and releases set forth therein (Indemnification);

###### Section 17.7 (Property Rights);

###### Section 17.14 (Confidentiality)

###### Attachment 8C of Appendix 8 regarding Subcontractor and surety recoveries (Anticipated Stage 2 Design-Build Cost Schedule and Design-Builder Contingency);

###### Appendix 10 (Insurance Requirements);

###### All provisions of this Design-Build Contract with respect to payment obligations of the Design-Builder or the City accrued prior to the Termination Date;

###### Any other provisions which either expressly or by their context or inherent character should survive expiration or earlier termination of this Design-Build Contract or the completion of the Contract Obligations; and

###### Any provisions necessary to give effect to the provisions referenced or described in this Section 3.2.

# GENERAL PERFORMANCE REQUIREMENTS

## PROJECT SCOPE AND PERSONNEL.

### Project Scope Generally.  The Project and the Project Sites are generally described in Appendix 1.  The Design-Builder recognizes that the Project will ultimately be defined by the Baseline Design Documents, which will be developed by the Design-Builder as part of the Stage 1 Preliminary Services.

### Pricing Established on the Contract Date.  The parties acknowledge and agree that the not-to-exceed limit for the Stage 1 Preliminary Services Fee, the Design-Builder Fee and the General Conditions Fee were proposed by the Design-Builder as part of the Proposal, negotiated by the parties prior to the Contract Date and included in this Design-Build Contract as executed on the Contract Date, and shall not be the subject of (1) any Early Work Package Submittal or any Early Work Package Amendment, and (2) the GMP Submittal or the GMP Amendment.  The parties acknowledge that the General Conditions Fee fully compensates the Design-Builder for General Conditions Costs as defined in Appendix 8.  The City reserves the right to transition the Preliminary Services Fee, Design-Builder Fee and/or General Conditions Fee to a lump sum basis.

### Pricing Established Subsequent to the Contract Date.  The parties further acknowledge and agree that all other elements of pricing provided for in this Design-Build Contract are to be negotiated by the parties subsequent to the Contract Date in connection with establishing any Early Work Package Amendment and the GMP Amendment in accordance with the terms and conditions of this Design-Build Contract.

### Estimated Substantial Completion Date.  As of the Contract Date, the estimated Scheduled Substantial Completion Date is ______________, 20__, based on an estimated Stage 1 Preliminary Services Period (including the negotiation of the GMP Amendment) of ___ days, and an estimated Stage 2 Period of __ days.  The Design-Builder shall be responsible for updating and refining the estimated Scheduled Substantial Completion Date as part of the Stage 1 Preliminary Services.  Ultimately, the parties intend to negotiate and agree on the definitive Scheduled Substantial Completion Date (expressed as a number of days following the GMP Amendment Date) in accordance with Section 5.8, and to incorporate the agreed upon Scheduled Substantial Completion Date in the GMP Amendment.

## DESIGN-BUILDER RESPONSIBILITIES GENERALLY.

### Reliance.  The Design-Builder acknowledges and agrees that the City is entering into this Design-Build Contract in reliance on the Design-Builder’s expertise with respect to the performance of the Contract Obligations.  The Design-Builder recognizes that the City’s sole purpose is to provide an essential public service and that the achievement of Substantial Completion by the Scheduled Substantial Completion Date and Final Completion by the date specified in Section 8.4 is critically important to the City.  The Design-Builder agrees that it will be relieved of its performance obligations under this Design-Build Contract solely to the extent provided in Article 14 with respect to the occurrence of Uncontrollable Circumstances.

### Scope of the Contract Obligations.  The Contract Obligations are divided into the Stage 1 Preliminary Services, the Stage 2 Design-Build Work and the Warranty Work, each as more particularly described in Article 5, Article 6, Article 8 and Article 10.  The Design-Builder recognizes that, notwithstanding this division, the Contract Obligations may overlap and agrees to perform all Contract Obligations in accordance with the Contract Standards.  In no event shall the Design-Builder commence with the Stage 2 Design-Build Work prior to the GMP Amendment Date and the issuance of a Notice to Proceed with Stage 2 Design-Build Work in accordance with (A) or, in respect of any Early Work Package, the execution of an Early Work Package Amendment and the issuance by the City of the associated Notice to Proceed in accordance with (H).  Following the issuance of a Notice to Proceed with Stage 2 Design-Build Work, the Design-Builder shall be solely responsible for undertaking and completing the design and for the construction of the Project in accordance with the Contract Documents, including supervision, coordination and administration of all design work and of all Construction, and all other work reasonably inferable from the Contract Documents.

### Cooperation.  The Design-Builder agrees to cooperate with the City and any entity engaged by the City in connection with the work to be performed toward completion of the Project and any Related Project, including the Owner Representative and any Separate Contractor, as well as with any contractor performing work for a non-City owner that could affect the Stage 1 Preliminary Services or the Stage 2 Design-Build Work.  The Design-Builder recognizes that a cooperative and collaborative environment among all persons engaged in performing such work is essential to the successful implementation of the Project and agrees to use all reasonable efforts to work with all such other persons toward fostering such an environment.

### Responsibility for Personnel and Subcontractors.  All obligations of the Design-Builder under this Design-Build Contract shall be performed by Design-Builder employees, agents or Subcontractors (subject to the limitations set forth in Article 7) who are qualified to perform the specific services and meet all licensing and certification requirements of Applicable Law.  The Design-Builder shall be fully responsible, in accordance with the terms and conditions of this Design-Build Contract, for all Contract Obligations performed by its employees, agents or Subcontractors.

### Stationing of Key Personnel.  From and after the Construction Commencement Date, the Design-Builder’s construction superintendent shall on a full-time basis be stationed at the Project Site, and the Project Manager and other appropriate Key Personnel shall also be stationed at the Project Site or be available as required for communications with the City.

## ENVIRONMENTAL REVIEW.

### SEPA.  The City is complying with the State Environmental Policy Act (SEPA) for the Project as described herein.  For purposes of SEPA compliance, the Project is divided into the upland portion and the shoreline portion.  The City has determined that the upland portion of the Project, qualifies as a planned action under the South Downtown and North Downtown Subarea Plans Final Environmental Impact Statements (FEISs).  The City will adopt the South Downtown Subarea Plan FEIS for the shoreline portion of the Project, and no further action is necessary for the SEPA compliance except that the Design-Builder must comply with the Environmental Mitigation Measures set forth in Reference Documents to this Design-Build Contract.  The Environmental Mitigation Measures constitute part of the Baseline Design Documents, which the Design-Builder is obligated to perform hereunder.

### NEPA.  The parties acknowledge that NEPA compliance may be required depending on the ultimate alignment selected. In the event the selected alignment requires NEPA compliance, the City will serve as the lead agency with respect to any such necessary compliance. The Design-Builder shall provide the City with any reasonably requested assistance associated with NEPA compliance and any environmental mitigation measures required as a result of the NEPA process shall constitute Baseline Design Documents, which the Design-Builder is required to comply with hereunder.

## ACCESS TO AND SUITABILITY OF THE PROJECT SITES.

### Familiarity with the Project Sites.  Prior to the issuance of a Notice to Proceed with Stage 2 Design-Build Work, the Design-Builder’s agents and representatives shall have inspected and become familiar with the Project Sites, their physical condition relevant to the obligations of the Design-Builder pursuant to this Design-Build Contract, including surface conditions, normal and usual soil conditions, roads, Utilities, topographical conditions and air and water quality conditions and, as part of the Stage 1 Preliminary Services, shall have developed the Geotechnical Baseline Report, the Geotechnical Evaluation Report, the Contaminated Materials Management Plan, and the Contamination Assessment Report and other Stage 1 Preliminary Services Deliverable Materials.   As of the issuance of a Notice to Proceed with Stage 2 Design-Build Work, the Design-Builder shall be familiar with all local and other conditions which may be material to the Design-Builder’s performance of the Design-Build Work (including transportation; seasons and climate; access, availability, disposal, handling and storage of materials and equipment; and availability and quality of labor and Utilities); the Design-Builder shall have received and reviewed all information regarding the Project Sites provided to or developed by it in connection with the Stage 1 Preliminary Services pursuant to this Design-Build Contract; and the Design-Builder shall have made all other site investigations that it deems necessary to make a determination as to the suitability of the Project Sites and to submit its GMP Submittal to the City in accordance with Section 5.7.

### Independent Verification of the City-Provided Project Sites Information.  The Design-Builder acknowledges that, except as otherwise provided under Section 4.5(B), it is responsible for the independent verification and confirmation of any Project Sites information, including geotechnical, soils, utility locations, groundwater levels and other reports, surveys and analyses regarding the Project Sites, supplied to it by or on behalf of the City and upon which it elects to rely in connection herewith.  Except as otherwise provided in Section 4.5(B) and except, with respect to Differing Site Conditions and Regulated Site Conditions, as and to the extent provided in Section 6.3(D) and 6.4(E) respectively, no error or omission in any such information shall constitute an Uncontrollable Circumstance, or relieve the Design-Builder from the Contract Obligations or entitle the Design-Builder to any increase in compensation hereunder.  Notwithstanding any factual statement, conclusion, or any language or recommendation contained in any information supplied to the Design-Builder by or on behalf of the City, the Design-Builder assumes full responsibility for inspecting the Project Sites and for the means and methods of construction that it employs when performing the Design-Build Work.

### Access to the Project Sites.  Except as provided in Section 4.4(D), the execution of this Design-Build Contract shall be deemed to constitute the granting of a license to the Design-Builder to access the Project Sites located on and under City streets and at the Existing Outfall for the purposes of performing the Contract Obligations, including such additional surface, subsurface and geotechnical studies or tests required to be performed as part of the Stage 1 Preliminary Services and as deemed necessary by the Design-Builder prior to the commencement of Construction in accordance with Good Engineering and Construction Practice.  Such access shall be subject to the City’s prior approval, which shall not be unreasonably withheld, as to time and scope, and shall be subject to all City procedures and requirements regarding Project Sites security and any applicable easement or right of way restrictions.  The Design-Builder shall perform all such activities in accordance with the Contract Standards, including the specific requirements set forth in Appendix 2 and Appendix 5, and shall provide the City with all reports or analyses generated by such activities promptly after such reports or analyses are generated.  Except to the extent provided in Section 6.4 with respect to Regulated Site Conditions, the Design-Builder shall assume all risks associated with such activities and shall indemnify, defend and hold harmless the City Indemnitees in accordance with and to the extent provided in Article 15 from and against all Loss-and-Expense resulting therefrom.  Following the issuance of the Notice to Proceed with Stage 2 Design-Build Work and for the duration of the Stage 2 Design-Build Period, the Design-Builder shall have all Project Sites access rights as are necessary for the performance of the Design-Build Work in accordance with the Contract Documents.  Notwithstanding any of the foregoing, the Design-Builder shall not access portions of the alignment that are not under City streets or the Existing Outfall until either the Design-Builder or the City has obtained legal access rights, and the Design-Builder shall at all times comply with the Project Sites access requirements and restrictions set forth in the Contract Documents, including Appendix 5, and shall coordinate the Design-Build Work and interface with all Separate Contractors in accordance with Section 6.13.

### Surface Water Conveyance Pipeline Rights of Way.  The City shall acquire all easements or rights of way necessary for the Surface Water Conveyance Pipeline Rights of Way assuming the Design-Builder elects to follow the alignments for Outfall Alternative 1 or 2 as shown on the aerial map included in Appendix 1 hereto, except for the BNSF and Washington State Department of Transportation crossings.  The Design-Builder shall be responsible for obtaining any rights of way or easements which the City does not already have associated with portions of the alignment necessary for an outfall location other than Outfall Alternative 1 or 2 as shown on the Preliminary Project Map set forth in Appendix 1, and shall be responsible for obtaining necessary rights of way or easements associated with the BNSF and Washington State Department of Transportation crossings.  Upon such acquisition, the acquiring party shall notify the other party, and the Design-Builder shall thereafter have access rights in respect thereof in accordance with (C).  Each party shall use all reasonable efforts to inform the other party of its progress toward acquiring such.

### Project Sites Signage.  The Design-Builder shall provide all Project Sites signage, including directional, safety, information, and warning signs in accordance with the Contract Standards.

## INFORMATION PROVIDED BY OR ON BEHALF OF THE City.

### Generally.  The City makes no representation or warranty with respect to any information provided to the Design-Builder by or on behalf of the City in connection with this Design-Build Contract except as specifically provided in subsection (B) of this Section.  The Design-Builder shall assess all risks related to the Project and independently verify and confirm all information supplied to it by or on behalf of the City and upon which the Design-Builder elects to rely in connection herewith.  Except as otherwise provided in subsection (B) of this Section and as may reasonably be requested by the Design-Builder, agreed upon by the City in its discretion, and expressly established in the GMP Amendment or any Early Work Package Amendment, the Design-Builder shall have no right to relief hereunder or to make any claim against the City, or to seek any adjustment to the Contract Compensation or the Scheduled Substantial Completion Date as the result of any error, omission or insufficiency relating to any information provided to the Design-Builder by or on behalf of the City in connection with this Design-Build Contract.

### Limited Reliance by Design-Builder.  Notwithstanding anything to the contrary provided in subsection (A) of this Section, the Design-Builder shall have the right to rely on the following information supplied to it by or on behalf of the City:

###### Data and information in Geo Engineers Geotechical Report [Note: Report is under preparation and will be provided to Design-Builder];

###### The fact that there are no additional City stormwater, wastewater, streets, public works, Tacoma Water or Tacoma Power plans or drawings available beyond those identified in Appendix 1 (provided that drawings discovered by the Design-Builder or the City during performance of the Preliminary Services shall be incorporated into such list);

###### Accuracy of the information included in the drawings identified in Appendix 1 to the extent that the Design-Builder has undertaken the drawings review and potholing obligations set forth in the Preliminary Services and has not identified any discrepancy with such drawings.

If the Design-Builder establishes that any error, omission or insufficiency relating to the information provided to the Design-Builder specified in this subsection directly and materially impacts the Design-Builder’s cost or time of performance, then the Design-Builder shall be entitled to Uncontrollable Circumstance relief as and to the extent provided in Article 14.  The Design-Builder acknowledges that, as stated above, the reliance permitted by this subsection is for the purpose of determining whether the Design-Builder is entitled to Uncontrollable Circumstances relief, and such reliance right does not entitle the Design-Builder to any rights or causes of action against the authors or generators of such reports and information on which this subsection allows the Design-Builder to rely.

## COMPLIANCE WITH APPLICABLE LAW.

### Compliance with Applicable Law Generally.  The Design-Builder shall, and shall cause all Subcontractors to, perform the Contract Obligations in accordance with Applicable Law and all other applicable Contract Standards.  The Design-Builder shall provide all notices required by Applicable Law and the Contract Standards.  The incorporation, reference or citation of specific statutes or other parts of Applicable Law in the Contract Documents is not intended, nor shall it be construed, to limit the generality of the Design-Builder’s and all Subcontractors’ obligations to comply with Applicable Law (whether or not specifically incorporated or referenced in the Contract Documents).

### Compliance with Conditions in Governmental Approvals.  The Design-Builder shall comply with all conditions and requirements of all Governmental Approvals required to be made, obtained or maintained under Applicable Law in connection with the performance of the Contract Obligations, including the City Managed Governmental Approvals.  The Design-Builder shall report to the City, immediately upon obtaining knowledge thereof, all violations of the terms and conditions of any Governmental Approval or Applicable Law pertaining to the Project.  The City, in its capacity as the counterparty to the Design-Builder under this Design-Build Contract, shall have the right independently to enforce compliance with this Design-Build Contract regarding the requirements of any Governmental Approval regardless of whether a concurrent or different regulatory enforcement action has been undertaken by any other Governmental Body. The Design-Builder shall comply with and perform all Environmental Mitigation Measures in a timely manner to the extent required under applicable Governmental Approvals. Any violations of or noncompliance with any Governmental Approval caused by the Design-Builder violating or not being in compliance with a Governmental Approval shall be at the sole risk of the Design-Builder and shall not be a basis for Uncontrollable Circumstance relief under this Design-Build Contract.

### Fines, Penalties and Remediation.  In the event that the Design-Builder or any Subcontractor fails at any time to comply with Applicable Law with respect to the Design-Build Work, the Design-Builder shall:

###### Promptly respond to any notice of non-compliance, warning letter, notice of violation or other enforcement action and seek amicable resolution of the issues;

###### Immediately correct such failure and resume compliance with Applicable Law;

###### Pay any resulting fines, assessments, levies, impositions, penalties or other charges;

###### Indemnify, defend and hold harmless the City Indemnitees in accordance with and to the extent provided in Article 15 from and against all Loss-and-Expense resulting therefrom;

###### Make all changes in performing the Contract Obligations which are necessary to assure that the failure of compliance with Applicable Law will not recur; and

###### Comply with any corrective action plan filed with or mandated by any Governmental Body in order to remedy a failure of the Design-Builder to comply with Applicable Law.

## ENGAGEMENT OF City REPRESENTATIVES.

The Design-Builder shall fully cooperate with the Owner Representative and any other representative designated by the City from time to time.  The services of the Owner Representative and other City-designated representatives may include the following:

###### Reviewing drawings, plans and specifications for compliance with the Contract Documents;

###### Reviewing proposed changes to the Baseline Design Documents;

###### Determining the completion of specified portions of the Design-Build Work and reviewing the release of funds to the Design-Builder pursuant hereto;

###### Reviewing and monitoring Construction progress, scheduling, payments and procedures;

###### Monitoring testing undertaken by the Design-Builder;

###### Assisting the City in reviewing the validity of the Design-Builder’s written notice that an Uncontrollable Circumstance has occurred; and

###### Reviewing and advising the City with respect to material changes to the Project during the Term.

It is understood that the services intended to be provided by the Owner Representative shall be of an observational and review nature only, and that the Owner Representative shall not have authority to interfere with, halt or delay in any way the construction of the Project or to require or approve changes to the Design-Builder’s Baseline Design Documents or plans and specifications made in accordance therewith.  Any fees of the Owner Representative shall be paid by the City.  Nothing in this Section 4.7 shall be construed to limit the right of any the City personnel or representative having the authority to protect the health and safety from inspecting the Project or otherwise exercising any power permitted under Applicable Law.

## OWNERSHIP AND USE OF DOCUMENTS AND INFORMATION.

The Design-Builder acknowledges and agrees that the City shall own exclusively the Deliverable Material and any and all other documents and information in whatsoever form and character produced or maintained in accordance with, pursuant to, or as a result of this Design-Build Contract.  All such documents and information may be used as the City determines and shall be delivered to the City at no additional cost to the City as required hereunder, upon request, upon Project completion or upon termination of this Design-Build Contract.  If the City uses any such documents and material for a purpose other than the Project, such use shall be at the City’s sole risk and liability.

## MONTHLY PROGRESS REPORTS.

The Design-Builder shall provide the City and the Owner Representative with monthly written reports (“Monthly Progress Report”) prepared in accordance with the Contract Standards, covering the Project and addressing work performed during the past month, percentage of work completion and compliance with the Project Schedule.  The Design-Builder shall describe Project issues, problems or concerns that the City should be made aware of and how the Design-Builder proposes to address them in each Monthly Progress Report.  The Monthly Progress Report shall include a description of the work planned for the next three months. The City’s and the Owner Representative’s receipt or acceptance of the Monthly Progress Report (or any revised Monthly Progress Report) shall not bind the City in any manner.  Thus, the City’s and the Owner Representative’s receipt or acceptance of the Monthly Progress Report (or any revised Monthly Progress Report) shall not imply the City approval or consent to any of the matters set forth therein and shall not limit or otherwise affect the Design-Builder’s obligations to achieve Substantial Completion by the Scheduled Substantial Completion Date and Final Completion by the date specified in Section 8.4.

# STAGE 1 PRELIMINARY SERVICES

## SCOPE OF THE STAGE 1 PRELIMINARY SERVICES.

### Generally.  The Design-Builder shall render and perform the Stage 1 Preliminary Services to and for the City in accordance with Appendix 2, the Stage 1 Preliminary Services Health and Safety Plan, the Stage 1 Preliminary Services Quality Management Plan, and the terms and conditions of this Design-Build Contract.  The Design-Builder’s responsibility to perform the Stage 1 Preliminary Services shall include the employment of or the subcontracting for all necessary professionals, technicians and engineers, properly qualified, licensed and skilled in the various aspects of the Stage 1 Preliminary Services, and the performance of all services reasonably inferable from the Contract Documents.

### Stage 1 Preliminary Services Tasks; Notice to Proceed.  The Design-Builder acknowledges that the Stage 1 Preliminary Services are divided into discrete Stage 1 Preliminary Services Tasks identified in Appendix 2 and associated with the advancement of the Stage 1 Preliminary Services.  The Design-Builder shall commence performing the Stage 1 Preliminary Services only upon the issuance by the City Contract Representative of a Notice to Proceed with the Stage 1 Preliminary Services.  In no event shall the Design-Builder be entitled to compensation for the performance of a Stage 1 Preliminary Services prior to the issuance by the City of a Notice to Proceed with the Stage 1 Preliminary Services.

## CHANGES TO THE SCOPE OF THE PRELIMINARY SERVICES.

### Generally.  The City shall have the right to make changes to the scope of the Stage 1 Preliminary Services set forth in Appendix 2 at any time, in its discretion, by written notice to the Design-Builder, subject to the terms and conditions of this Section.  Changes to the scope of the Stage 1 Preliminary Services may be made by the City to account for an Uncontrollable Circumstance or any other reason determined by the City.

### Additional Stage 1 Preliminary Services.  Except as otherwise specifically provided in this Section, the Design-Builder shall be entitled to an equitable adjustment to the maximum amount of the Stage 1 Preliminary Services Fee (as stated in Appendix 2) and the Stage 1 Preliminary Services Schedule (non-guaranteed) in the event of any expansion of the scope of the Base Stage 1 Preliminary Services pursuant to this Section (the “Additional Stage 1 Preliminary Services”).  Any expansion of the scope of the Base Stage 1 Preliminary Services under this subsection (B) and the corresponding equitable adjustment to the maximum amount of the Stage 1 Preliminary Services Fee and the Stage 1 Preliminary Services Schedule (non-guaranteed) shall be reflected in a Change Order or a Contract Amendment.  The Design-Builder shall not be entitled to compensation for any Additional Stage 1 Preliminary Services beyond the scope of the Base Stage 1 Preliminary Services unless, prior to the performance of any such Additional Stage 1 Preliminary Services, the Design-Builder shall have received express written authorization from the City to perform the Additional Stage 1 Preliminary Services.  In the absence of any the City-directed change to the scope of the Base Stage 1 Preliminary Services reflected in a Change Order or a Contract Amendment, the Design-Builder shall have no obligation to perform work outside the scope of the Base Stage 1 Preliminary Services.

### Additional Stage 1 Preliminary Services Resulting From Delay.  Except as otherwise set forth in Section 6.5, extra costs resulting from delays caused by Uncontrollable Circumstances, shall be deemed to be costs resulting from Additional Stage 1 Preliminary Services, provided the Design-Builder demonstrates that the costs claimed (1) resulted from time or expenses actually incurred in performing the Stage 1 Preliminary Services, (2) were incurred by Design-Builder as a direct result of the delay and not otherwise within the scope of the Stage 1 Preliminary Services, and (3) are documented to the City’s reasonable satisfaction.

### Exclusions from Additional Stage 1 Preliminary Services.  Additional Stage 1 Preliminary Services shall not include work or services necessary because of errors, omissions or conflicts of any type in the Design-Builder’s plans and specifications or other Stage 1 Preliminary Services Deliverable Material.  All such work or services shall constitute Base Stage 1 Preliminary Services and shall be performed at no cost to the City, and shall include any required corrections or revisions to reports, plans or specifications.

### Changes that Reduce the Scope of the Stage 1 Preliminary Services.  The City shall have the right to reduce the scope of the Stage 1 Preliminary Services at any time by written notice to the Design-Builder.  Changes to the Stage 1 Preliminary Services that reduce the scope of the Stage 1 Preliminary Services shall be effective upon the delivery of the written notice by the City pursuant to this subsection (E).  Any reduction in the scope of the Stage 1 Preliminary Services shall result in an appropriate reduction in the Stage 1 Preliminary Services Fee and an adjustment to the Stage 1 Preliminary Services Schedule (non-guaranteed), as appropriate, which shall be reflected in a Change Order or a Contract Amendment.

## PRELIMINARY SERVICES SCHEDULE.

The Stage 1 Preliminary Services Schedule is set forth in Attachment 2A and shall be updated as provided in Appendix 2.  The Design-Builder acknowledges that time is of the essence in the performance of the Stage 1 Preliminary Services and agrees to complete the Stage 1 Preliminary Services in a diligent, efficient and timely manner.  While the parties acknowledge that the Stage 1 Preliminary Services Schedule is not a guaranteed schedule, the Design-Builder shall use its best efforts to complete the various Stage 1 Preliminary Services under this Design-Build Contract as expeditiously as practicable and in any event in accordance with the Stage 1 Preliminary Services Schedule.

## COORDINATION WITH CITY.

### Meetings and Reports Generally.  The Design-Builder shall hold periodic meetings and conferences with the City during the Stage 1 Preliminary Services Period, in accordance with Appendix 2, to verify and confirm that the development of the Project (1) has the full benefit of the City’s experience and knowledge of existing needs and facilities, (2) is consistent with the City’s current policies and standards, and (3) is proceeding in accordance with the Stage 1 Preliminary Services Schedule.  The Design-Builder shall also keep the City regularly informed as to the progress of the Stage 1 Preliminary Services through the submittal of Monthly Progress Reports in accordance with the requirements set forth in Section 4.9 and Appendix 2.  The Monthly Progress Report shall present Project budget information and indicate amounts billed by Stage 1 Preliminary Services Task by the Design-Builder for the past month, cumulatively to date and the amount of funds remaining.  The Monthly Progress Report shall include a section on the progress of the design and list any concerns, actions, changes, and reviews and approvals from the City that the Design-Builder requires.  The Design-Builder shall indicate any Governmental Body, BNSF or Utility requirements and issues that the City should be aware of.

### Information Provided by the City.  The City shall make available for the Design-Builder’s use in the performance of the Stage 1 Preliminary Services all existing plans, maps, field notes, statistics, computations, and other data in the City’s possession relating to the Project, as reasonably requested in writing by the Design-Builder, at no cost to the Design-Builder.  All such information is provided to the Design-Builder for the sole purpose of the Design-Builder’s convenience and for use in relation to the performance of the Stage 1 Preliminary Services, may not be relied upon by the Design-Builder, except as otherwise provided under Section 4.5(B), and must be verified by the Design-Builder as provided in subsection (C) of this Section.  The Design-Builder shall promptly notify the City in writing when it reasonably believes or suspects that information provided by the City is not accurate or cannot be checked.  Any and all information provided by the City shall remain the property of the City and shall be returned promptly to the City upon written request.

### Required Design Information.  Notwithstanding the provisions of subsection (B) of this Section, the Design-Builder shall be responsible for obtaining and verifying all information required as further described in Appendix 2 in order to properly design the Project so that it is designed, constructed and performs in accordance with Applicable Law and the Contract Standards.

### Revisions to Drawings and Specifications.  Notwithstanding anything in this Design-Build Contract to the contrary, the Design-Builder shall, at no additional expense to the City, provide reasonable minor revisions to any and all drawings and specifications provided to the City, whether or not previously reviewed and accepted by the City, as may be required to satisfy the Stage 1 Preliminary Services established by this Design-Build Contract.  It is agreed and understood that the scope of each of the Stage 1 Preliminary Services Tasks in Appendix 2 (Stage 1 Preliminary Services) may require some reasonable minor revisions to drawings and specifications provided to the City, as the scope of the Project is refined, and that such reasonable minor revisions are included within the existing Stage 1 Preliminary Services under this Design-Build Contract.  The Design-Builder shall make, without additional expense to the City, such reasonable minor revisions or corrections to the Stage 1 Preliminary Services Deliverable Material as may be required.

## PROJECT DESIGN.

### Design Considerations.  The design for the Project undertaken and performed by the Design-Builder shall:

###### Be undertaken by a design team exercising such degree of care, skill and diligence as would reasonably be expected from consultants qualified to perform services similar in scope, nature and complexity to the design, as of the date of this Design-Build Contract, and the Design-Builder shall appoint a design team that:

- (a)	Is so qualified;

- (b)	Includes [(as required by Applicable Law)] licensed or registered professional engineers and architects; and

- (c)	Has sufficient expertise and experience to expeditiously and efficiently perform all of the design in a proper and professional manner to the standard set out in this Design-Build Contract;

###### Include specific consideration of “constructability” and “life cycle” cost issues at all stages of design, as appropriate; and

###### Include consideration of efficient and cost-effective operation and maintenance.

### Design-Builder Assumption of Full Design Liability.  The Design-Builder acknowledges and agrees that, as provided in Section 6.7, if and when a GMP Amendment is executed by the parties (and with respect to any Early Work Package work, when an Early Work Package Amendment is executed by the parties), the Design-Builder will have the sole and exclusive responsibility and liability for the design (except with respect to the Tacoma Water water main), construction and performance of the Project in accordance with and subject to the terms and conditions of the Contract Documents.  Accordingly, the Design-Builder shall have the right and the responsibility to develop and provide the Preliminary Design Documents and to perform the Stage 1 Preliminary Services under this Design-Build Contract in a manner that would permit a design-build contractor, acting reasonably and having the experience and qualifications required to successfully undertake and complete the design and construction of a project similar in scale and complexity to the Project, to assume such responsibility and liability.  In particular, the Design-Builder shall not propose or agree to any element of the Baseline Design Documents or other work product to be incorporated in any GMP Amendment or Early Work Package Amendment that would, in its reasonable judgment, be inconsistent with the assumption of such responsibility and liability.

## EARLY WORK PACKAGES.

### Early Work Packages.  The parties anticipate that there may be some phases of the Design-Build Work that are ready for commencement before it is appropriate to arrive at an overall agreed-upon Base Guaranteed Maximum Price in accordance with Section 5.7.  The Design-Builder shall recommend such phases or elements of the Design-Build Work (“Early Work Packages”) to the City Contract Representative, as appropriate, through the performance of the Stage 1 Preliminary Services, based on Early Work Package submittals (“Early Work Package Submittals”).  The City shall have the discretion to authorize the commencement of Design-Build Work associated with an Early Work Package pursuant to this Section.  The agreement of the parties as to an Early Work Package shall be effectuated through a Contract Amendment authorizing the Design-Build Work associated with the Early Work Package and specifying the terms and conditions of compensation payable to the Design-Builder and the completion dates associated with such Design-Build Work (an “Early Work Package Amendment”).  All work performed pursuant to an Early Work Package Amendment shall constitute Design-Build Work hereunder and shall be performed in accordance with the Contract Standards.  The City shall have no obligation to enter into an Early Work Package Amendment.  All Early Work Package Amendments agreed upon in accordance with this subsection (A) shall be taken into consideration in the preparation of the GMP Submittal submitted in accordance with Section 5.7.  The Design-Builder shall furnish a Performance Bond and a Payment Bond with a penal sum equal to the guaranteed maximum price or lump sum amount applicable to the Early Work Package, in compliance with the requirements set forth in Section 16.1 prior to the City’s issuance of a construction NTP for the Early Work Package.

### Early Work Package Submittals.  An Early Work Package Submittal shall include and be based upon the applicable Baseline Design Documents and all other specifications, information, analysis, findings and reports developed by the Design-Builder during the performance of the Stage 1 Preliminary Services as developed to the date of submittal, and shall be prepared in accordance with the Contract Standards.  An Early Work Package Submittal shall include the following:

Price Submittal:

###### a proposed lump sum or guaranteed maximum price, as authorized by the City, including the terms and conditions of payment, focused solely on the Design-Build Work associated with the Early Work Package and prepared in accordance with subsection (E) of this Section, together with a description of how such price will impact overall Project costs;

Technical Submittal:

###### A detailed description of the Design-Build Work associated with the Early Work Package Submittal and the associated Baseline Design Documents;

###### A proposed schedule for completion of the Design-Build Work associated with the Early Work Package, together with a description of how such work will impact the Project Schedule;

###### A listing of any assumptions, clarifications or qualifications made by the Design-Builder in providing the Early Work Package Submittal that are material to any part thereof, including a statement as to what information supplied by the City (if any) the Design-Builder proposes to use as the basis of any portion of its Early Work Package Submittal; and

###### Any other information reasonably requested by the City prior to the due date for the Early Work Package Submittal as necessary or appropriate to negotiate and complete the Early Work Package Amendment.

### Early Work Package Submittal Revisions.  The Design-Builder shall provide the City with at least seven days’ notice prior to submitting an Early Work Package Submittal for review.  The City will act reasonably in considering any proposed Early Work Package in light of the schedule requirements under this Design-Build Contract.  In the event the Early Work Package Submittal does not comply with the Contract Standards, the City may provide written notice to the Design-Builder of any additions, corrections or revisions required to achieve such compliance.  In such event, the Design-Builder, without any increase in the Stage 1 Preliminary Services Fee, shall promptly take all necessary rectification action, making multiple re-submittals if required.

### Negotiation and Execution.  If the City agrees to authorize the commencement of a portion of the Design-Build Work under an Early Work Package Submittal, the Design-Builder and the City shall negotiate and enter into an Early Work Package Amendment.  An Early Work Package Amendment at a minimum shall incorporate and definitively address all of the items identified in subsection (B) of this Section, and shall contain any other commercial terms and conditions specific to the Early Work Package, including the rights of the City to terminate the work being performed pursuant to the Early Work Package Amendment and the right of the City to direct the Design-Builder to continue performance of the Early Work Package in the event the parties do not enter into a GMP Amendment.  Early Work Packages may be structured in a manner that provides for the commencement of the related Design-Build Work at any time determined by the parties.

### Complete Early Design-Build Work Package Pricing.  It is the intention of the parties that each Early Work Package Submittal, and any associated Early Work Package Amendment, include complete pricing for the Design-Build Work to be performed thereunder, including: (1) the maximum cost of the Design-Build Work described in the Early Work Package Submittal excluding the Design-Builder Fee, the General Conditions Fee and contingency; (2) the Design-Builder Fee, attributable to the Design-Build Work described in the Early Work Package Submittal; (3) the General Conditions Fee attributed to the Design-Build Work described in the Early Work Package Submittal; and a contingency amount for such Design-Build Work to be administered in the same manner as the Design-Builder Contingency.  Alternatively, an Early Work Package Submittal may include pricing for all or part of the Design-Build Work on a firm, fixed price basis.

### Compensation Payable in Connection With Early Work Packages.  The City shall pay the Early Work Package Price to the Design-Builder for Design-Build Work properly performed and completed pursuant to the terms of the Early Work Package Amendment in accordance with, and subject to the limitations contained in, Appendix 8, notwithstanding the fact that no GMP Amendment will be in effect at the time the parties execute an Early Work Package Amendment.

### Design-Builder Representations in an Early Work Package Amendment.  The execution of any Early Work Package Amendment will be deemed to constitute representations by the Design-Builder with respect to the Early Work Package to the same effect as the representations made in (H) with respect to the GMP Amendment, with references to Design-Build Work referring to the Early Work Package and references to the Base Guaranteed Maximum Price referring to the Early Work Package Price.

### Limited Authorization to Proceed; Commencement of Early Work Package.  If the parties agree to an Early Work Package Amendment, the City shall issue a limited Notice to Proceed with the Design-Build Work associated with the Early Work Package, subject to this Section.  Notwithstanding the issuance of a limited Notice to Proceed with an Early Work Package, the Design-Builder shall not commence any Construction at the Project Sites in connection with such Early Work Package until the Design-Builder has satisfied the following requirements:

###### The Design-Builder shall have provided a Performance Bond and a Payment Bond for the Early Work Package, and certified that such Performance Bond and Payment Bond are in full force and effect and in compliance with the requirements set forth in Section 16.1;

###### The Design-Builder shall have provided the City with certificates for all Required Insurance in accordance with Section 13.1 and certified that all such policies are in full force and effect and in compliance with the requirements of Section 13.1 and Appendix 10;

###### The Design-Builder shall have satisfied all requirements of Applicable Law with respect to the commencement of construction and shall have obtained all Governmental Approvals required for the commencement of the Construction of the Early Work Package Design-Build Work as well as Governmental Approvals that the City has determined in its discretion must be obtained prior to the commencement of Construction and provided copies of such Governmental Approvals to the City.  All such Governmental Approvals shall be in full force and effect; and

###### The Design-Builder shall have provided the City with the final, approved Health and Safety Plan in accordance with the Contract Standards.

The foregoing requirements are in addition to any other preconditions to the commencement of Construction established by the Contract Documents.

## GMP SUBMITTAL.

### Stage 1 Preliminary Services and GMP Submittal.  As part of the Stage 1 Preliminary Services, the Design-Builder is obligated to develop the design of the Project to a level sufficient to make the GMP Submittal.  The GMP Submittal, as described in the Preliminary Services set forth in Appendix 2, shall be completed and submitted to the City on a timely basis as required under Appendix 2, and shall remain a firm offer by the Design-Builder for at least 90 days; provided that the City shall respond to the Design-Builder regarding the GMP Submittal in accordance with Appendix 2.  The Design-Builder shall not condition the GMP Submittal by inclusion of any requirement that a GMP Amendment be entered into by the parties or that a Notice to Proceed with Stage 2 Design-Build Work be issued by the City prior to the expiration of such 90 day period.  The GMP Submittal shall include and be based upon the Baseline Design Documents, Substantial Completion Standards and all other information, analysis, findings and reports developed by the Design-Builder during the performance of the Stage 1 Preliminary Services, and shall be prepared in accordance with the Contract Standards.  Without limiting the requirements of Appendix 2, the GMP Submittal shall include a price submittal, a technical submittal and an additional information submittal, as follows:

Price Submittal:

###### A proposed Base Guaranteed Maximum Price, to be incorporated in Section 8.7.2 of Appendix 8, together with all supporting information required by subsection (B) of this Section;

###### A proposed Anticipated Stage 2 Design-Build Cost Schedule and a proposed Design-Builder Contingency, to be prepared in accordance with, and attached as part of Attachment 8C to Appendix 8;

###### If applicable and requested by the City, a list of any proposed allowance items, alternate prices and unit prices;

###### Technical Submittal:

###### Proposed Baseline Design Documents, to be incorporated in and to constitute Appendix 4 of this Design-Build Contract;

###### The final and complete list of required Governmental Approvals for the Project (including Governmental Approval Application Dates and Assumed Approval Issuance Dates, all as required by Appendix 2) to be incorporated in Appendix 3 of this Design-Build Contract;

###### A description of any Change-in-Law that has occurred between the Contract Date and the date of the GMP Submittal;

###### An updated and finalized description of the Project alignment and the Project Sites;

Commercial Terms Submittal:

###### A proposed Stage 2 Baseline Design-Build Schedule including the Scheduled Substantial Completion Date (expressed as the number of calendar days following the GMP Amendment Date by which Substantial Completion shall be achieved); and

###### A proposed delay liquidated damages amount to be inserted in subsection 8.3(C).

Additional Information Submittal:

###### A proposed final Subcontracting Plan;

###### The names of additional proposed Subcontractors (other than any existing Approved Subcontractors) and descriptions of their roles for approval by the City as Approved Subcontractors;

###### A description of the manner in which any Early Work Packages will be integrated into the final Design-Build Work, including price, schedule and performance considerations;

###### A letter from a surety qualified under Section 16.1 confirming the intent of the surety to provide the Payment Bond and Performance Bond required under such Section on the GMP Amendment Date;

###### A listing of any assumptions, clarifications or qualifications made by the Design-Builder in providing its GMP Submittal that are material to any part thereof, including a statement as to what information supplied by the City (if any) the Design-Builder proposes to use as the basis of any portion of its GMP Submittal; and

###### Any other information reasonably requested by the City prior to the due date for the GMP Submittal as necessary or appropriate to negotiate and complete the GMP Amendment.

### Derivation of Proposed Base Guaranteed Maximum Price.  The GMP Submittal shall include a detailed and comprehensive description of how the proposed Base Guaranteed Maximum Price was derived and the material factors on which it was based, all in compliance with the requirements for establishing the Base Guaranteed Maximum Price set forth in Appendix 2, together with any other related information required pursuant to this Section.  All costs, bids, quotes, estimates and other information supporting the GMP Submittal shall be made available to the City upon request.  The proposed Base Guaranteed Maximum Price and the other elements of the GMP Submittal shall be based upon the risk allocation established by this Design-Build Contract as of the Contract Date, unless the City, in its discretion, agrees to changes in such risk allocation.

### Stage 1 Preliminary Services Fee, Design-Builder Fee and General Conditions Fee.  The parties acknowledge and agree that the not-to-exceed amount of the Stage 1 Preliminary Services Fee, the Design-Builder Fee and the General Conditions Fee were proposed by the Design-Builder as part of the Proposal, negotiated by the parties prior to the Contract Date and included in this Design-Build Contract as executed on the Contract Date, and shall not be  subject to change in the GMP Submittal or the Definitive Contract Amendment.

### Early GMP Submittal.  The parties may agree, each in its discretion, that the GMP Submittal may be made, and the GMP Amendment negotiated, prior to the 60% design stage.  In such event, any Stage 1 Preliminary Services that have not been completed at the time of an early GMP Amendment shall be performed as part of the Design-Build Work and the compensation therefor paid as part of the Stage 2 Design-Build Price.

## GMP AMENDMENT.

### Non-Compliant GMP Submittal.  In the event the GMP Submittal does not comply with the requirements of this Design-Build Contract, the City shall provide written notice to the Design-Builder of any additions, corrections or revisions required to achieve such compliance.  In such event, the Design-Builder, at its cost and expense, and without any increase in the Stage 1 Preliminary Services Fee, shall promptly take all necessary rectification action, making multiple re-submittals if required.  The failure of the Design-Builder to furnish the Stage 1 Preliminary Services and provide the GMP Submittal in accordance with the Contract Standards shall be a material breach of this Design-Build Contract.

### Negotiation and Execution of the GMP Amendment.  The City and the Design-Builder acknowledge and agree that each intends to negotiate and enter into a Contract Amendment for the performance of all Construction and all other Design-Build Work necessary to achieve Final Completion (the “GMP Amendment”) based on the GMP Submittal and the completion of the other Stage 1 Preliminary Services.  The principles for negotiating the Base Guaranteed Maximum Price are set forth in subsection (C) of this Section.  The GMP Amendment at a minimum shall incorporate and definitively address all of the items identified in (A).  In the event the parties elect to execute the GMP Amendment, the date of execution and delivery thereof shall constitute the “GMP Amendment Date” hereunder, and thereupon the Stage 2 Design-Build Period shall commence.  Without limiting anything set forth in this Design-Build Contract, the parties may enter into a GMP Amendment that includes a fixed lump sum price for completion of the Design-Build Work in lieu of a Base Guaranteed Maximum Price and such GMP Amendment shall include modifications to the terms and conditions specified herein necessary to effectuate payment for Design-Build Work based upon the fixed lump sum price.  The parties acknowledge and agree that the GMP Amendment shall be reflected in an amendment and restatement of this Design-Build Contract, and will not be effective except upon approval by the City Council.

### Base Guaranteed Maximum Price Negotiating Principles.  Each party acknowledges that it intends to negotiate the Base Guaranteed Maximum Price taking into account the following:

(1)	The reasonably estimated costs of completing the design and construction of the Project (including costs payable under Early Work Packages) and achieving Substantial Completion and Final Completion in accordance with the Contract Standards and the cost elements set forth in Appendix 2.  Considerations of risk shall be taken into account separately, pursuant to item (2) below.  Such costs shall be the basis of the items constituting the Anticipated Stage 2 Design-Build Cost Schedule.

(2)	An amount reasonably attributable to indeterminable costs that, considered individually and valued in the aggregate based on agreed-upon probability-of-occurrence models adapted specifically to the Project, may be incurred should the risks assumed by the Design-Builder in performing the Design-Build Work occur.  Such costs shall be the basis of establishing the Design-Builder Contingency.  The risks assumed by the Design-Builder shall be identified in the risk register prepared as part of the Stage 1 Preliminary Services, and include:

##### The risks identified as excluded from the definitions of “Uncontrollable Circumstances”;

##### The risk of Subcontractor delay or non-performance;

##### Changes in the scope or cost of Design-Build Work that may occur as the design is advanced from the level set forth in the Baseline Design Documents to a fully complete level;

##### The risk that inflation in the cost of commodities, materials, equipment, labor and services necessary for the completion of the Design-Build Work will exceed the level assumed by the parties in establishing the Base Guaranteed Maximum Price under item (1) above;

##### The risk that it may be necessary to incur additional capital and operating expenses in order to meet the Substantial Completion Standards and achieve Substantial Completion; and

##### Any other risk specifically referred to herein as a risk to be borne by the Design-Builder in performing the Design-Build Work.

(3)	The fact that costs associated with Uncontrollable Circumstances are separately compensable from the Stage 2 Design-Build Costs that are limited by the Base Guaranteed Maximum Price.  Such costs shall be borne by the City as and to the extent provided in Article 14 and shall not be included in the Design-Builder Contingency.

### Obligations of the Design-Builder Relating to the GMP Amendment.  In connection with a potential GMP Amendment, the Design-Builder shall be obligated (1) to make a complete bona-fide GMP Submittal in accordance with this Section and Section 5.7, and (2) to negotiate in good faith toward a GMP Amendment based on the GMP Submittal, if and to the extent the City elects pursuant to subsection (E) of this Section to enter into and continue such negotiations.  The Stage 1 Preliminary Services do not include negotiating a GMP Amendment, and the Design-Builder represents that the Stage 1 Preliminary Services Fee does not include consideration for the costs and expenses of negotiating the GMP Amendment.  The Design-Builder shall bear all such negotiating costs and expenses, whether paid or incurred concurrently with or upon completion of the performance of the Stage 1 Preliminary Services and the preparation and delivery of the GMP Submittal.

### No Obligation of the City to Enter Into a GMP Amendment.  Notwithstanding the intent of the parties as expressed in subsection (B) of this Section, the City has no obligation whatsoever to negotiate with the Design-Builder to enter into a GMP Amendment.  The City, in its discretion, may elect not to commence or continue negotiations and not to enter into and execute a GMP Amendment for any reason.  The Design-Builder acknowledges and agrees that no failure by the City to negotiate or to enter into the GMP Amendment shall entitle the Design-Builder to make any claim for damages or compensation as a result of any such failure, and all such claims are hereby waived and released by the Design-Builder.  The Design-Builder acknowledges and agrees that neither the intent of the parties to negotiate and enter into the GMP Amendment, nor the conduct or discontinuance of any such negotiations, shall be construed to limit or affect the City’s right to terminate this Design-Build Contract for its convenience at any time as provided in Section 12.6.

### Elective Continuance of the Project by the Parties on Other Bases.  The City at any time may request a proposal from the Design-Builder or the lead design Subcontractor acting as Engineer-of-Record to provide professional engineering and other services necessary to advance the design of the Project (either partially or to the fully complete level) so that the Project may be procured and constructed on a design-bid-build or other alternative basis.  The Design-Builder shall make a bona fide proposal to enter into such services on terms and conditions substantially identical to the terms and conditions of this Design-Build Contract pertaining to the design services element of the Stage 1 Preliminary Services, and to negotiate in good faith to enter into a Change Order with the City to provide such services.  At the City’s request, the Design-Builder shall cause the lead design Subcontractor to make such proposal and to negotiate in good faith to enter into a separate agreement with the City to provide such services.

### Elective Continuance of the Project by the City with Other Contractors; Project Documents.  The City shall have the right at any time in its discretion to proceed to develop and implement the Project with other contractors and service providers.  The City may exercise such right during the performance of the Stage 1 Preliminary Services, upon termination of this Design-Build Contract or upon any failure of the parties to execute a GMP Amendment.  The City shall have the further right in connection therewith, based on its ownership of the Stage 1 Preliminary Services Deliverable Material as provided in Section 4.8, to use any Stage 1 Preliminary Services Deliverable Material in any manner it chooses to complete the design and construction of the Project.  In such event, the Design-Builder shall be liable for the Stage 1 Preliminary Services Deliverable Material solely to the extent of errors or omissions in the Stage 1 Preliminary Services Deliverable Material, as determined based on the developmental stage of the Stage 1 Preliminary Services Deliverable Material at the time of transfer to the City and a standard of care ordinarily used by members of the subject profession, having experience with projects similar in scope and complexity and practicing in major United States urban areas.  This limitation as to the Design-Builder’s liability for the Stage 1 Preliminary Services Deliverable Material is applicable only to the extent the City determines not to enter into the GMP Amendment or otherwise terminates this Design-Build Contract and is intended to recognize the City’s investment in the Stage 1 Preliminary Services Deliverable Material and to provide the City with a meaningful alternative for the design and construction of the Project in such circumstances, while recognizing that the Design-Builder will not have control over the use of the Stage 1 Preliminary Services Deliverable Material in such circumstances.  The Design-Builder acknowledges and agrees that such limitation will have no applicability if the parties enter into the GMP Amendment and proceed with the Stage 2 Design-Build Work.

### Design-Builder Representations in a GMP Amendment.  In the event the parties execute a GMP Amendment, the GMP Amendment shall be deemed to constitute a representation by the Design-Builder that:

###### It has examined, carefully studied, and thoroughly understands the Contract Documents associated with the Design-Build Work;

###### It has thoroughly reviewed and verified all information (except that the Design-Builder is not required to verify the information identified in subsection 4.5(B) other than as set forth therein) provided to or obtained by the Design-Builder through the performance of the Stage 1 Preliminary Services, including:

- Reports of explorations and tests of subsurface conditions at or contiguous to the Project Sites and all drawings of physical conditions in or relating to existing surface or subsurface structures at or contiguous to the Project Sites which have been identified or made available by the City; and

- Reports as to Regulated Substances, if any, at the Project Sites which have been identified or made available by the City;

###### It has become familiar with and is satisfied as to the general, local, and Project Sites conditions that may affect cost, progress, and performance of the Design-Build Work;

###### It is familiar with and is satisfied as to all Applicable Law that may affect cost, progress, and performance of the Design-Build Work;

###### It is aware of the nature of the Related Projects and is satisfied that the Design-Build Work can be performed in accordance with the requirements concerning the Related Projects, as set forth in the Contract Documents;

###### It has considered the information known to the Design-Builder, including information commonly known to designers and contractors doing business in the locality of the Project Sites; information and observations obtained from visits to the Project Sites; and the Project Sites-related reports and drawings identified in the Contract Documents, with respect to the effect of such information, observations, and documents on:

- The cost, progress, and performance of the Design-Build Work;

- The means, methods, techniques, sequences, and procedures of construction to be employed by the Design-Builder, including any specific means, methods, techniques, sequences, and procedures of construction expressly required by the Contract Documents; and

- Design-Builder’s health and safety precautions and programs;

###### Based on all of the foregoing and the performance of the Stage 1 Preliminary Services, the Project Sites constitute acceptable and suitable sites for the performance of the Design-Build Work;

###### It does not consider that further examinations, investigations, explorations, tests, studies, or data are necessary for it to enter into the GMP Amendment for the performance of the Design-Build Work for the Base Guaranteed Maximum Price on or before the Scheduled Substantial Completion Date, and in accordance with the other terms and conditions of this Design-Build Contract;

###### The Baseline Design Documents are sufficient to enable the Design-Builder to determine the Base Guaranteed Maximum Price; and

###### Subject to the terms and conditions of this Design-Build Contract, the Design-Build Work can be completed in accordance with the Contract Standards for the Base Guaranteed Maximum Price by the Scheduled Substantial Completion Date.

### Performance Bond and Payment Bond.  The Design-Builder, as provided in (A) and in Section 16.1, shall provide the Performance Bond and the Payment Bond concurrently with the execution of the GMP Amendment.

## APPROVALS REQUIRED PRIOR TO STAGE 2.  The parties acknowledge that the Design-Builder and the City will be obtaining Governmental and Non-Governmental Approvals during the Stage 1 Preliminary Services Period.  The parties further acknowledge that the City does not intend to execute a GMP Amendment until all Governmental and Non-Governmental Approvals listed in Appendix 3 have been obtained, unless waived in writing by the City.

# DESIGN-BUILD WORK

## STAGE 2 DESIGN-BUILD WORK GENERALLY.

### Authorization to Proceed; Commencement and Completion of the Stage 2 Design-Build Work.  The City shall issue a Notice to Proceed with the Stage 2 Design-Build Work concurrently with the occurrence of the GMP Amendment Date, and following issuance of such Notice to Proceed with Stage 2 Design-Build Work the Design-Builder shall promptly proceed to undertake, perform and complete the Design-Build Work in accordance with the Contract Standards; provided, however, that the Design-Builder shall not commence Construction of the Project until the Construction Commencement Date.  The Design-Builder shall be paid the Stage 2 Design-Build Price pursuant to Article 9 as its entitlement to payment of portions of the Stage 2 Design-Build Price arise thereunder.

### Elements of the Stage 2 Design-Build Work.  In performing the Stage 2 Design-Build Work generally, the Design-Builder shall, in accordance with the Contract Standards:

###### Apply for, obtain and maintain any Governmental and Non-Governmental  Approvals required for the Stage 2 Design-Build Work (other than the City Managed Governmental Approvals), and assist the City in obtaining the City Managed Governmental and Non-Governmental Approvals which have not been obtained as of the GMP Amendment Date; [Note: It is anticipated that all approvals identified in Appendix 3 will have been obtained prior to the GMP Amendment Date];

###### Perform all necessary Project Sites preparation and excavation activities;

###### Demolish and remove any existing improvements at the Project Sites, as and to the extent required by the Baseline Design Documents;

###### Modify, re-route, repair or replace or cause the modification, re-routing, repair, or replacement of, any Utilities, as and to the extent required by the Contract Documents;

###### Remove from the Project Sites and dispose of any demolition or construction debris resulting from the Design-Build Work and any unused soil excavated therefrom in an environmentally safe manner;

###### Complete the design and construct the Project;

###### Restore the surface of the Project Sites to the condition prior to construction and consistent with the standards and requirements set forth in Appendix 4.

###### Achieve Substantial Completion; and

###### Achieve Final Completion,

all so that the Project is suitable and adequate for the purposes hereof.

### Sequencing and Staging of Stage 2 Design-Build Work.  The Design-Builder shall not be limited in the sequencing or staging of the Stage 2 Design-Build Work, except to the extent that the Contract Standards impose limitations.  The City understands and acknowledges that the Design-Builder intends to complete the Stage 2 Design-Build Work in stages, whereby particular segments of the Stage 2 Design-Build Work will be designed and built prior to the completion of the design of the Project as a whole.  Although this Design-Build Contract does not require the Design-Builder to fully complete the entire design of the Project prior to proceeding with particular segments of the Construction of the Project, the Design-Builder shall comply with all requirements of Applicable Law in performing the Design-Build Work and shall further comply with the design submittal requirements set forth in (C).

### Construction Work Hours.  Without limiting any other requirement hereunder, the Design-Builder shall not perform Construction work between 6 PM and 7 AM, or on Sundays, holidays or Saturdays without specific permission from the City.  The parties acknowledge that compliance with the Project Schedule is critical, and the City agrees to act reasonably and cooperate with the Design-Builder in an effort to accommodate reasonable Design-Builder requests to perform Construction work during the hours specified in the preceding sentence to the extent consistent with Applicable Law.

### Laydown Areas.  Laydown and staging areas for construction materials required for the Design-Build Work shall be located off-Project Site at locations identified and provided by the Design-Builder and shall be identified in the Baseline Design Documents.

### Stage 2 Design-Build Work Schedule and Reports.  The initial Stage 2 Design-Build Work Schedule shall be prepared in accordance with Appendices 2 and 5 during performance of the Stage 1 Preliminary Services.  Throughout the Stage 2 Design-Build Period, the Design-Builder shall further update and maintain the Stage 2 Design-Build Work Schedule in accordance with Appendix 5.  The Design-Builder shall provide Monthly Progress Reports, which shall include updates to the Stage 2 Design-Build Work Schedule, in accordance with the requirements set forth in Section 4.99 and Appendix 5.  The Design-Builder acknowledges and agrees that it has a material obligation to provide the City with, and to update, maintain and revise, the Stage 2 Design-Build Work Schedule throughout the Stage 2 Design-Build Period in accordance with the Contract Standards.

### On-Site Meetings and Design and Construction Review.  During the Stage 2 Design-Build Period, the Design-Builder, the City and the Owner Representative shall conduct regular progress and management meetings as set forth in Appendix 5.  Such meetings shall take place in a field office to be provided by the Design-Builder in accordance with Appendix 5 or as otherwise directed by the City.  The Monthly Progress Report shall be prepared by the Design-Builder and provided to the City and the Owner Representative at least five days prior to each monthly meeting.

### Construction Utilities.  The Design-Builder shall provide, make all arrangements necessary to secure the availability of all Utilities necessary for the performance of the Design-Build Work.  The Design-Builder shall be responsible for the payment of all Utility bills in a timely manner in connection with all Design-Build Work performed from the issuance of the Notice to Proceed with Stage 2 Design-Build Work until the Substantial Completion Date.

### Quality Assurance and Quality Control.  The Design-Builder shall have full responsibility for quality assurance and quality control for the Design-Build Work, including compliance with the Stage 2 Design-Build Work Quality Management Plan.  Without limiting any other requirement hereunder, the Design-Builder shall perform quality control inspection and testing services to assure compliance with the Contract Standards.

### Title and Risk of Loss.  Title to the pipes, structures, improvements, fixtures, machinery, equipment and materials constituting the Project shall pass to the City upon incorporation in the Project or payment therefor by the City, whichever first occurs, free and clear of all Encumbrances as provided in subsection (K) of this Section.  Except to the extent provided in (E), however, the Design-Builder shall bear all risk of loss concerning such pipes, structures, improvements, fixtures, machinery, equipment and materials until the Substantial Completion Date, regardless of the extent to which the loss was insured or the availability of insurance proceeds.  The procedures set forth in Section 6.19 shall be applicable in the event of any damage to, loss or the destruction of the Design-Build Work at the Project.  Notwithstanding anything set forth in this subsection (J) or Section 6.19, the Design-Builder shall bear all risk of loss concerning any pipes, structures, improvements, fixtures, machinery, equipment or materials required for the Design-Build Work and stored at any location other than the Project, regardless of whether the City has paid for any such structures, improvements, fixtures, machinery, equipment or materials.

### Encumbrances.  The Design-Builder shall not directly or indirectly create or permit to be created or to remain, and shall promptly discharge or bond any Encumbrance or Lien (other than Permitted Encumbrances) arising in relation to the Project or the Design-Build Work.  The Design-Builder’s Subcontracts with all materialmen, suppliers, and Subcontractors shall provide that the sole recourse for such materialmen, suppliers, and Subcontractors for non-payment shall be against the Payment Bond.

### Notice of Default.  The Design-Builder shall provide to the City, promptly following the receipt thereof, copies of any notice of default, breach or non-compliance received under or in connection with any Governmental Approval, Subcontract, Security Instrument or other transaction agreement pertaining to the Contract Obligations.

### Required Project Manager Certification.  Any notice, certification, report or application delivered by the Design-Builder to the City in connection with the Design-Build Work, or payment therefor, under this Article, Article 8, Article 9 or any Appendix relating to the performance of the Design-Build Work shall be accompanied by a signed certificate of the Project Manager affirming the accuracy thereof to the best of his or her knowledge.  The form of certification required pursuant to this subsection (M) shall comply with all requirements of Applicable Law.

### Partnering Requirements.  The Design-Build Work shall be subject to the City’s formal partnering requirements, as set forth in Appendix 5.

### Temporary Project Sites Facilities.  The Design-Builder shall be responsible for ensuring that adequate temporary facilities are provided as necessary to enable Subcontractors to perform their work and that provisions have been made for all Project Sites facilities necessary for the Design-Builder to manage, inspect and supervise the Design-Build Work, including all facilities and services the cost of which constitutes a General Conditions Cost.

### Sensitivity to Stakeholders.  It is the intention of the City to be sensitive to the needs and concerns of the stakeholders.  It is the Design-Builder's responsibility to adhere to this intent to the best of its ability and in accordance with the approved Stakeholder Outreach Plan to be developed as part of the Stage 1 Preliminary Services.  The Design-Builder shall, whenever possible, address stakeholder inquiries about the Project in coordination with the City, provide to citizens lodging complaints the names and numbers of the City personnel with whom they can follow up (as provided by the City), immediately inform the City of any citizen complaints, and provide for continuous access to all private property affected by the Design-Build Work.

### Utility Coordination and Re-location.  The parties acknowledge the existence of underground Utility facilities along the alignment of the Project. The Design-Builder is responsible for coordination with the Utilities and implementing the measures identified in the Utility Relocation Plan developed by the Design-Builder as a Stage 1 Preliminary Service and approved by the City.  Such measures shall be carried out in a manner which will avoid or minimize any delays to the Project.  In undertaking excavation and tunneling, the Design-Builder shall comply with the State’s Underground Utilities Demand Prevention Act (RCW 19.122 et seq.).  The Design-Builder shall provide all Utilities with reasonable notification of the need for the Utility to adjust or relocate any facilities. Notification periods shall be at a minimum of 90 days.  In the event that a Utility is uncooperative or notifies the Design-Builder that it is unable to comply with the notice provided by the Design-Builder, the Design-Builder shall immediately notify the City so that the City can exercise any legal rights it may have.  The failure to comply with this subsection shall waive any right by the Design-Builder to seek Uncontrollable Circumstance relief as a result if a delay caused by a Utility, and shall constitute a breach by the Design-Builder which would allow the City to seek from the Design-Builder any damages incurred by the City as a result of such breach.

## CONSTRUCTION COMMENCEMENT DATE.

### Construction Commencement Date Generally.  Except with respect to Early Work Packages as provided in Section 5.6, in no event shall the Design-Builder commence with the Construction of the Project prior to the “Construction Commencement Date”.  The Construction Commencement Date shall not occur prior to the satisfaction of the following “Construction Commencement Date Conditions,” each of which must be and remain satisfied as of the Construction Commencement Date:

###### The Design-Builder shall have certified that it has completed all pre-construction requirements set forth in Appendix 5 and shall have provided the City with an updated Stage 2 Design-Build Work Schedule in accordance with Appendix 5 and Health and Safety Plan.

###### The Design-Builder shall have satisfied all requirements of Applicable Law with respect to the commencement of construction and shall have obtained all Governmental and Non-Governmental Approvals set forth in Appendix 3 and as otherwise required for the commencement of the Construction of the Project (unless waived by the City), and provided copies of such Governmental and Non-Governmental Approvals to the City.  All such Governmental and Non-Governmental Approvals shall be in full force and effect.

###### The Design-Builder shall have provided the City with certificates for all Required Insurance in accordance with Section 13.1 and certified that all such policies are in full force and effect and in compliance with the requirements of Section 13.1 and Appendix 10.

###### The Design-Builder shall have complied with the design submittal requirements set forth in (C) to the extent necessary to commence with the Construction of the Project.

###### The Design-Builder shall have held pre-construction conferences with the City and its representatives in accordance with Appendix 5.

The foregoing requirements are in addition to any other preconditions to the commencement of Construction established by the Contract Documents.

### Establishment of the Construction Commencement Date.  In no event shall the Construction Commencement Date be established prior to the satisfaction by the Design-Builder of the Construction Commencement Date Conditions.  The Design-Builder shall provide 10 days’ written notice to the City as to the satisfaction of the Construction Commencement Date Conditions and the date it proposes to establish as the Construction Commencement Date hereunder.  The City shall issue a Notice to Proceed with Construction on the Construction Commencement Date proposed by the Design-Builder upon satisfaction of the Construction Commencement Date Conditions.  In the event the City determines that the Design-Builder has not satisfied the Construction Commencement Date Conditions, notwithstanding the Design-Builder’s notice pursuant to this subsection, the City Contract Representative, by written notice to the Design-Builder delivered not later than three days prior to the Construction Commencement Date proposed by the Design-Builder, shall notify the Design-Builder of the City’s determination and state which conditions the Design-Builder has failed to satisfy.  The Design-Builder shall satisfy all such conditions prior to the establishment of the Construction Commencement Date.  Without limiting any of the foregoing, the City, in its discretion, may waive (in writing) a Construction Commencement Date Condition or issue a limited Notice to Proceed with Construction pending satisfaction by the Design-Builder of all Construction Commencement Date Conditions and the specific terms and conditions under which the Design-Builder is authorized to proceed with Construction shall be specified in such Notice to Proceed.

### Effect of the Establishment of the Construction Commencement Date.  Upon the issuance by the City of the Notice to Proceed establishing the Construction Commencement Date, the Design-Builder shall have the right to proceed with the Construction of the Project.  Absent the occurrence of Uncontrollable Circumstances as and to the extent provided in this Design-Build Contract, no delay in the establishment of the Construction Commencement Date shall entitle the Design-Builder to any price, schedule or performance relief hereunder.

## DIFFERING SITE CONDITIONS.

### Stage 1 Preliminary Services Relating to Differing Site Conditions.  The Design-Builder shall review all available information and undertake all soils, groundwater, utility, locations, facilities and other site conditions investigations required with respect to the Project Sites as required by the Stage 1 Preliminary Services, and shall furnish the City with the reports identified in Appendix 2.

### Commencing Subsurface Excavations.  Prior to commencing any trenching or excavations, the Design-Builder shall, taking into account the information in the Reference Documents and reports developed as part of the Stage 1 Preliminary Services and in compliance with Good Engineering and Construction Practice, conduct further site investigations in accordance with Appendix 5 (General Design-Build Work Requirements), including exploratory excavations and further borings, to confirm the location and type of underground structures that could be damaged as a result of the excavations.  Such underground structures include, but are not limited to, all sewer, water, gas, and other piping, and manholes, chambers, electrical conduits, wires, tunnels and other existing subsurface work located within or adjacent to the Project Sites.  The Design-Builder shall carefully sustain in their places and support, or if necessary relocate or causes to be relocated, all underground and surface structures located within or adjacent to the Project Sites and as required by the party owning or controlling such structure.  Existing surface facilities which are temporarily removed to facilitate installation of the Design-Build Work shall be replaced and restored to their original condition.  The Design-Builder shall notify the City at least five business days in advance of any work that might impact utilities of business or residents in the area surrounding the Project Sites so that the City can notify such businesses or residents of such work.  As set forth in subsection 6.1(Q), the Design-Builder shall comply with all requirements set forth under Applicable Law, including the Underground Utilities Damage Prevention Act prior to and during undertaking such excavations or tunneling.

### Discovery of Differing Site Conditions.  Upon discovering an alleged Differing Site Condition and before the condition is further disturbed, the Design-Builder shall immediately, after taking appropriate measures to secure the affected Design-Build Work: (1) stop work in and secure the affected area; and (2) notify the City of the alleged Differing Site Condition.  The Design-Builder’s notice to the City shall be issued by telephone or in person and followed within 24 hours thereafter by written notice, providing a brief description of why the condition encountered is considered a Differing Site Condition.  Promptly upon receipt of the Design-Builder’s notice, the City will investigate the Project Site conditions.  Such notice shall describe the specific ground conditions encountered and the measures taken to deal with the ground conditions.  Notwithstanding anything set forth in subsection Section 6.3 or in Article 14, no Uncontrollable Circumstance relief shall be allowed for any alleged Differing Site Condition unless the Design-Builder provides the City with notice in accordance with this subsection.

### Relief for Differing Site Conditions.  If the Design-Builder establishes that the actual conditions encountered during Construction: (1) meet the criteria for a Differing Site Condition, and (2) directly and materially impact the Design-Builder’s cost or time of performance, then the Design-Builder shall be entitled to Uncontrollable Circumstance relief as and to the extent provided in Section 14.1.  The Design-Builder shall not be provided relief for any conditions of which it should have been aware.

## REGULATED SITE CONDITIONS.

### Design-Builder Responsibilities.  The parties recognize that in performing the Design-Build Work, the Design-Builder may encounter various Regulated Site Conditions and is anticipated to, in fact, encounter Regulated Substances.  In performing the Design-Build Work, the Design-Builder shall exercise due care, in light of all relevant facts and circumstances, to avoid exacerbating any Regulated Site Condition after the location and existence of such Regulated Site Condition has been disclosed to the Design-Builder or becomes actually known by the Design-Builder through Stage 1 Preliminary Services or physical observation.  Notwithstanding anything to the contrary in this Section, the Design-Builder shall bear full responsibility for the handling, treatment, storage, removal, remediation, avoidance, or other appropriate action (if any), with respect to:

###### Any Regulated Substance present at, on, in or under, or migrating or emanating to or from the Project Sites, that was generated by or brought or caused to be brought on the Project Sites by any act or omission of the Design-Builder or any Subcontractor; and

###### The creation of any Regulated Site Condition due to Design-Builder Fault, or the exacerbation of any Regulated Site Condition due to Design-Builder Fault once the location and existence of such Regulated Site Condition becomes actually known to the Design-Builder.

All remediation costs resulting from Regulated Substances or Regulated Site Conditions for which the Design-Builder bears responsibility pursuant to this subsection (A) shall constitute Unallowable Costs borne solely by the Design-Builder.  The Design-Builder shall indemnify, defend and hold harmless the City Indemnitees in accordance with and to the extent provided in Article 15 from and against all Loss-and-Expense resulting from Regulated Substances or Regulated Site Conditions for which the Design-Builder bears responsibility pursuant to this subsection (A).

### Cultural Resources.  The Design-Builder shall not remove or disturb, or cause to be removed or disturbed, any historical, archaeological, architectural, or other cultural artifacts, relics, vestiges, remains, or objects of antiquity.  If the Design-Builder discovers any of these items, the Design-Builder shall immediately notify the City Contract Representative and comply with the cultural resources discovery plan and procedures prepared by the City in connection with the Project, and all Applicable Law.

### Endangered Species.  Should either threatened or endangered plant or animal species (as determined under Applicable Law) be encountered in the performance of the Design-Build Work, the Design-Builder shall cease work immediately in the area of encounter, notify the City Contract Representative and comply with all Applicable Law. The Design-Builder shall not resume Design-Build Work in the affected area until authorized to do so by the City Contract Representative.

### Encountering of Regulated Substances.  If the Design-Builder encounters any materials or substances at the Project Site that it reasonably believes to be Regulated Substances, it shall immediately notify the City and shall comply with the Contaminated Media Management Plan developed by the Design-Builder pursuant to the Stage 1 Preliminary Services.

### Uncontrollable Circumstance Relief.  Without limiting the Design-Builder’s obligations under subsection (D) of this Section, if the Design-Builder establishes that the actual conditions encountered during Construction:

###### Meet the criteria for Regulated Site Conditions;

###### Directly and materially impact the Design-Builder’s cost or time of performance; and

###### Were not known or could not have been reasonably discovered through the Design-Builder’s performance of the Preliminary Services including the preparation of the Contamination Assessment Report and the Contaminated Media Management Plan, review of Reference Documents including the Cultural Resources Assessment or reasonable diligence;

###### then the Design-Builder shall be entitled to Uncontrollable Circumstance relief as and to the extent provided in Article 14.  The Design-Builder acknowledges that the Reference Documents and Stage 1 Preliminary Services have identified the presence of Regulated Substances on the Project Sites and the Base Guaranteed Maximum Price is intended to include all costs associated with such identified Regulated Substances.  No Uncontrollable Circumstance relief will be granted due to the presence of Regulated Substances that were disclosed to the Design-Builder as of the Baseline Date.

### Generator Liability.  Nothing contained herein is intended to identify the Design-Builder as the generator of any pre-existing Regulated Substance, except as provided by Applicable Law.  Except with respect to those Regulated Substances identified in subsection (A) of this Section as to which the Design-Builder bears responsibility, the City shall execute, as generator, Hazardous Waste manifests required in order for the Design-Builder to fulfill its obligations under this Section, as and to the extent required under Applicable Law.

## PERMITTING RESPONSIBILITIES AND SCHEDULE.

[NOTE: The City has determined to make the receipt of all material permits a condition to execution of the GMP Amendment, however, the following provisions are included to describe the parties’ responsibilities with respect to obtaining such approvals whether obtained before the GMP Amendment Date, in the event the City waives receipt of a permits as a condition to the GMP Amendment.]

### Design-Builder Governmental and Non-Governmental Approval Responsibility, Generally.  The Design-Builder shall, except for the City Managed Governmental and Non-Governmental Approvals, obtain and maintain all Governmental Approvals and Non-Governmental Approvals necessary to commence, continue and complete the Design-Build Work and achieve Substantial Completion.  In connection therewith, the Design-Builder shall:

#### Prepare and complete all required filings, applications and reports;

#### Develop and furnish all necessary data, information, plans, documentation and supporting material;

#### Familiarize itself with all applicable terms and conditions;

#### Attend all required meetings and hearings;

#### Pay all required permit and filing fees; and

#### Take all other action necessary in obtaining, maintaining, renewing, extending and complying with the terms of all Design-Builder Governmental and Non-Governmental Approvals.

The Design-Builder shall be responsible for identifying, obtaining and maintaining any Governmental and Non-Governmental Approvals required for the performance of the Design-Build Work that are not the City Managed Governmental Approvals.

### Application Process.  The City shall be notified by the Design-Builder prior to any application, data submittal, or other communication by the Design-Builder with any Governmental Body regarding Governmental Approvals.  The Design-Builder shall not knowingly take any action in any application, data submittal or other communication with any entity regarding Governmental or Non-Governmental Approvals or the terms and conditions thereof that would impose any unreasonable cost or unreasonable burden on the City or that would materially contravene any City policies with respect to the matters contained therein.  The City reserves the right, after reasonable notification and consultation with the Design-Builder, to modify, alter, amend, delete or supplement any information supplied, or term or condition proposed, by the Design-Builder which would have the effect described in the preceding sentence.  The final terms and conditions of any Governmental Approval shall be subject to the City’s approval, which approval shall not be unreasonably withheld or delayed.  The Design-Builder shall deliver to the City, promptly after the Design-Builder’s receipt, a copy of each Governmental Approval, and shall provide a listing of the status of all Governmental Approvals in its Monthly Progress Report.

### City Governmental Approval Responsibility.  The City shall:

###### Be responsible for obtaining the City Managed Governmental Approvals, subject to the Design-Builder’s obligations under subsection (D) of this Section;

###### Cooperate with and, upon the reasonable request of the Design-Builder, provide reasonable assistance to the Design-Builder in obtaining from Governmental Bodies the Governmental Approvals (including any modifications, renewals and extensions of existing Governmental Approvals from Governmental Bodies) required to be obtained by the Design-Builder under this Section;

###### Where necessary to obtain, renew, replace, extend the validity of, or arrange necessary amendments to any Governmental Approval and within a reasonable period of time after being requested to do so by the Design-Builder:

##### Execute Governmental Approval application and related documents, either in its own name or jointly with the Design-Builder, as and to the extent required under Applicable Law or the administrative practices of the applicable Governmental Body;

##### Provide for attendance by appropriate City staff at public hearings and meetings of applicable Governmental Bodies; and

##### Provide the Design-Builder with existing relevant data and documents that are within the City’s custody or control or are reasonably obtainable by the City and which are reasonably required for such purpose.

To the extent Applicable Law or the administrative practice of the applicable Governmental Body requires that Governmental Approvals that are required to be obtained by the Design-Builder pursuant to this Section be applied for or issued in the City’s name or that the City directly coordinates with such Governmental Bodies, the Design-Builder shall, at its own cost and expense, provide all necessary support and efforts to apply for and obtain such Governmental Approvals, including preparing all application and related documents for execution by the City.  The City’s obligation to assist and cooperate pursuant to this Section shall be subject to the Design-Builder’s obligations under this Section and shall not require the City to:

###### Staff the Design-Builder’s permitting or development efforts, to undertake any new studies or investigations with respect to the Project, or to affirmatively seek to obtain the issuance of the Governmental Approvals required to be obtained by the Design-Builder hereunder;

###### Take a position which it believes to be inconsistent with the Contract Documents, the Contract Standards, or the City policy (except policies that are incompatible with the contracting methodology associated with this Design-Build Contract or are inconsistent with the express obligations of the City hereunder);

###### Take a position that is not usual and customary for the City to take in addressing similar circumstances affecting its own projects (except for usual and customary arrangements that are incompatible with the contracting methodology associated with this Design-Build Contract or are inconsistent with the express obligations of the City hereunder); and

###### Refrain from concurring with a position taken by Governmental Body if the City believes that position to be correct.

### Design-Builder Responsibility For the City Managed Governmental Approvals.  In connection with the City Managed Governmental and Non-Governmental Approvals, the Design-Builder shall cooperate with and assist the City in carrying out any of the City’s responsibilities hereunder with respect to the City Managed Governmental and Non- Governmental Approvals, including:

#### Preparing and completing all required filings, applications and reports;

#### Developing and furnishing all necessary data, information, plans, documentation and supporting material;

#### Familiarizing itself with all applicable terms and conditions;

#### Attending all required meetings and hearings; and

#### Take all other action reasonably necessary in accordance with Good Engineering and Construction Practice to assist the City in obtaining, complying with, maintaining, renewing, and extending all the City Managed Governmental and Non-Governmental Approvals.

### Schedule Adjustment Based on Delays Affecting Design-Builder Managed Governmental Approvals.  If in seeking to obtain a Governmental or Non-Governmental Approval:

###### The Design-Builder has complied with the requirements of this Design-Build Contract;

###### The Design-Builder has submitted all applications, data, studies, reports, responses and other information required under Applicable Law and the adopted administrative practice of the Governmental Body in order to obtain the Governmental Approval;

###### The Design-Builder has in all respects used its best efforts to obtain the Governmental Approval; and

###### There has been a failure to issue the Governmental Approval by the “Assumed Approval Issuance Date” set forth in the Governmental Approvals Schedule Table;

then an Uncontrollable Circumstance shall be deemed to have occurred and the Design-Builder shall be entitled to an adjustment to the Scheduled Substantial Completion Date in accordance with Article 14 and to the extent provided therein and in this subsection (E).  The Design-Builder shall not be entitled to an adjustment of the Base Guaranteed Maximum Price or the not-to-exceed Preliminary Services Fee in connection with any delay in the receipt of Governmental or Non-Governmental Approvals.

### Adjustment to Scheduled Substantial Completion Date Based on Delays in Obtaining City Managed Governmental Approvals.  In the event any delay in the issuance of a City Managed Governmental or Non-Governmental Approval materially delays the achievement of Substantial Completion, an Uncontrollable Circumstance shall be deemed to have occurred and the Design-Builder shall be entitled to an adjustment to the Scheduled Substantial Completion Date as and to the extent provided, and upon compliance with the procedures set forth in Article 14, except to the extent the Design-Builder fails to comply with its obligations with respect thereto under this Section, under the Approvals Responsibility Table, or under Section 17.10.  Schedule relief shall be granted under this subsection only if the delay in issuance of a City Managed Governmental Approval materially affects the Design-Build Schedule’s critical path.  The Design-Builder shall not be entitled to an adjustment in the not-to-exceed Stage 1 Preliminary Services Fee unless such delays were caused by the failure of the City to use good faith efforts to obtain such approvals in a timely manner.

### Relief Based on Certain Permitting Terms and Conditions.  In the event that a Governmental Body imposes terms and conditions in connection with a Governmental Approval following the execution of the GMP Amendment that require material changes to the Technical Specifications or the Acceptance Standards, an Uncontrollable Circumstance shall be deemed to have occurred and the Design-Builder shall be entitled to a Base Guaranteed Maximum Price Adjustment as and to the extent provided in Article 15.

## BNSF MASTER UTILITIES LICENSE AGREEMENT APPROVAL.  As set forth in Appendix 3, the Design-Builder is responsible for obtaining the Non-Governmental Approvals, including the BNSF Approval on behalf of the City.  The parties acknowledge that the City has entered into a Master Utilities License Agreement with BNSF dated December 27, 2006 that defines the procedures and terms and conditions for the City or those acting on behalf of the City to obtain a license from BNSF to construct water lines under and across certain portions of BNSF’s real corridor or property.  The Design-Builder shall apply for the BNSF Approval pursuant to the application requirements and terms and conditions set forth in the Master Utilities License Agreement (included in the list of Reference Documents).

## FINAL DESIGN RESPONSIBILITIES AND RISK ASSUMPTION.

### Performance of the Design Work.  Following the issuance of the Notice to Proceed with Stage 2 Design-Build Work, the Design-Builder agrees to undertake, perform, and complete the designs and plans for the Project in accordance with the Contract Standards and to prepare all Stage 2 Design Documents necessary or appropriate to carry out and complete the Design-Build Work.  All Design-Builder working and final Stage 2 Design Documents shall comply with the Baseline Design Documents and shall ensure that the Project is constructed to a standard of quality, integrity, durability and reliability which is equal to or better than the standard established by the Baseline Design Documents.  The Design-Builder shall be responsible for the professional quality, technical accuracy, timely completion and coordination of all Stage 2 Design Documents and shall, without additional compensation, correct or revise any errors, omissions or other deficiencies in the Baseline Design Documents or the Stage 2 Design Documents.

### Sole Responsibility and Liability.  The Design-Builder shall have the sole and exclusive responsibility and liability for the design[ (except with respect to the Tacoma Water main, if applicable)], construction, and performance capability of the Project hereunder in accordance with the Contract Standards, (1) notwithstanding the fact that the RFP included certain design criteria, requirements and performance standards for the Design-Build Work, and (2) the City’s role in defining the nature and extent of the Stage 1 Preliminary Services, reviewing and commenting on the Stage 1 Preliminary Services Deliverable Material, and negotiating and agreeing upon the GMP Amendment.  The Design-Builder acknowledges that, in the RFP process, the performance of the Stage 1 Preliminary Services, the delivery of the GMP Submittal and the negotiation of the GMP Amendment, the Design-Builder had the unrestricted right and opportunity not to submit its Proposal and not to execute this Design-Build Contract or the GMP Amendment if the Design-Builder had determined that such design criteria and requirements or the establishment of the Contract Standards would in any manner or to any degree impair the Design-Builder’s ability to perform the Design-Build Work in compliance herewith.  Without limiting the Design-Builder’s right to claim relief in the event of Uncontrollable Circumstances as and to the extent provided in this Design-Build Contract, all risks relating to the design [(except with respect to the Tacoma Waster water main, if applicable)],  construction and performance capability of the Project, including all risks of design defects, constructability and efficacy, have been transferred to the Design-Builder under this Design-Build Contract.

### City Review and Comment on Stage 2 Design Documents.  The City shall have the right to review and comment on all Stage 2 Design Documents within the time frames specified in Appendix 7 in order to confirm the compliance and consistency of the Stage 2 Design Documents with the Contract Documents.  In no event shall the Design-Builder proceed with the Construction of any particular segment of the Design-Build Work without first complying with the requirements of Appendix 7.  The Design-Builder shall give due consideration and provide written responses, in the time and manner provided in Appendix 7, to any comments delivered by the City or its representatives as to the Design-Builder’s design submittals.  Neither compliance by the Design-Builder with the Baseline Design Documents, nor review and comment by the City or the Owner Representative on the Design-Builder’s Preliminary Design Documents or Stage 2 Design Documents, nor any failure by the City or the Owner Representative to comment on any design submittals shall in any way relieve the Design-Builder of full responsibility for the design, construction and performance capability of the Project, as demonstrated through the Substantial Completion Test, in accordance with the Contract Standards.  The parties acknowledge and agree that the review and comment rights of the City under this subsection (C) are intended for the informational purposes of the City and for the City to determine whether the Stage 2 Design Documents comply with the Baseline Design Documents.

### Documents at the Project Site.  The Design-Builder shall maintain at the Project Site all Stage 2 Design Documents, including a complete set of record drawings, in accordance with the Contract Standards.  These documents shall be available to the City for reference, copying and use, and a complete set thereof shall be delivered to the City upon completion of the Design-Build Work.

## CHANGES TO THE BASELINE DESIGN DOCUMENTS AT DESIGN-BUILDER REQUEST.

### City Consent Required.  The Design-Builder acknowledges the City’s material interest in each provision of the Baseline Design Documents, and agrees that, subject to Section 6.9, no material change to the Baseline Design Documents shall be made except with the consent of the City, which may be withheld or conditioned in its discretion.  Any such changes shall be evidenced by a Contract Amendment or Change Order, as applicable.

### Notice and Information as to Proposed Change.  Without limiting anything under subsection (A) of this Section, the Design-Builder shall give the City written notice of, and reasonable opportunity to review and approve, any Baseline Design Requirements Change proposed to be made at the Design-Builder’s request.  The notice shall contain sufficient information for the City to determine that the proposed Baseline Design Requirements Change:

###### Does not diminish the capacity of the Project to be operated so as to meet the Contract Standards;

###### Does not impair the quality, integrity, durability and reliability of the Project;

###### Is reasonably necessary or is advantageous for the Design-Builder to fulfill its obligations under this Design-Build Contract; and

###### Is feasible.

## OTHER CHANGES TO THE BASELINE DESIGN DOCUMENTS.

### Changes Made Due to Uncontrollable Circumstances.  Upon the occurrence of an Uncontrollable Circumstance after the GMP Amendment Date, the Design-Builder shall promptly proceed, subject to the terms, conditions and procedures set forth in Article 14 and subject to the City’s approval, to make or cause to be made all Baseline Design Requirements Changes reasonably necessary to address the Uncontrollable Circumstance.  The Design-Builder shall consult with the City concerning possible means of addressing and mitigating the effect of any Uncontrollable Circumstance.  The parties shall use all reasonable efforts to address Baseline Design Requirements Changes required due to Uncontrollable Circumstances in a manner that will not impact the critical path of planned Design-Build Work in the Stage 2 Design-Build Work Schedule.  The Design-Builder shall be entitled to schedule and price relief resulting from any such Baseline Design Requirements Change to the extent provided in Article 14.  Without limiting the right of the City to issue a Work Change Directive under Section 6.11, any Baseline Design Requirements Change made on account of Uncontrollable Circumstances, and any related change in the terms and conditions of the Contract Documents, shall be reflected in a Change Order.

### Changes Required by Governmental Bodies.  The parties recognize that a Governmental Body may impose terms and conditions in connection with a Governmental Approval after the issuance of the Notice to Proceed with Stage 2 Design-Build Work that require a Baseline Design Requirements Change.  In the event of the imposition of any such additional terms and conditions imposed by a Governmental Body, the Design-Builder shall promptly proceed, subject to the City’s approval, to make or cause to be made all Baseline Design Requirements Changes reasonably necessary to comply with such additional terms and conditions, or the City may elect to contest any such additional terms and conditions if such terms and conditions are not acceptable to the City; provided that, if such contest by the City delays the performance of the Design-Build Work, the Design-Builder shall be entitled to Uncontrollable Circumstance relief as and to the extent provided in Article 14.  As set forth in Section 6.5(H), the City shall bear the risk of the imposition of any such additional terms and conditions imposed by a Governmental Body in connection with a Governmental Approval.  Without limiting the right of the City to issue a Work Change Directive under Section 6.11, any such Baseline Design Requirements Change and any related change in the terms and conditions of this Design-Build Contract shall be reflected in a Change Order.

### Changes Required by the City.  The City shall have the right to require the Design-Builder to make Baseline Design Requirements Changes at any time prior to Final Completion in its discretion for any reason whatsoever, whether and however the exercise of such rights affects this Design-Build Contract so long as the Design-Builder’s rights are protected as provided in this subsection (C).  The Design-Builder shall be entitled to a Change Order providing appropriate price, schedule, performance and other relief in the event of a Baseline Design Requirements Change made at the direction of the City under this subsection (C); provided, however, that the Design-Builder shall not be entitled to any such price, schedule, performance or other relief to the extent that any such Baseline Design Requirements Change is required due to Design-Builder Fault.  The City shall have no obligation to make any Baseline Design Requirements Change on account of its rights under this subsection (C).

## CHANGE PROCEDURES.

### Generally.  The sole means of providing for an adjustment to the Scheduled Substantial Completion Date, the Contract Compensation or a Base Guaranteed Maximum Price Adjustment, or any other price, performance or schedule relief under this Design-Build Contract shall be through the issuance of a Change Order or Work Change Directive.  All work authorized or modified pursuant to a Change Order shall constitute Design-Build Work hereunder and shall be completed in accordance with the Contract Standards.  Each Change Order shall be specific and final as to prices and extensions of time with no reservations or other provisions allowing for future additional money or time as a result of the particular changes identified and fully compensated in the Change Order, except as provided in subsection (C) of this Section with respect to actual costs subject to Cost Substantiation.  Price determinations associated with Change Orders and Work Change Directives shall be made in accordance with Section 9.7.  The Design-Builder is not authorized to proceed with any contemplated change in the Design-Build Work prior to the Design-Builder's receipt of a Change Order or Work Change Directive.

### Design-Builder Change Order Proposal.  The City Contract Representative may, in anticipation of possibly issuing a Change Order, request the Design-Builder to prepare a proposal of cost and time to perform the contemplated changes in the Design-Build Work, along with any other proposed changes to this Design-Build Contract.  The Design-Builder’s written proposal shall be prepared in accordance with the Contract Standards on a proposal request form approved by the City Contract Representative and shall be transmitted to the City Contract Representative promptly, but not later than seven days (unless the City Contract Representative agrees to a longer duration, in writing) after the Design-Builder’s receipt of the City Contract Representative’s written request, and shall remain a firm offer for a period not less than 15 Business Days after receipt thereof by the City Contract Representative, unless the parties agree to a longer duration, in writing.

### Negotiation of Proposed Change Order.  The Design-Builder shall consult with the City and the Owner Representative concerning possible means of addressing any proposed Change Order, and the Design-Builder and the City shall cooperate in order to minimize any delay and lessen any additional cost associated with the Change Order.  The City may negotiate the written proposal delivered pursuant to subsection (B) of this Section.  If the City accepts such written proposal without adjustment to its terms, the City may issue a Change Order for the written proposal within the firm-offer period specified in subsection (B) of this Section, and the parties’ signing of the written proposal shall be deemed equivalent to signing the Change Order.  Change Orders may provide for a Base Guaranteed Maximum Price Adjustment based on (1) unit prices included in the GMP Amendment or otherwise agreed to by the parties; (2) negotiated lump sum pricing; (3) actual costs subject to Cost Substantiation in accordance with Section 9.8; or (4) a combination of the foregoing.  A Change Order that reduces the scope of the Design-Build Work shall provide for a Base Guaranteed Maximum Price Adjustment reducing the Guaranteed Maximum Price, as determined in the same manner as provided for any increase to the Guaranteed Maximum Price.  Except as otherwise directed by the City pursuant to Section 6.14, the Design-Builder shall, pending the negotiation of any Change Order, diligently proceed with the performance of all Design-Build Work not subject to such proposed Change Order.

### Effect of Design-Builder’s Signature.  The signing of a Change Order by the Design-Builder indicates the Design-Builder’s acceptance and approval thereof, including any adjustment to the Scheduled Substantial Completion Date or the Contract Compensation or other price, performance or schedule relief or change provided for therein.  The signing of any Change Order by the Design-Builder shall constitute an acknowledgement and agreement that:

###### Any compensation paid in conjunction with the terms of a Change Order shall comprise the total compensation due the Design-Builder for the work or the change defined in the Change Order;

###### The stipulated compensation includes all payment for the Design-Build Work authorized by the Change Order, including all payment for the interruption of schedules, stop work orders, extended overhead, delay, or any other impact, claim or ripple effect;

###### The Change Order constitutes full accord and satisfaction for the change in the Design-Build Work;

###### The Design-Builder reserves no right to pursue any subsequent claim concerning the Change Order; and

###### All necessary amendments to this Design-Build Contract, including all necessary Baseline Design Requirements Changes, are reflected in the Change Order and no subsequent claim or amendment to the Contract Documents will arise out of or as a result of the Change Order.

## WORK CHANGE DIRECTIVES.

### City Right to Issue.  The parties intend to negotiate the terms of any Change Order providing for a Baseline Design Requirements Change prior to the Design-Builder incurring any costs with respect to any such change or adjustment.  However, notwithstanding the foregoing, the City shall have the right to issue a written order directing a Baseline Design Requirements Change or other change to the Design-Build Work pursuant to this subsection (A), which order shall specify any appropriate price, performance or schedule relief, if any, associated with any such change (a “Work Change Directive”).  No Work Change Directive shall be made that would be contrary to Applicable Law.  Upon receipt of a Work Change Directive, the Design-Builder shall promptly proceed with the performance of any change in the Design-Build Work as instructed and shall promptly advise the City in writing of the Design-Builder’s agreement (or disagreement) with any price, performance or schedule relief, if any, as may be proposed by the City in the Work Change Directive.  If the Design-Builder receives a written communication signed on behalf of the City, which the Design-Builder believes is a Work Change Directive that is not so identified, it shall not proceed with the purported change in the Design-Build Work until it receives written confirmation from the City that such communication is in fact a Work Change Directive.  A Work Change Directive that is signed by the Design-Builder and approved by the City in accordance with its procurement rules and regulations, reflecting the scope of work and any price, schedule and performance relief, if any, shall be deemed a Change Order.

### Disagreement with Terms of a Work Change Directive.  If the Design-Builder disagrees in writing with the suggested price, schedule or performance relief, if any, set out in the Work Change Directive, the Design-Builder may elect to initiate dispute resolution procedures in accordance with Section 11.1.  In such case, the Design-Builder shall proceed with the performance of the Design-Build Work in accordance with the Work Change Directive and shall keep and present, in such form as the City may request, an itemized accounting to go with the appropriate supporting data with respect to the Design-Builder’s position, including all information necessary to substantiate any cost claimed by the Design-Builder.  The Design-Builder shall provide notice of any disagreement pursuant to this subsection (B) within 15 days after receipt of the Work Change Directive.  The failure of the Design-Builder to provide notice of any such disagreement in accordance with this subsection (B) shall constitute a waiver of any further right to dispute the terms and conditions of a Work Change Directive.

## STAGE 2 DESIGN-BUILD WORK DELIVERABLE MATERIAL.

As the Design-Build Work progresses (or upon the termination of the Design-Builder’s right to perform the Design-Build Work), the Design-Builder shall deliver to the City all Stage 2 Design-Build Work Deliverable Material.  The provisions of Section 17.7 shall apply to any Stage 2 Design-Build Work Deliverable Material used by the Design-Builder in the Design-Build Work that is proprietary in nature or otherwise subject to the property rights of a third party.  The City shall have the right from and after the Contract Date to use (or permit use of) all such Stage 2 Design-Build Work Deliverable Material, all oral information received by the City in connection with the Design-Build Work, and all ideas or methods represented by such Stage 2 Design-Build Work Deliverable Material, without additional compensation; provided, however, that the City shall not publish, distribute, or sell such Stage 2 Design-Build Work Deliverable Material to third parties not employed by or under contract to the City, except as required by Applicable Law with respect to public records requests or in connection with requests for proposals to perform construction work or design, or consulting services on behalf of the City and in connection with the performance of such work.  The City’s use of any such Stage 2 Design-Build Work Deliverable Material for any purpose other than the Project shall be at its own risk and the Design-Builder shall have no liability therefor.

## INTERFACE AND COORDINATION.

### Maintenance of Operations During Construction.  The Design-Builder shall undertake and execute the Design-Build Work in a manner which does not interfere with or impair the ongoing operations of the City utility systems or private utilities.  The Design-Builder shall comply with the requirements of the Utility Relocation Plan developed as part of the Preliminary Services and shall arrange and/or provide for all necessary bypasses and other measures necessary to maintain utility services.  The Design-Builder shall coordinate all Design-Build Work with the City in accordance with the Contract Standards, including the approved Utility Relocation Plan.

### Related Projects Generally.  The Design-Builder acknowledges that the City may be undertaking other projects at the Project Sites and, without limiting any other obligation under this Design-Build Contract, agrees to coordinate the Design-Build Work with the work associated with such other projects in accordance with the Contract Standards.  Any other project being undertaken at or in the vicinity of the Project Sites, are referred to herein as the “Related Projects”.  Nothing in this Design-Build Contract shall be interpreted as granting the Design-Builder exclusive occupancy of the Project Sites.  The Design-Builder must ascertain to its own satisfaction the scope of the Project and the nature of any other contracts that have been or may be awarded by the City in relation to its overall capital improvement program or other Related Project, of which the Design-Builder becomes aware.  The Design-Builder shall cause the Design-Build Work to be performed without damaging the work or property of any Separate Contractor and so as not to cause any unnecessary hindrance or delay to any Separate Contractors working at the Project Sites.  The Design-Builder agrees to reasonably cooperate and coordinate its activities with those of the City and all Separate Contractors so that the Project and any Related Project can be completed in an orderly and coordinated manner without unreasonable disruption.  The Design-Builder agrees that it shall not be entitled to any price, performance or other Uncontrollable Circumstance relief hereunder due to any delay or hindrance to the extent caused by a failure of any Design-Builder Person to cooperate or coordinate its work with the work of any Separate Contractor.

### Interrelated Work.  If part of the Design-Build Work depends on proper execution of construction or operations by the City or a Separate Contractor, the Design-Builder shall, prior to proceeding with that portion of the Design-Build Work, inspect the other work and promptly report to the City Contract Representative any apparent discrepancies or defects in the other construction that would render it unsuitable for the proper execution of the Design-Build Work.  The Design-Builder shall be entitled to Uncontrollable Circumstance relief as and to the extent provided in Article 14 in the event that defects in the work of the City or any Separate Contractor render the work unsuitable for the proper execution or result of any part of the Design-Build Work.  However, failure of the Design-Builder to report apparent discrepancies or defects in the other construction shall constitute acknowledgment that the City’s or the Separate Contractor’s completed or partially completed construction is fit and proper to receive the Design-Build Work, except as to discrepancies or defects not then reasonably discoverable pursuant to Good Engineering and Construction Practice.

### Disputes Associated with Separate Work.  If the performance of any work by the City or a Separate Contractor under contract with the City is likely to be interfered with by the simultaneous performance of some other contract or contracts, the City shall decide which contractor shall cease work temporarily and which contractor shall continue or whether the work under the contracts can be coordinated so that the contractors may proceed simultaneously.  Any decision by the City to halt or delay the performance of the Design-Build Work by the Design-Builder pursuant to this Section shall be made in accordance with Section 6.14, and the Design-Builder shall be entitled to Uncontrollable Circumstance relief as and to the extent provided therein.

## SUSPENSION OF WORK.

The City may, through a written notice executed by the City Contract Representative, order the Design-Builder to suspend, delay or interrupt all or any part of the Design-Build Work for such period of time as the City Contract Representative may determine to be appropriate for the coordination of the Related Projects or otherwise for the convenience of the City.  The Design-Builder shall have no entitlement to relief hereunder or any adjustment to the Scheduled Substantial Completion Date or the Contract Compensation under circumstances of the City ordering the Design-Builder to suspend, delay or interrupt all or any part of the Design-Build Work due to Design-Builder Fault, including any failure of compliance by any Design-Builder Person with the Design-Builder’s obligations under this Design-Build Contract in respect of the maintenance of operations during Construction, coordination in respect of Related Projects or any health and safety requirement.  However, if the City exercises its right to suspend, delay or interrupt all or any part of the Design-Build Work pursuant to this Section under circumstances other than Design-Builder Fault, an Uncontrollable Circumstance shall be deemed to have occurred, subject to the terms and conditions of Article 14.

## CONSTRUCTION PRACTICE.

### Exclusive Responsibility of Design-Builder.  The Design-Builder shall have exclusive responsibility for all construction means, methods, techniques, sequences, and procedures necessary or desirable for the correct, prompt, and orderly prosecution and completion of the Design-Build Work as required by the Contract Documents.  The responsibility to provide the construction means, methods, techniques, sequences and procedures referred to above shall include the obligation of the Design-Builder to provide the following construction requirements: supervision, tools, implements, machinery, labor, materials and accessories necessary and proper for the purpose; installation, periodic inspection, and removal of temporary site lighting, including specific task lighting and emergency lighting; temporary offices and construction trailers; installation, daily inspection, and removal of miscellaneous temporary barricades, fencing, partitions, and other means of temporary separation/isolation on the site during construction, including any temporary covered wooden walkways for sidewalks; required design certifications; required approvals; weather protection; dust control; noise abatement, barriers, etc.; miscellaneous de-watering requirements; clean-up and housekeeping of the Project Sites; construction trade management; temporary parking; vehicle traffic; health, safety and first aid facilities and equipment; correction of defective work or equipment; Subcontractors’ insurance; storage areas; workshops and warehouses; temporary fire protection; security of the Project Sites; temporary Utilities; Utility relocations necessary or convenient to its performance of the Design-Build Work; potable water; sanitary services; Subcontractor and vendor qualification; receipt and unloading of delivered materials and equipment; erection rigging; temporary supports; and construction coordination.  The use of explosives in connection with the performance of the Design-Build Work is permitted solely to the extent permissible under Applicable Law and with the prior written approval of the City, acting reasonably.

### Project Sites Debris, Trash and Waste.  The Design-Builder shall keep the Project Sites reasonably free from debris, trash and construction wastes to permit the Design-Builder to perform its construction services efficiently, safely and without interfering with the use of adjacent land areas and without causing complaints from Separate Contractors, adjacent property owners, local public officials or members of the public.  The Design-Builder shall be responsible for the maintenance of grass, shrubbery and trees located on the Project Sites, including any right of way.  Prior to Final Completion, the Design-Builder shall remove all debris, trash, construction wastes, materials, equipment, machinery and tools arising from the Design-Build Work or applicable portions thereof (and not otherwise incorporated into the Project in accordance with the Contract Documents).

## RESPONSIBILITY FOR SAFETY AND SECURITY.

### Safety Manager.  The Design-Builder assumes responsibility for implementing and monitoring all health and safety precautions and programs related to the performance of the Design-Build Work.  The Design-Builder shall, prior to commencing construction, designate an individual with the qualifications and experience necessary under Good Engineering and Construction Practice to supervise the implementation and monitoring of all health and safety precautions and programs related to the Design-Build Work (the “Safety Manager”).  The Safety Manager shall be an individual stationed at the Project Sites.

### Precautions and Protection; Project Sites Security.  The Design-Builder shall take all reasonable precautions for the health and safety of, and shall provide all reasonable protection to prevent damage, injury or loss to:

###### All employees on the Project Sites and all other persons who may be affected thereby;

###### All the Design-Build Work, whether in storage on or off the Project Sites, under the care, custody or control of Design-Builder or any of its Subcontractors.  Machinery and equipment shall have proper guards in place and all hazards shall be eliminated in accordance with the latest health and safety provisions of the OSHA Construction Industry Regulations 29 CFR, Parts 1910 and 1926; and

###### Other property at the Project Sites or adjacent thereto, including plant facilities, trees, shrubs, lawns, walks, pavements, roadways, structures and Utilities not designated for removal, relocation or replacement in the course of construction.

The Design-Builder shall develop and administer a security program for the Project Sites in coordination with the City.  The Design-Builder shall cooperate with the City in connection with the City’s program for the badging of all personnel and vehicles that require authorization for entry to the Project Sites.

### Health and Safety Inspections and Meetings.  The Design-Builder is solely responsible to inspect, survey, and assess the Project Sites and identify the existence of all permit-required confined spaces and non-permit confined spaces and comply with applicable OSHA regulations and standards.  The Design-Builder’s Project Sites assessment shall begin upon the initiation of Design-Build Work and continue throughout the duration of the Stage 2 Design-Build Period.  The Design-Builder shall comply with all health and safety requirements imposed by Applicable Law, including 29 CFR 1910.146, in the performance of the Design-Build Work.  The Safety Manager shall make routine daily inspections of the Project Sites and shall hold weekly health and safety meetings with the Design-Builder’s personnel, Subcontractors and others as applicable.  The Design-Builder shall provide minutes of each health and safety meeting to the City within five days of such meeting.

### Health and Safety Compliance Requirements.  The Design-Builder shall, and shall cause all Subcontractors to, shall comply with:

###### All Applicable Law relating to safety;

###### The Health and Safety Plan; and

###### Any the City-specific health and safety requirements provided to the Design-Builder.

The Design-Builder shall immediately report (no later than within 12 hours after its occurrence), in writing, any health and safety-related injury, loss, damage, accident or near miss arising from the Design-Build Work to the City and, to the extent mandated by Applicable Law, to all Governmental Bodies having jurisdiction over health and safety-related matters involving the Project.  Where any dangerous condition or nuisance exists in and around the Project Sites, including equipment and supply storage areas or other areas in any way connected with the performance of the Contract Obligations, the Design-Builder shall provide and maintain reasonable warning of such danger or nuisance.  The Design-Builder shall not create excavation, obstructions, or any dangerous condition or nuisance of any nature whatsoever in connection with the performance of this Design-Build Contract unless necessary to its performance, and in that event the Design-Builder shall provide and maintain at all times reasonable means of warning of any danger or nuisance created.  The duties of the Design-Builder in this Section shall be non-delegable, and the Design-Builder’s compliance with any specific recommendations or requirements of the City as to the means of warning shall not excuse the Design-Builder from the faithful performance of these duties should such recommendations or requirements not be adequate or reasonable under the circumstances.  The City, through the City Contract Representative, shall have the right to suspend any or all Design-Build Work if the Design-Builder fails to comply with its obligations hereunder without any requirements of providing the Design-Builder with Uncontrollable Circumstance relief hereunder.

### Emergencies.  The Design-Builder shall develop an emergency response plan in accordance with the requirements set forth in Appendix 5.  The emergency response plan shall be subject to the approval of the City and shall establish the protocols for the Design-Builder in dealing with emergencies impacting the performance of the Design-Build Work.  In case of an emergency which threatens immediate loss or damage to property or health and safety of life, the Design-Builder shall act immediately to prevent threatened loss, damage, injury or death.  The Design-Builder shall notify the City of the situation and all actions taken immediately thereafter.  If, in the opinion of the Design-Builder, immediate action is not required, the Design-Builder shall notify the City of the emergency situation and proceed in accordance with the City’s instructions.  However, if any loss, damage, injury or death occurs that could have been prevented by the Design-Builder’s prompt and immediate action, Design-Builder shall be fully liable for all costs, damages, claims, actions, suits, attorneys’ fees and all other expenses arising therefrom or relating thereto.  Prior to commencing its Design-Build Work and at all times during the performance of the Design-Build Work, the Design-Builder shall provide the City with two 24 hour emergency phone numbers where its representatives can be contacted.

### Traffic Control.  In the performance of Construction, the Design-Builder shall comply with all traffic related requirements of Applicable Law and shall comply with the traffic control requirements set forth in the Stage 2 Health and Safety Plan.

## CONSTRUCTION MONITORING, OBSERVATIONS, TESTING AND UNCOVERING OF WORK.

### Observations and Design-Build Work Review Protocol.  During the progress of the Design-Build Work through Final Completion, the Design-Builder shall at all times during normal working hours afford the City and its designated representatives, including the Owner Representative, every reasonable opportunity for observing all Design-Build Work at the Project Sites, and shall comply with the Design-Build Work review procedures set forth in Appendix 7.  The Design-Builder shall provide sufficient, safe and proper facilities at all reasonable times for the observation and inspection of the Design-Build Work by the City and its designated representatives. During any such observation and inspection, all representatives of the City shall comply with all reasonable health and safety and other rules and regulations applicable to presence in or upon the Project Sites, and shall in no material way interfere with the Design-Builder’s performance of any Design-Build Work.  The right of access provided for under this subsection (A) shall extend to all storage facilities associated with the Design-Build Work, whether located on or off the Project Sites.

### Factory Fabrication, Inspection and Testing.  The City reserves the right to have its designated representatives, including the Owner Representative, witness any factory fabrication, inspection or testing.  The Design-Builder shall provide the City with its anticipated schedule for such fabrication, inspection and testing at the initial Project meeting and shall provide 30 days’ advanced written notice of any actual factory fabrication, inspection or test.  The City shall provide the Design-Builder with reasonable advance notice (at least 14 days) of its intention to witness any factory fabrication, inspection or test pursuant to this subsection (B), which notice shall indicate the identity and number of designated representatives of the City who will witness the fabrication, inspection or test.

### Design-Builder Tests.  The Design-Builder shall conduct all tests of the Design-Build Work (including shop tests) or inspections required by the Contract Standards.  The Design-Builder shall give the City and the Owner Representative reasonable advance notice (consistent with the approved Stage 2 Design-Build Work Quality Management Plan prepared in accordance with Appendix 6) of tests or inspections required by the Contract Standards prior to the conduct thereof.  In no event shall the inability, failure, or refusal of the City or any of its representatives to attend or be present at or during any such test or inspection delay the conduct of such test or inspection, delay the performance of the Design-Build Work, or otherwise serve as the basis for relief from the Design-Builder’s obligations hereunder.  The Engineer-of-Record shall conduct or witness any such test or inspection to the extent required by the Contract Standards.  All analyses of test samples shall be conducted by persons appearing on lists of laboratories authorized to perform such tests by the State or federal agency having jurisdiction or, in the absence of such an authorized list in any particular case, shall be subject to the approval of the City, which approval shall not be unreasonably withheld or delayed.

### Certificates and Reports.  The Design-Builder shall secure and deliver to the City promptly all required certificates of inspection, test reports, work logs, or approvals with respect to the Design-Build Work as and when required by the Contract Standards.

### City Tests, Observations and Inspections.  The City, its employees, agents, representatives and contractors (which may be selected in the City’s discretion), and all Governmental Bodies having lawful jurisdiction, may at any reasonable time and with reasonable notice conduct such on-site observations and inspections, and such civil, structural, mechanical, electrical or other tests as the City deems necessary or desirable to ascertain whether the Design-Build Work complies with the Contract Standards.  The Stage 2 Design-Build Costs paid in connection with any of such test, observation or inspection shall result in a Change Order unless such test, observation or inspection reveals a material failure of the Design-Build Work to comply with the Contract Documents or Applicable Law, in which event the costs and expenses of such observation, inspection or test shall be Unallowable Costs borne solely by the Design-Builder.  The Design-Builder shall be entitled to Uncontrollable Circumstance relief as and to the extent provided in Article 14 in the event that any requested test, observation or inspection causes a delay in the critical path of the Stage 2 Design-Build Work Schedule, but only if such testing, observation or inspection does not reveal any material failure or non-compliance as set forth herein.

### Notice of Covering Design-Build Work.  The Design-Builder shall give the City notice in the Monthly Progress Report of its upcoming schedule with respect to the covering and completion of any Design-Build Work, and shall update such notice, if necessary, within a reasonable time period (at least seven days) before such covering and completion.  The City shall give the Design-Builder reasonable notice (a minimum of 48 hours) of any intended inspection or testing of such Design-Build Work in progress prior to its covering or completion.  If the City provides such notice, the Design-Builder shall afford the City a reasonable opportunity to conduct such tests or inspections, which the City shall promptly complete.  At the City’s written request, the Design-Builder shall take apart or uncover for inspection or testing any previously-covered or completed Design-Build Work; provided, however, that the City’s right to make such requests shall be limited to circumstances where there is a reasonable basis for concern by the City as to whether the disputed Design-Build Work complies with the requirements of the Contract Documents.  The cost of uncovering, taking apart, or replacing such Design-Build Work along with the costs related to any delay in performing Design-Build Work caused by such actions, shall:

###### Be Unallowable Costs borne solely by the Design-Builder, if such Design-Build Work was covered prior to any observation or test required by the Contract Standards or for which the City was not provided reasonable advance notice hereunder, or prior to the date on which the City was to conduct any observation or test as to which the City has provided notice of its intention to conduct in accordance with this subsection (F); and

###### In all other cases, as follows:

#### Be Unallowable Costs borne solely by the Design-Builder, if such observation or test reveals that the Design-Build Work does not comply with the Contract Documents; or

      - Be Stage 2 Design-Build Costs, if such observation or test reveals that the Design-Build Work complies with the Contract Documents, and shall result in a Change Order.

In the event such Design-Build Work does comply with the Contract Documents and the associated costs are determined to be Stage 2 Design-Build Costs pursuant to this subsection, the delay caused by such observation or test shall be treated as having been caused by an Uncontrollable Circumstance and any costs incurred with respect to such observation or test shall be costs for the account of the City in accordance with Article 14.

## CORRECTION OF WORK.

### Correction of Non-Conforming Design-Build Work.  Throughout the Stage 2 Design-Build Period, the Design-Builder shall complete, repair, replace, restore, re-perform, rebuild and correct promptly any Design-Build Work that does not conform with the Contract Standards.  The Design-Builder shall be solely responsible at its cost for the removal of defective work.  In the event of a failure of the Design-Builder to correct any such nonconforming Design-Build Work in a timely manner, the City shall have the right, but not the obligation, to correct or provide for the correction of such nonconforming Design-Build Work and the costs and expenses reasonably incurred by the City in connection therewith shall be reimbursed by the Design-Builder to the City.  The City shall provide the Design-Builder with seven days’ advance written notice prior to exercising its right to correct or provide for the correction of any nonconforming Design-Build Work pursuant to this subsection (A).

### Election to Accept Non-Conforming Design-Build Work.  The City may elect by Change Order, at the Design-Builder’s request, to accept non-conforming Design-Build Work and charge the Design-Builder (through a Base Guaranteed Maximum Price Adjustment) for the amount agreed upon by the parties as reflecting the reduction in value of the Design-Build Work.  The City shall have no obligation to accept non-conforming Design-Build Work pursuant to this subsection (B).

### Relation to Other Obligations.  The obligations specified in this Section establish only the Design-Builder’s specific obligation to correct the Design-Build Work and shall not be construed to establish any limitation with respect to any other obligations or liabilities of the Design-Builder under this Design-Build Contract.  This Section is intended to supplement (and not to limit) the Design-Builder’s obligations under any other provisions of this Design-Build Contract or Applicable Law.

## PROPERTY DAMAGE DURING THE DESIGN-BUILD PERIOD.

### Damage Prevention.  In performing the Design-Build Work, the Design-Builder shall use care and diligence, and shall take all appropriate precautions in accordance with the Contract Standards to protect the Design-Build Work from loss, damage or destruction.

### Restoration.  During the Stage 2 Design-Build Period, in case of damage to the Design-Build Work, and regardless of the extent thereof or the estimated cost of restoration, and whether or not any insurance proceeds are sufficient or available for the purpose, the Design-Builder shall promptly undertake and complete restoration of the damage to the Design-Build Work to the character and condition existing immediately prior to the damage and in accordance with the procedures set forth herein, as applicable, regarding Uncontrollable Circumstances, Change Orders and Work Change Directives.  The City shall have the right to monitor, review and inspect the performance of any repair, replacement and restoration work by the Design-Builder in accordance with this Article.  If the Design-Builder fails to undertake restoration of the damage, or having so commenced fails to complete restoration in accordance with the Contract Documents, the City may (but shall not be obligated to) undertake or complete restoration at the Design-Builder’s expense to the extent applicable in accordance with this Section.  The City shall provide the Design-Builder with seven days’ advance written notice prior to exercising its right to undertake or complete restoration pursuant to this subsection (B).  Notwithstanding any of the foregoing, to the extent that Uncontrollable Circumstances cause damage to the Design-Build Work and insurance proceeds or other third-party payments are not sufficiently available to pay for restoration work pursuant to this subsection (B), the Design-Builder’s obligation to perform such restoration work shall be subject to the receipt of reasonable assurances from the City of its ability to pay the costs for which it is financially responsible under this Section.

### Notice and Reports.  In addition to the notification requirements set forth in (E), the Design-Builder shall notify the City and the insurers under any applicable policy of Required Insurance of any incident causing property damage to the Design-Build Work in excess of $5,000 or of any OSHA recordable injury accident on the Project Sites related to the Design-Build Work, as promptly as reasonably possible after the Design-Builder learns of any such damage or accident.  As soon as practicable after learning of any such incident or accident (but in no event later than 72 hours), the Design-Builder shall submit a written report to the City.  Such report shall be updated on a weekly basis and upon culmination of all tests, analysis and reviews, a final report incorporating all of the tests, analysis and reviews and the findings thereof shall be submitted to the City.  The Design-Builder shall also submit to the City copies of all accident and other reports filed with (or given to the Design-Builder by) any insurance company, adjuster, or Governmental Body or otherwise prepared or filed in connection with the damage or accident.

### Insurance and Other Third-Party Payments.  To the extent that any repair, replacement or restoration costs incurred pursuant to this Section can be recovered from any insurer or from another third party, each party shall assist each other in exercising such rights as it may have to effectuate such recovery.  Each party shall provide the other with copies of all relevant documentation, and shall cooperate with and assist the other party upon request by participating in conferences, negotiations and litigation regarding insurance claims; provided, however, that neither party shall be obligated pursuant to this subsection (D) to provide the other party with documents subject to the attorney-client privilege under the laws of the State.

### Payment for Restoration Work and Uninsured Costs.  All insurance proceeds and recoveries from third parties resulting from damage to or the loss or destruction of the Design-Build Work, including proceeds from all policies of Required Insurance, shall be for the benefit of the City.  The City shall pay the Design-Builder for restoration work required pursuant to this Section with such proceeds and recoveries and, as necessary, other funds of the City obtained pursuant to the Change Order provisions of this Article and the payment provisions of Article 9, as applicable.  All costs not covered by insurance proceeds or third-party payments shall constitute Stage 2 Design-Build Costs; provided, however, that such costs shall be Unallowable Costs borne solely by the Design-Builder to the extent the loss, damage or destruction was caused by Design-Builder Fault or to the extent insurance proceeds are not available due to a failure of the Design-Builder to obtain or maintain any applicable policy of Required Insurance.

### Repair of the City and Private Property.  The Design-Builder shall promptly at its sole cost and expense repair or replace all the City Property and all private property damaged by the Design-Builder or any officer, director, employee, representative, agent or Subcontractor of the Design-Builder in connection with the performance of, or the failure to perform, the Design-Build Work.  The repair and replacement work shall restore the damaged property, to the maximum extent reasonably practicable, to its character and condition existing immediately prior to the damage.  Nothing in this subsection (F) is intended to waive any rights of recovery under applicable policies of insurance.

## PUNCH LIST ITEMS.

### Punch List Requirements.  The Design-Builder shall submit a proposed Punch List to the City and the Owner Representative when the Design-Builder believes that the Design-Build Work has achieved the requirements for Substantial Completion in compliance with the Contract Documents.  The “Punch List” shall be a statement of repairs, corrections and adjustments to the Design-Build Work, and incomplete aspects of the Design-Build Work, which in the Design-Builder’s opinion:

###### The Design-Builder can complete before the date specified in subsection (B) of this Section, and with minimal interference to the occupancy, use and lawful operation of the Project; and

###### Would represent, to perform or complete, a total cost of not more than 0.3% of the portion of the Guaranteed Maximum Price applicable to the construction of the Project (unless the City determines, in its discretion, that a higher percentage is acceptable, as evidenced by the written approval of the City Contract Representative).

The City shall have the right to approve the Punch List in its discretion.

### Completion of Punch List Items.  The Design-Builder shall complete all items on the Punch List within 90 days following the Substantial Completion Date.  All work associated with the Punch List items shall constitute Design-Build Work hereunder and shall be performed by the Design-Builder in accordance with the Contract Standards.

# MANAGEMENT, LABOR AND SUBCONTRACTORS

## MANAGEMENT.

### Project Manager.  The Design-Builder has designated an employee of the Design-Builder, as the “Project Manager” to oversee all Stage 1 Preliminary Service Work and all Stage 2 Design-Build Work.  When the Design-Builder or any Subcontractor is performing Construction Work, the Construction Superintendent (or designee reasonably acceptable to the City) shall be present at the Project Sites.  The Project Manager shall, among other things:

###### Be familiar with the Contract Obligations and all requirements of the Contract Documents;

###### Coordinate the Contract Obligations and give the Contract Obligations regular and careful attention and supervision;

###### Maintain a daily status log of the Design-Build Work when being performed; and

###### Attend all Project meetings (including meetings concerning scope, review, pre-bid, pre-construction, and construction matters) with the City and its representatives.

The Design-Builder represents and warrants that the Project Manager shall be vested with the authority to act on behalf of the Design-Builder in connection with the performance of the Contract Obligations and to bind the Design-Builder with respect to any certification required under this Design-Build Contract to be made by the Project Manager.  If the Design-Builder is comprised of two or more persons functioning as a joint venture, the Design-Builder shall have the authority to represent and act for the joint venture.  The Design-Builder may change the person assigned as the Project Manager solely in accordance with the provisions of subsection (B) of this Section.

### City Rights With Respect to Key Personnel.  The Design-Builder acknowledges that the identity of the Project Manager and the other key management and supervisory personnel proposed by the Design-Builder and its Subcontractors in its Proposal was a material factor in the selection of the Design-Builder to perform this Design-Build Contract.  Such personnel, their affiliations and their anticipated roles in the performance of the Contract Obligations are set forth in Appendix 11.  The Design-Builder shall utilize such personnel to perform such services unless such personnel are unavailable for good cause shown.  “Good cause shown” shall not include performing services on other projects for the Design-Builder or any of its Affiliates, but shall include termination for cause, employee death, disability, retirement, resignation or any job protected leave available under Applicable Law.  In the event of any such permissible unavailability, the Design-Builder shall utilize replacement key management and supervisory personnel of equivalent skill, experience and reputation.  Any on-site personnel change shall be proposed to the City with reasonable advance notice for its review and approval, which shall not be unreasonably withheld or delayed.  The Design-Builder shall remove or replace, or have removed or replaced, any personnel performing the Contract Obligations if the City, acting reasonably, determines that an unworkable relationship has developed between the City and the individual.

## LABOR.

### Personnel Performance.  The Design-Builder shall enforce discipline and good order at all times among the Design-Builder’s employees and all Subcontractors.  All persons engaged by the Design-Builder for performance of the Contract Obligations shall have requisite skills for the tasks assigned.  The Design-Builder shall employ or engage and compensate engineers and other consultants to perform all engineering and other services required for the Contract Obligations.  The Design-Builder shall ensure that all persons performing Contract Obligations, including all Subcontractors, comply with all registration, licensing and certification requirements imposed by any Governmental Body or otherwise under Applicable Law, including Design-Builder and Subcontractor employees.

### Training of Design-Builder and Subcontractor Employees.  The Design-Builder shall provide training for all individuals employed by the Design-Builder or Subcontractors as a prerequisite to their entry to the Project Sites. The Design-Builder’s training program for such employees shall include orientation training, safety and awareness training, and any other training deemed necessary.  In addition, the training program shall, to the extent applicable for each employee, provide training for the start-up, Commissioning and Substantial Completion Test activities, and transition management and administration of the Project.

### Labor Relations.  The Design-Builder shall furnish labor that can work in harmony with all other elements of labor employed for the performance of the Design-Build Work.  The Design-Builder shall have exclusive responsibility for disputes or jurisdictional issues among unions or trade organizations representing employees of the Design-Builder or its Subcontractors, whether pertaining to organization of the Design-Build Work, arrangement or subdivision of the Baseline Design Documents, employee hiring, or any other matters.  The City shall have no responsibility whatsoever for any such disputes or issues and the Design-Builder shall indemnify, defend and hold harmless the City and the City Indemnitees in accordance with and to the extent provided in Section 15.1 from and against all Loss-and-Expense resulting from any such labor dispute.

### Notice of Labor Disputes.  If the Design-Builder has knowledge of an actual or potential labor dispute that may affect any of the Contract Obligations, the Design-Builder shall promptly:

###### Give notice thereof to the City, including all relevant information related to the dispute of which the Design-Builder has knowledge; and

###### Take all reasonable steps to ensure that such labor dispute does not affect the performance of any of the Contract Obligations including by applying for relief to appropriate forums or courts.

### Prevailing Wages.  The Design-Builder shall pay or cause to be paid by its Subcontractors prevailing wages for all labor engaged in connection with the Design-Build Work, in accordance with the rate determined by the Industrial Statistician of the Washington State Department of Labor and Industries pursuant to Chapter 34.12 RCW.  The Design-Builder shall, and shall cause each Subcontractor to, keep a record showing:

###### The name and occupation of each worker employed by the Design-Builder or Subcontractor in the Construction work; and

###### The actual per diem wages paid to each worker in the form of certified payrolls. The record shall be available at all reasonable hours for inspection by the City.

[Additionally, the Design-Builder shall track and report to the City as to compliance with the requirements of this subsection (E).  The City will address complaints concerning alleged violations and withhold amounts due under this Design-Build Contract.

### Labor Compliance.  The Design-Builder and all Subcontractors must submit certified payrolls and labor compliance documentation starting with the first Certified Payroll Report (CPR) and every CPR thereafter.

### Non-Discrimination.  The Design-Builder and its Subcontractors (1) understand and agree to comply with the “Non-Discrimination Policy” of the City contained in Article 17 hereof, and (2) agree not to engage in employment practices which have the effect of discriminating against any employee or applicant for employment and will take affirmative steps to ensure that applicants are employed and employees are treated during employment without regard to their race, color, religion, national origin, sex, sexual orientation, gender identity, veteran status, age, disability, or political belief or affiliation, unless exempted by state or federal law.  The Design-Builder shall indemnify, defend and hold harmless the City and the City Indemnitees from and against all Loss-and-Expense which any of them may incur arising from any claim of harassment, including sexual harassment, arising from the conduct of the Design-Builder or any Design-Builder Person.  In the event of a harassment complaint against the Design-Builder or any Design-Builder Person, the Design-Builder shall take immediate and appropriate action in response to such complaint, including termination or appropriate discipline of any officer, employee, agent or Subcontractor.  This is a continuing obligation that survives the termination of this Design-Build Contract.

### Drug-Free Workplace.  During the performance of this Design-Build Contract, the Design-Builder agrees to (a) provide a drug-free workplace for the Design-Builder’s employees; (b) post in conspicuous places, available to employees and applicants for employment, a statement notifying employees that the unlawful manufacture, sale, distribution, dispensation, possession, or use of a controlled substance or marijuana is prohibited in the Design-Builder’s workplace and specifying the actions that will be taken against employees for violations of such prohibition; (c) state in all solicitations or advertisements for employees placed by or on behalf of the Design-Builder that the Design-Builder maintains a drug-free workplace; and (d) include the provisions of the foregoing clauses in every Subcontract of over $10,000, so that the provisions will be binding upon each Subcontractor.  For the purposes of this Section, “drug-free workplace” means a site for the performance of Contract Obligations performed in conjunction with this Design-Build Contract.  The Design-Builder’s employees, in accordance with this Section, are prohibited from engaging in the unlawful manufacture, sale, distribution, dispensation, possession or use of any controlled substance or marijuana during the performance of this Design-Build Contract.  The Design-Builder shall adhere to and certify that its employees comply with this substance abuse program.

## SUBCONTRACTING GENERALLY.

### Right to Subcontract.  The Design-Builder may carry out the Design-Build Work and other Contract Obligations by contracting such obligations to one or more Subcontractors in accordance with the requirements of this Article.  The Design-Builder shall retain full responsibility to the City under this Design-Build Contract for all matters related to the Contract Obligations, notwithstanding the execution of, or the terms and conditions contained in, any Subcontract.  Subcontracts entered into by the Design-Builder for the performance of the Contract Obligations shall neither supersede nor abrogate any of the terms or provisions of this Design-Build Contract.

### Approval Required.  The Subcontractors identified in Appendix 11 are approved by the City for the performance of the specific Contract Obligations identified therein, subject to the rights of the City under this Section.  The Design-Builder shall retain such Subcontractors to perform such services, unless otherwise agreed to in writing by the City.  All other Subcontractors shall be subject to the approval of the City, which approval shall not be unreasonably withheld.  The Design-Builder shall replace any Subcontractor at the request of the City, after notice and a reasonable opportunity for corrective action, in the event that the City determines, acting reasonably, that an unworkable relationship has developed between the City or the Design-Builder and the Subcontractor.  The City’s approval of any Subcontractor performing Contract Obligations shall be subject to the terms and conditions of Section 7.4.

### Performance Failure.  The Design-Builder shall retain full responsibility to the City under this Design-Build Contract for all matters related to the Contract Obligations.  No failure of any Subcontractor used by the Design-Builder in connection with the provision of the Contract Obligations shall constitute an Uncontrollable Circumstance or otherwise relieve the Design-Builder from its obligations hereunder to perform the Contract Obligations, except as provided in items (h) and (j) of the list of “Inclusions” in the definition of Uncontrollable Circumstances.  The Design-Builder shall be responsible for settling and resolving with all Subcontractors all claims including those:

###### Arising out of delay, disruption, interference, hindrance, schedule extension caused by the Design-Builder;

###### Arising from the actions or inactions of the Design-Builder or a Subcontractor; or

###### Inflicted on the Design-Builder or a Subcontractor by the actions of another Subcontractor.

The Design-Builder shall provide to the City, promptly following the receipt thereof, copies of any notice of default, breach or non-compliance received under or in connection with any Subcontract that may have a material and adverse effect on performance by the Design-Builder of its obligations under the Contract Documents.

### Restricted Persons.  In providing the Contract Obligations, the Design-Builder shall not contract with, or allow any of its Subcontractors to contract with, any person that, in the reasonable opinion of the City, is a Restricted Person.

### Subcontractor Licensing.  All trade Subcontractors shall possess a valid contractor license as required by Applicable Law for the classification required for the work to be performed by the Subcontractor at the time of the Subcontract and throughout the duration of the Subcontract.  (A) shall be applicable to all Subcontractors performing Design Professional Services.

### Availability of Subcontractors and Key Personnel.  At the request of the City, the Design-Builder shall make the key representatives of Subcontractors available for meetings between the City and the Design-Builder concerning design review, construction progress, Substantial Completion or any other matter relating to the performance of the Design-Build Work.  The Design-Builder shall provide the City with periodic human resource allocation summary reports concerning the personnel of the Material Subcontractors, which reports shall include anticipated personnel allocations for all ongoing and planned projects and shall demonstrate human resource sufficiency.

### Assignability.  All Subcontracts entered into by the Design-Builder with respect to the Project shall be assignable to the City, solely at the City’s election and without cost or penalty, upon any early termination of this Design-Build Contract, including convenience termination under Section 12.6.

### Prompt Payment.  The Design-Builder shall pay its Subcontractors in accordance with Applicable Law.  Any reduction of retention by the City to the Design-Builder under Article 9 shall result in a corresponding reduction to Subcontractors who have performed satisfactory work.  The Design-Builder shall pay Subcontractors the reduced retention within 10 days after the payment of the reduction of the retention to the Design-Builder.  No contract between the Design-Builder and its Subcontractors may materially alter the rights of any Subcontractor to receive prompt payment and retention reduction as provided herein.  If the Design-Builder fails to make payments in accordance with this Section, the City may take any one or more of the following actions and the Design-Builder agrees that the City may take such actions:

###### To declare the Design-Builder in breach of this Design-Build Contract;

###### Withhold future payments, including retention, until proper payment has been made to Subcontractors in accordance with this Section; or

###### Terminate this Design-Build Contract for an Event of Default by the Design-Builder under (B).

The Design-Builder shall include prompt payment provisions consistent with this Section and the requirements of Applicable Law in every Subcontract, including procurement of materials and leases of equipment entered into in connection with this Design-Build Contract.  Nothing contained in this Section or otherwise in this Design-Build Contract shall provide a basis for any Subcontractor claim against the City.

### Subcontractor Claims.  The Design-Builder shall pay or cause to be paid to all Subcontractors all amounts due in accordance with their respective Subcontracts and the requirements of this Article. The Design-Builder acknowledges that its indemnity obligations under Article 15 shall extend to all claims for payment or damages by any Subcontractor who furnishes or claims to have furnished any labor, services, materials or equipment in connection with the Design-Build Work.  No Subcontractor shall have any right or claim against the City for labor, services, materials or equipment furnished for the Contract Obligations.

### Design-Builder Employee Claims.  The Design-Builder specifically assumes potential liability for actions brought by the Design-Builder’s own employees against the City and, solely for the purpose of this indemnification and defense, the Design-Builder specifically waives any immunity under the state industrial insurance law, Title 51 RCW. The Design-Builder recognizes that this waiver was the subject of mutual negotiation.

## SELF-PERFORMANCE AND SUBCONTRACTOR SELECTION.

### Self-Performed Construction Work Generally.  Construction work on the Project shall not be performed by the Design-Builder, or its Affiliates, except with the approval of the City given in its discretion pursuant to subsection (G) of this Section.  The parties agree that, during the performance of the Stage 1 Preliminary Services, specific aspects of the Construction may be proposed for self-performance by the Design-Builder, any Affiliate of the Design-Builder or by an Approved Subcontractor.  The City agrees to allow for such self-performance if the Design-Builder demonstrates to the City’s satisfaction that providing for such self-performance is in the best interest of the Project and that the pricing therefor will be fair, reasonable and consistent with industry standards for similar services.  The City, in its discretion, may require that any such demonstration be supported by an independent cost estimate.

### Subcontractor Selection Generally.  Subcontractors shall be selected on a competitive basis, unless the City approves otherwise in accordance with subsection (G) of this Section.

### Subcontracting Plan.  A proposed final Subcontracting Plan shall be prepared during performance of the Stage 1 Preliminary Services and proposed by the Design-Builder as part of the GMP Submittal, and negotiated and agreed upon by the parties as part of the GMP Amendment.

### Division of Work.  The Design-Builder shall coordinate and develop with the City Contract Representative bid packages and work scope descriptions for each separate bid category that represents the entirety of the scope of the Design-Build Work for each phase and stage of the Project.  The Design-Builder shall be responsible for determining the Baseline Design Documents that are applicable to each Subcontractor performing Design-Build Work, including all trade Subcontractors and Suppliers.  The Design-Builder shall be responsible for the assembly, reproduction and distribution of all documents defining the scope of work for each Subcontractor.

### Pre-Bid Conferences.  The Design-Builder shall schedule and conduct pre-bid or pre-proposal conferences with trade Subcontractors and Suppliers for the purpose of generating interest in the Project among potential Subcontractors.  The Design-Builder shall coordinate such pre-bid conferences with the City Contract Representative and shall record and preserve conference minutes.

### Competitive Procedures for Construction Work.  Except as may otherwise be approved in writing by the City Contract Representative in accordance with subsection (G) of this Section, the Design-Builder shall enter into fixed-price Subcontracts for the performance of all Construction work and, in connection therewith, shall utilize a competitive bidding or competitive sealed proposal process approved by the City.  In connection with any such procurement, the Design-Builder shall, in accordance with the Contract Standards:

###### Develop procurement procedures in consultation with the City Contract Representative and prepare all necessary procurement documents;

###### Publicly advertise and receive bids or proposals;

###### Open and review all bids or proposals in a manner that does not disclose the contents of the bids or proposals to persons not employed by the Design-Builder, the City or the Owner Representative;

###### Evaluate the bids or proposals in accordance with the selection criteria established in the procurement documents; and

###### Recommend a bid or proposal for approval by the City Contract Representative in accordance with such evaluation.

#### Any Subcontract awarded for the performance of Construction work shall be subject to the City’s approval and shall have terms and conditions and a risk allocation substantially identical to that established by this Design-Build Contract.  The City Contract Representative’s approval of a bid or proposal recommended by the Design-Builder in accordance with this Section shall not be unreasonably withheld.  Without limiting any of the foregoing, the Design-Builder acknowledges and agrees that the City and the Owner Representative shall have the right to: (i) review and comment on all procurement documents; (ii) attend any bid or proposal openings; (iii) attend any meetings with prospective Subcontractors or Suppliers, including scope review meetings; (iv) review all bids, proposals, and other information developed or otherwise resulting from any competitive procurement, including the Design-Builder’s tabulation, scoring or evaluation materials; and (v) otherwise participate in the negotiation and contract award process. Upon contract award, the Design-Builder shall provide the City Contract Representative with a description of the competitive process undertaken in connection with such contract award, together with copies of all material documents used in connection therewith and agreements resulting therefrom.

### Alternative Procedures for Construction Work.  The Design-Builder may propose to the City Contract Representative alternative procedures for the procurement of Construction work, including performance of Construction work by labor forces of the Design-Builder, any Affiliate of the Design-Builder or by an Approved Subcontractor as indicated in subsection (A) of this Section.  The City Contract Representative’s approval of any such alternative procedure shall be in the City Contract Representative’s discretion.  The Design-Builder recognizes that, if the Designer-Builder wishes to perform Construction work with its own labor forces or the labor forces of an Affiliate or an Approved Subcontractor, the City Contract Representative may, but is not obligated to, require that the Design-Builder, Affiliate or Approved Subcontractor submit a bid or proposal for the work on a competitive basis, as contemplated by subsection (F) of this Section.  If the Design-Builder or any Affiliate of the Design-Builder intends to submit a competitive bid or proposal for Construction work, the Design-Builder shall notify the City Contract Representative in writing prior to the issuance of procurement documents for the work, and the City Contract Representative shall have the right to require the submittal of all bids or proposals directly to the City (and not to the Design-Builder) for review, evaluation and selection.  Any decision by the City Contract Representative to approve the performance of Construction work without obtaining competitive bids or proposals shall be subject to an “open book” process to provide the City Contract Representative with sufficient information to determine whether the proposed pricing of the work is fair, reasonable and consistent with industry standards for similar services.

### Procurement of Subcontractors Prior to the GMP Amendment Date.  The Design-Builder, during the Stage 1 Preliminary Services Period, in the development of the proposed Base Guaranteed Maximum Price to be submitted to the City in the GMP Submittal (1) may conduct discussions with and obtain indicative pricing information from potential Construction Subcontractors, and (2) may initiate, subject to the approval of the City given in its discretion, the formal procurement process for selecting Construction Subcontractors.  Any such formal procurement process shall be conducted in accordance with the requirements of this Section.  No Subcontract resulting from such procurement process shall be executed prior to the GMP Amendment Date without the City’s consent given in its discretion.

### Security for Construction Subcontractor Performance.  Security for the performance of Subcontractors under Construction Subcontracts shall be provided in a manner agreed to by the parties, and the costs therefor shall constitute Stage 2 Design-Build Costs.

## TERMINATION, AMENDMENT, ASSIGNMENT AND REPLACEMENT OF MATERIAL SUBCONTRACTS.

### Termination, Amendment and Assignment.  Unless the Design-Builder has, at its earliest practicable opportunity, submitted to the City notice of the proposed course of action (and any relevant documentation) and the City has consented in writing to such course of action, such consent not to be unreasonably withheld or delayed, the Design-Builder shall not:

###### Terminate, or agree to, or permit the termination of, any Material Subcontract;

###### Make, or agree to, or permit the making of (a) any material amendment of any Material Subcontract; or (b) any departure by any party from any material provision of any Material Subcontract; or

###### Permit any Material Subcontract party to assign or transfer to any person any of such Material Subcontract party’s rights or obligations under a Material Subcontract.

### Replacement.  If any Subcontract at any time lapses, terminates, or otherwise ceases to be in full force and effect (whether by reason of expiration or otherwise), unless the goods, services or rights which were the subject matter of such Subcontract are no longer reasonably required for the Project, the Design-Builder will forthwith enter into, or cause to be entered into, a replacement contract or contracts upon the same or substantially similar terms as the contract so replaced (to the extent reasonably practicable).  If at any time any amendment is made to any Material Subcontract, or a replacement Material Subcontract (or any agreement which materially affects the interpretation or application of any Material Subcontract) is entered into, the Design-Builder shall deliver to the City a copy of each such amendment or agreement within 14 days of the date of its execution or creation, certified as a true copy by the Project Manager.

# SUBSTANTIAL COMPLETION AND FINAL COMPLETION

## SUBSTANTIAL COMPLETION DATE CONDITIONS.

The following conditions shall constitute the “Substantial Completion Date Conditions”, each of which must be satisfied in all material respects by the Design-Builder in order for the Substantial Completion Date to occur, and each of which must be and remain satisfied as of the Substantial Completion Date:

###### Physical Completion.  All pipelines, facilities, materials and equipment for the Project have been installed in accordance with the requirements of the Contract Documents and inspected (tv’d), (each joint isolated and air tested, Mandrel test for flexible pipes), tested in accordance with Appendix 4 and the Project has been cleaned out as necessary and required by the City and Applicable Law;

###### Project Equipment.  The Project pipes and other equipment are installed in a manner that does not void any Subcontractor or Supplier warranties and such Project pipes and equipment can be operated in a safe and prudent manner;

###### Certificates of Proper Installation.  The Design-Builder has delivered to the City certificates of proper installation for the Project;

###### Verification of Governmental Approval Compliance.  The Design-Builder shall provide documentation that all activities and conditions have been met to comply with all the Governmental Approvals and Non-Governmental Approvals;

###### No Encumbrances.  There are no Encumbrances registered or recorded on the Project Sites or any part of the Project other than Permitted Encumbrances;

###### Equipment Warranties and Manuals.  The Design-Builder shall be in possession of, and shall have delivered to the City, copies of the warranties of pipes and equipment constituting a part of the Project, together with copies of any related operating manuals supplied by the equipment supplier;

###### Punch List.  The Design-Builder and the City have agreed in writing upon the Punch List (or, if they are unable to agree, the City shall have prepared and issued the Punch List to the Design-Builder within 30 days of the Design-Builder having submitted its proposed Punch List to the City);

###### No Event of Default.  The Design-Builder shall have certified that there is no Event of Default by the Design-Builder existing under this Design-Build Contract, or event which with the giving of notice or the passage of time would constitute an Event of Default by the Design-Builder hereunder; and

###### Approvals.  All Governmental and Non-Governmental Approvals required under Applicable Law and this Design-Build Contract to be obtained by the Design-Builder which are necessary for the continued use of the Project shall be in full force and effect and certified copies of all such Governmental and Non-Governmental Approvals shall have been delivered to the City.

The Design-Builder shall notify the City in writing when all of the Substantial Completion Date Conditions have been achieved and provide evidence and/or certifications to such achievement, as applicable.

## CONCURRENCE OR DISAGREEMENT WITH SUBSTANTIAL COMPLETION DATE.

### Substantial Completion Date Concurrence.  The Substantial Completion Date shall be the day on which the Substantial Completion Date Conditions have been achieved, as determined in accordance with this Section.  If the Design-Builder certifies in writing pursuant to Section 8.1 that the Substantial Completion Date Conditions have been achieved, the City shall determine, within [30] days following its receipt of such report, whether it concurs in such certification.  If the City states in writing that it concurs with the Design-Builder’s certification, the Project shall be deemed to have achieved Substantial Completion and the Substantial Completion Date shall be deemed to have been established on the date of the Design-Builder’s original certification.

### Substantial Completion Date Disagreement.  If the City determines at any time during such [30]-day review period that it does not concur with the Design-Builder’s certification of Substantial Completion, the City shall immediately send written notice to the Design-Builder of the basis for its disagreement.  In the event of any such non-concurrence by the City, the parties shall meet to discuss such disagreement. Either party may elect to initiate dispute resolution procedures in accordance with Section 11.1 following such meeting if the parties are unable to resolve the disagreement.

## EFFECT OF UNEXCUSED DELAY; EXTENSION PERIOD.

### Schedule for Completing the Design-Build Work.  The Design-Builder shall achieve Substantial Completion by the Scheduled Substantial Completion Date, as such date may be extended in accordance with this Section.  In the event one or more delays in the Design-Build Work caused by an Uncontrollable Circumstance or a Change Order, occurring during the Stage 2 Design-Build Period, the Scheduled Substantial Completion Date shall be the date determined by adding to the Scheduled Substantial Completion Date the aggregate number of days of delay in the performance of the Design-Build Work by the Design-Builder caused by such occurrence.

### Unexcused Delay.  It is agreed that time is of the essence in the performance of the Design-Build Work.  If Substantial Completion has not occurred on or before the Scheduled Substantial Completion Date, the Design-Builder shall be entitled to complete the Substantial Completion Date Conditions in order to secure Substantial Completion of the Project, subject to the City’s right to terminate this Design-Build Contract in accordance with subsection (D) of this Section.  During the Extension Period, the Design-Builder shall pay delay liquidated damages, as and to the extent provided in subsection (C) of this Section.

### Delay Liquidated Damages.  Subject to relief in accordance with the terms and conditions of this Design-Build Contract in the event of Uncontrollable Circumstances, if the Substantial Completion Date occurs subsequent to the Scheduled Substantial Completion Date, the Design-Builder shall pay to the City, at the election of the City, either (1) delay liquidated damages in the amount of [$______] [Note: To be finalized on the GMP Amendment Date] per day for each day that the Substantial Completion Date falls after the Scheduled Substantial Completion Date, or (2) the City’s actual demonstrated damages resulting from such delay, up to the end of the Extension Period and thereafter until any termination of this Design-Build Contract for an Event of Default.

### Failure to Achieve Substantial Completion by End of Extension Period.  If, as of the last day of the Extension Period, the Design-Builder has not achieved Substantial Completion in accordance with this Article, an Event of Default by the Design-Builder shall be deemed to have occurred, notwithstanding any absence of notice, further cure opportunity or other procedural rights accorded the Design-Builder thereunder, and the City shall thereupon have the right to terminate this Design-Build Contract upon written notice to the Design-Builder.  Upon any such termination, the City shall have all of the rights provided in Article 12 upon a termination of this Design-Build Contract for cause.

## FINAL COMPLETION.

### Requirements.  The Design-Builder shall achieve Final Completion within 60 days following the Substantial Completion Date.  “Final Completion” shall be deemed to have occurred when all of the following conditions have been satisfied:

###### Design-Build Work Completed.  All Design-Build Work (including the Punch List items, and all clean up and removal of construction materials, demolition debris and temporary facilities and excluding Warranty Work) is complete and in all respects is in compliance with the Contract Documents;

###### Deliverable Material.  The Design-Builder shall have delivered to the City all Deliverable Material required by the Contract Documents;

###### Final Record Drawings.  The Design-Builder shall have delivered to the City a final and complete reproducible set of “as-built” construction record drawings, as required by Appendix 7;

###### Final Completion Payment Requirements.  The Design-Builder shall have satisfied all requirements associated with payment for Final Completion, as set forth in Section 9.5; and

###### Certification.  The Design-Builder has submitted written certification that all of the foregoing conditions have been satisfied and the City has approved the Design-Builder’s certification, which approval shall be effective as of the date of the Design-Builder’s certification.

### Notice and Report of Final Completion.  When the Design-Builder believes that it has achieved Final Completion, it shall deliver to the City a written notice thereof (the “Notice of Final Completion”).  The Notice of Final Completion shall contain a report in a form acceptable to the City, and with sufficient detail to enable the City to determine the completion by the Design-Builder of all Design-Build Work to be performed under this Design-Build Contract, including completed Punch List items, and such other information that the City may require to determine whether Final Completion has been achieved.

### Achievement of Final Completion.  The City shall, in consultation with the Owner Representative, within 20 days following receipt of the Notice of Final Completion, inspect the Project, review the report submitted by the Design-Builder and either (1) deliver a written certificate to the Design-Builder stating that all conditions set forth in subsection (A) of this Section have been satisfied, or (2) notify the Design-Builder in writing that Final Completion has not been achieved, stating in detail the reasons therefor.  In the event that the City determines that Final Completion has not been achieved, the Design-Builder shall promptly take such action or perform such Design-Build Work as will achieve Final Completion and shall issue to the City another Notice of Final Completion pursuant to (B) of this Section.  Such procedure shall be repeated as necessary until Final Completion is achieved.  If the City, in its written certificate delivered in accordance with this subsection, states that it concurs that all conditions set forth in subsection (A) of this Section have been satisfied, the Project shall be deemed to have achieved Final Completion and Final Completion shall be deemed to have been established on the date of the Design-Builder’s most recent Notice of Final Completion.

# CONTRACT COMPENSATION

## COMPENSATION FOR STAGE 1 PRELIMINARY SERVICES.

### Compensation for Base Stage 1 Preliminary Services.  The City shall pay the Design-Builder the Stage 1 Preliminary Services Fee in the manner and subject to the terms and conditions set forth in this Design-Build Contract including Appendix 2.  The Design-Builder agrees that the Stage 1 Preliminary Services Fee, when earned, shall be the Design-Builder’s entire compensation and reimbursement for the performance of the Stage 1 Preliminary Services, inclusive of all costs, expenses and disbursements paid or incurred by the Design-Builder, as well as all overhead, administration, risk and profit.  The Stage 1 Preliminary Services Fee shall be subject to the maximum amount set forth in Appendix 2 which amount shall be subject to adjustment solely in accordance with Section 5.2.

### Compensation for Additional Stage 1 Preliminary Services.  The Design-Builder shall be compensated for any Additional Stage 1 Preliminary Services on a time and materials or lump sum basis, agreed to in writing through a Change Order or a Contract Amendment executed by the City and the Design-Builder.  Compensation for Additional Stage 1 Preliminary Services may consist of compensation on the basis of Design-Builder’s and Subcontractors’ billing rates set forth in Appendix 2 or as otherwise approved by the City.  The Change Order or Contract Amendment, as applicable, may set forth additional compensation and Payment Request requirements.

### Payment Requests and Payment.  The Design-Builder shall provide the City with a Payment Request for the performance of the Stage 1 Preliminary Services on a monthly basis in accordance with the specific requirements set forth in Appendix 2.  The Payment Request shall state the amount payable for the month and the total amount paid against the Stage 1 Preliminary Services Fee through the date of the Payment Request, along with a Monthly Progress Report regarding the performance of the Stage 1 Preliminary Services and such other information or documentation as the City may reasonably require.  The City shall make payment to the Design-Builder of all properly supported invoiced amounts within 30 days of receipt of the Payment Request, subject to the terms and conditions of this Design-Build Contract.  Payments of the Stage 1 Preliminary Services Fee shall not be subject to retainage holdback or, except as provided in subsection (E) of this Section, offset.

### Non-Compliant Stage 1 Preliminary Services.  Nothing contained in this Design-Build Contract shall require the City to pay for any unsatisfactory or duplicative Stage 1 Preliminary Services or for Stage 1 Preliminary Services that are not in compliance with the terms and conditions of this Design-Build Contract.  The City shall not be required to pay the Stage 1 Preliminary Services Fee to the Design-Builder at any time the Design-Builder is in breach or default under this Design-Build Contract.

### Billing Statement Disputes.  If the City disputes in good faith any Payment Request for Stage 1 Preliminary Services, the City shall pay all undisputed amounts when due but may withhold payment of the disputed amount, and shall provide the Design-Builder with a written objection indicating the amount being disputed and the reasons then known to the City for the dispute.  In the event that the Design-Builder disputes any amounts offset by the City, it shall provide the City with a written objection indicating the amount being disputed and the reasons then known to the Design-Builder.  If the Design-Builder is unable to reach agreement with the City as to the payment dispute, the Design-Builder may elect to initiate dispute resolution procedures in accordance with Section 11.1.  When any billing dispute is finally resolved, if payment by the City to the Design-Builder of amounts withheld is required, such payment shall be made within 30 days of the date of resolution of the dispute, together with interest thereon, from the date originally due, determined as provided in Section 9.9 of this Design-Build Contract.

## STAGE 2 DESIGN-BUILD PRICE.

The City shall pay the Design-Builder the Stage 2 Design-Build Price for properly performed and completed Design-Build Work during the Stage 2 Design-Build Period.  The Stage 2 Design-Build Price and the components thereof are defined in Appendix 8.  The City’s obligation to pay the Stage 2 Design-Build Price is subject to the Guaranteed Maximum Price and the terms and conditions of this Article and Appendix 8.  Except with respect to (1) payments of the Stage 1 Preliminary Services Fee in accordance with Section 9.1, and (2) Design-Build Work performed pursuant to an Early Work Package Amendment, the Design-Builder shall not be entitled to any compensation for costs or expenses incurred, or Design-Build Work performed, prior to the issuance by the City of the Notice to Proceed with Stage 2 Design-Build Work.  Any amount payable for Design-Build Work performed pursuant to an Early Work Package shall, upon the GMP Amendment Date, be part of the Stage 2 Design-Build Price and subject to the Guaranteed Maximum Price and all other terms and conditions of this Article and Appendix 8.

## STAGE 2 DESIGN-BUILD PRICE PAYMENT PROCEDURE.

### Payments.  The Design-Builder shall be paid the Stage 2 Design-Build Price in accordance with the final agreed upon cost model of the direct cost of the Stage 2 Design-Build Work and the terms and conditions of this Section.  The Design-Builder shall prepare and submit to the City for its approval preliminary and final drafts of the Anticipated Stage 2 Design-Build Cost Schedule in accordance with the Contract Standards.  After the final Anticipated Stage 2 Design-Build Cost Schedule is accepted by the City, it shall be used to assist in the tracking of actual Stage 2 Design-Build Costs against the anticipated costs and for keeping track of line item savings and the use of Contingency.

### Payment Request.  Subject to subsection (C) of this Section, the Design-Builder shall be entitled to submit Payment Requests to the City on a monthly basis and to receive from the City the payments, which (1) shall be made on a cost substantiated basis; (2) shall be subject to the Guaranteed Maximum Price limitations; and (3) shall be subject to the conditions to payment set forth in this Article.  Each Payment Request shall be in a form reasonably acceptable to the City and must be accompanied by a monthly requisition report, which shall include:

###### A reasonably detailed description of all Stage 2 Design-Build Work actually completed to date;

###### Revisions to the Stage 2 Design-Build Work Schedule, which shall reflect changes in the Design-Builder’s critical path schedule since the date of the last Payment Request and any line item savings or use of Contingency;

###### A certificate of the Project Manager and the Design-Builder Contract Representative certifying (a) the portion of the Stage 2 Design-Build Price payable to the Design-Builder for completed Design-Build Work; (b) that the Design-Builder is neither in default under this Design-Build Contract nor in breach of any material provision of this Design-Build Contract such that the breach would, with the giving of notice or passage of time, constitute an Event of Default; and (c) that all items applicable to the Stage 2 Design-Build Work entitling the Design-Builder to the requested payment have been completed in accordance therewith and with the Contract Documents;

###### Notice of any Encumbrances which have been filed together with evidence that the Design-Builder has discharged any such Encumbrances or made timely notification to the Payment Bond Surety regarding such Encumbrances; and

###### Any other documents or information relating to the Design-Build Work or this Design-Build Contract reasonably requested by the City or the Owner Representative or as may be required by Applicable Law, this Design-Build Contract or generally accepted accounting practices or principles, including payrolls, receipts, fully detailed invoices with check vouchers or other evidence of Stage 2 Design-Build Costs incurred which the City or the Owner Representative deems necessary to support the amount requested in the Payment Request.

The General Conditions Fee shall be shown as a separate line item on each Payment Request in accordance with Appendix 8.  The Design-Builder Fee shall also be shown as a separate line item on each Payment Request.  The Design-Builder shall identify the dollar amount of the total expected Design-Builder Fee in each Payment Request based on the total expected Stage 2 Design-Build Costs to which the Design-Builder Fee applies in accordance with Appendix 8.  The amount requested for the Design-Builder Fee in each Payment Request shall be in the same proportion to the total expected Design-Builder Fee as the amount requested for the applicable Stage 2 Design-Build Costs bears to the total expected Stage 2 Design-Build Costs to which the Design-Builder Fee applies, subject to the Guaranteed Maximum Price.

### City CPMS Project Management System.  The City’s projects are administered through its internet-based project management e-Builder system (hereinafter referred to as “CPMS”). The Design-Builder shall conduct all of its invoicing and billing to the City through CPMS, and the Design-Builder shall perform all contract and billing related functions using the CPMS system to submit and process all documentation to be generated, received or used in the performance of the Contract Obligations, including Payment Requests and processing of payments for the Contract Obligations. The City administers the CPMS software, and provides CPMS training to those Project team members who have reasonable need for access to it.  The City will make the software accessible via the internet to all such Design-Builder Project team members.  The Design-Builder shall designate a member of its key personnel to be the sole responsible party for the Design-Builder for receiving and implementing all software updates and to manage all Project documentation through the CPMS. The City will schedule training sessions with the Design-Builder’s designated personnel on the CPMS.]

### Review and Payment.  Prior to submitting a Payment Request for the Stage 2 Design-Build Price to the City, the Design-Builder shall submit a draft Payment Request to the City Contract Representative and the Owner Representative, including all information required pursuant to this Section.  The Owner Representative shall have no fewer than 10 days to review each draft Payment Request.  Within such 10-day period, the Owner Representative shall verify or dispute in writing (or by telecommunication promptly confirmed in writing) the Design-Builder’s certification that the Design-Builder has achieved the level of progress indicated and is entitled to payment.  If the Owner Representative determines that the Design-Build Work has progressed as indicated in the draft Payment Request, the Owner Representative shall notify the City and the Design-Builder, and the Design-Builder shall submit a final, certified Payment Request to the City, which may not contain any material change from the draft Payment Request reviewed by the Owner Representative, in accordance with subsection (C) of this Section.  The City shall pay the Design-Builder the requisitioned amount included in the final, certified Payment Request within 30 days following receipt, subject to subsection (E) of this Section and the City’s rights to withhold payments under Section 9.4.  Disputes regarding payments of the Stage 2 Design-Build Price shall be resolved in accordance with subsection (E) of this Section.  Any undisputed amounts of the Stage 2 Design-Build Price shall be paid within 30 days after receipt of the Design-Builder’s final, certified Payment Request.

### Payment Dispute Procedures.  If the City determines that the Stage 2 Design-Build Work required for any payment has not progressed as indicated by the Design-Builder in the draft Payment Request, or otherwise disputes any Payment Request, the City shall provide prompt written notice to the Design-Builder as to the City’s reasons, in reasonable detail, for such determination or the basis for such dispute. After receiving such determination notice, the Design-Builder may make the necessary corrections and resubmit the Payment Request, or the City may agree on a revised amount, in which case the Design-Builder shall promptly submit a final, certified Payment Request to the City as to any undisputed amount.  If the Design-Builder is unable to reach agreement with the City as to the progress of the Design-Build Work or the payment dispute, the Design-Builder may exercise its right to contest the City’s determination in accordance with the dispute resolution procedures set forth in Section 11.1.  Any proceedings undertaken to resolve a dispute arising under this subsection (E) shall immediately terminate if (1) the Design-Builder demonstrates to the City that the Stage 2 Design-Build Work has progressed as indicated in the Payment Request giving rise to the dispute and that the disputed Payment Request is correct, and (2) the City concurs with such demonstration.  The Design-Builder shall not be entitled to payment of the amount so requisitioned and disputed except upon resolution of the dispute in accordance with this subsection (E); provided, however, that the City shall pay all requisitioned amounts which are not in dispute in accordance with subsection (C) of this Section.  In the event that upon resolution of any such dispute, it is determined that the Design-Builder was properly entitled to the disputed amount as of a date earlier than the date on which payment is actually made, the Design-Builder shall be entitled to receive, promptly following such resolution, such disputed amount plus interest on such disputed amount as and to the extent provided under Section 9.9.

### Retainage.  Each construction drawdown payment will be subject to a 5% retainage holdback pursuant to TMC 10.10.010.  The City shall release to the Design-Builder the accumulated funds retained within 45 days of (i) receipt of certification from the Design-Builder and confirmation by the Owner Representative that Substantial Completion  has occurred pursuant to Section F-2 hereof; and (ii) the Design-Builder having provided to the City, notification from the Washington State Department of Revenue that the Design-Builder has paid all applicable taxes as of the date which is no more than 15 days prior to the date of the Design-Builder’s Certification in (i) above; provided, however, that to the extent items are contained on the Final Punch List, the City or the Owner Representative  shall reasonably estimate the cost to make each correction or to complete each such item and the City shall be entitled to withhold from payment of the retained funds an amount equal to two times the aggregate value of such items, in addition to the amount of unresolved or unbonded claims or liens by third parties in connection with the Stage 2 Design-Build Work and  earned interest on the retained funds.  Upon certification by the Owner Representative that Final Completion has occurred, the City shall release to the Design-Builder all remaining retained funds, including the amount equal to the interest actually received on the retainage holdback.

### Cost Control and Reporting.  The Design-Builder shall implement a Cost/Schedule Status Report (CSSR) program for Stage 2 Design-Build Work cost control, which system shall be disclosed to and reviewed and approved by the City and the Owner Representative prior to the GMP Amendment Date.  The Design-Builder shall develop cash flow reports and forecasts as reasonably requested or required by the City and the Owner Representative, including a good faith calendar quarterly estimate of payments of the Stage 2 Design-Build Price throughout the Stage 2 Design-Build Period, specifying the range of minimum and maximum monthly payments, which shall not exceed the Guaranteed Maximum Price.  The Design-Builder shall promptly (within seven days) after acquiring such information, identify and report to the City and the Owner Representative all variances between estimated costs and actual costs of the Stage 2 Design-Build Work, including any proposed corrective action to be taken by the Design-Builder.

### Certification of Amounts Due.  Whenever requested by the City or the Owner Representative, the Design-Builder shall submit a sworn statement certifying all amounts then due (or yet to become due) the Design-Builder for the Stage 2 Design-Build Work (or any portion thereof) and describing any payment or other dispute which may exist between the Design-Builder and any Subcontractor.

## PERMISSIBLE WITHHOLDINGS.

In addition to the amounts required to be retained pursuant to (F), the City may disapprove and withhold and retain all or any portion of any payment requested in any Payment Request for Stage 2 Design-Build Work in an amount equal to the sum of:

###### Any liquidated damages or reimbursement payments which are due and owing to the City hereunder;

###### Any indemnification amounts which are due and owing to the City hereunder and with respect to which a claim has been filed against a the City Indemnitee by a third party in accordance with Applicable Law;

###### Any amount determined pursuant to (E) and Appendix 10;

###### Any other deductions which are required by Applicable Law;

###### Any payments with respect to which documents to be delivered in connection therewith are not correct and complete;

###### Any payments to the extent that the Stage 2 Design-Build Work covered by such Payment Request (or any previous Payment Request) does not comply with this Design-Build Contract;

###### Damage to the work of a Separate Contractor to the extent caused by the Design-Builder or any Subcontractor;

###### Any payments with respect to which any person has filed a Lien resulting from the acts or omissions of the Design-Builder in performing the Design-Build Work and such Lien remains unreleased or unbonded;

###### All requisitioned payments if an Event of Default of the Design-Builder has occurred under Section 12.2; and

###### In the event the Design-Builder fails to pay any Taxes, assessments, penalties or fees imposed by any Governmental Body, then the Design-Builder authorizes the City to deduct and withhold or pay over to the appropriate Governmental Body those unpaid amounts upon demand by the Governmental Body.

In addition, the City may withhold payment for persistent and uncured Design-Builder noncompliance with the administrative provisions of this Design-Build Contract.  In the event of any permissible withholding under this Section, the City shall notify the Design-Builder in writing at least seven days prior to the date payment is otherwise due. The notice shall indicate the specific amounts the City intends to withhold, the reasons and contractual basis for the withholding, and the specific measures the Design-Builder must take to rectify the City’s concerns.  Any dispute associated with any such withholding shall be handled in accordance with (E).

## PAYMENT UPON FINAL COMPLETION.

### Final Completion Payment Request.  In connection with the achievement of Final Completion in accordance with Section 8.4, the Design-Builder shall prepare and submit to the City and the Owner Representative a Final Completion Payment Request.  The Final Completion Payment Request shall enclose:

###### A notarized affidavit in duplicate stating under oath that all Subcontractors, vendors, and other persons or firms who have furnished or performed labor or furnished materials for the Stage 2 Design-Build Work have been fully paid or satisfactorily secured; and if requested by the City, the Design-Builder shall submit further proof including waiver or release of lien or claims from any Subcontractors or Suppliers;

###### A certificate of the Surety for both the Performance Bond and the Payment Bond certifying that the Surety consents to payment for Final Completion and agrees that such payment shall not relieve the Surety of any of its obligations under the Performance Bond or the Payment Bond;

###### A general release executed by the Design-Builder waiving, upon receipt of payment for Final Completion, all claims arising out of or resulting from the Stage 2 Design-Build Work, except those claims made in writing to the City and remaining unsettled at the time of such payment, which claims shall be specifically listed in an attachment to the general release, identifying the claimant and the nature of the claim; and

###### Certificates of insurance confirming that required coverages will remain in effect consistent with the requirements of this Design-Build Contract.

### Final Completion Payment.  If based on the Owner Representative’s (1) observation of the Design-Build Work, (2) final inspection, and (3) review of the Final Completion Payment Request and other documents required by subsections (A) and (C) of this Section and Section 8.4, the Owner Representative is satisfied that the conditions for Final Completion have been achieved, the Owner Representative shall, within 15 days after receipt of the Final Completion Payment Request, furnish to the City and the Design-Builder the Owner Representative’s recommendation of payment for Final Completion.  If the Owner Representative is not satisfied, the Owner Representative shall return the Final Completion Payment Request to the Design-Builder, indicating in writing the reasons for not recommending payment, in which case the Design-Builder shall either (1) exercise its right to contest the Owner Representative’s determination in accordance with (E), or (2) make the necessary corrections and resubmit the Final Completion Payment Request.

###### City Concurrence.  If the City concurs with the Owner Representative’s recommendation of payment for Final Completion, the City shall, within 15 days, file a written notice of Final Completion and notify the Design-Builder of such concurrence.  As soon as reasonably practicable (but in no event later than 45 days after the City’s original receipt of the Design-Builder’s Final Completion Payment Request, subject to the City’s right to dispute payment in accordance with this Design-Build Contract and Applicable Law) after filing such notice, the City shall pay to the Design-Builder the balance of the Stage 2 Design-Build Price, subject to any withholdings and any other provisions governing final payment specified herein.

###### City Non-Concurrence.  If the City does not concur with the Owner Representative’s determination, the City shall return the Payment Request to the Design-Builder, indicating in writing its reasons for refusing payment for Final Completion.  The Design-Builder shall promptly make the necessary corrections and resubmit the Payment Request to the City and the Owner Representative.  The City’s written determination shall bind the Design-Builder, unless the Design-Builder delivers to the City written notice of a claim within 30 days after receipt of the City’s determination.

Payment for Final Completion does not constitute a waiver by the City of any rights relating to the Design-Builder’s obligations under this Design-Build Contract.  Except as specifically provided in subsection (A) of this Section with respect to exceptions taken in the Design-Builder’s general release, payment for Final Completion constitutes a waiver of all claims by the Design-Builder against the City, including all claims associated with Uncontrollable Circumstances, relating to the Stage 2 Design-Build Work, the payment of the Stage 2 Design-Build Costs or otherwise in connection with the Stage 2 Design-Build Period.

### Final Determination and Approval of Stage 2 Design-Build Price.  Notwithstanding any of the foregoing, the City shall have no obligation to make payment for Final Completion hereunder until a final accounting of the Stage 2 Design-Build Costs has been submitted by the Design-Builder and has been verified by the City and the Owner Representative.  Such accounting shall be provided by the Design-Builder in connection with the Final Completion Payment Request.  The aggregate total of payments to the Design-Builder with respect to the Stage 2 Design-Build Price (including amounts retained pursuant to (F)) shall not exceed the total of the actual Stage 2 Design-Build Costs, as verified by the City and the Owner Representative from the Design-Builder’s final accounting, plus the Design-Builder Fee and the General Conditions Fee, which together shall not exceed the Guaranteed Maximum Price.  If payments to the Design-Builder exceed that which is due and owing the Design-Builder pursuant to this Article, the Design-Builder shall promptly refund the excess to the City.  The Design-Builder acknowledges and agrees that the City shall have the right to withhold and retain amounts from payment for Final Completion in accordance with Section 9.4.

### Completion of Stage 2 Design-Build Work.  Notwithstanding payment for Final Completion pursuant to this Section, the Design-Builder acknowledges and agrees that the performance of the Stage 2 Design-Build Work is not complete until the expiration of the Warranty Period, and that the Design-Builder shall have the continuing obligation to perform Warranty Work pursuant to the terms and conditions of Article 10 until the expiration of the Warranty Period.  To the extent the Design-Builder is entitled to payment of any amount retained by the City pursuant to (F) upon expiration of the Warranty Period, the Design-Builder shall provide the City with a final Payment Request in a form reasonably acceptable to the City, and the City shall pay the amount due within 30 days following receipt of the final Payment Request.

## NO SUBSTANTIAL COMPLETION, WAIVER OR RELEASE.

Unless other provisions of this Design-Build Contract specifically provide to the contrary, none of the following, without limitation, shall be construed as (i) the City’s acceptance of any Design-Build Work which is defective, incomplete, or otherwise not in compliance with this Design-Build Contract, (ii) the City’s release of the Design-Builder from any obligation under this Design-Build Contract, (iii) the City’s extension of the Design-Builder’s time for performance, (iv) an estoppel against the City, or (v) the City’s acceptance of any claim by the Design-Builder:

###### The City’s payment to the Design-Builder or any other person with respect to performance of the Design-Build Work;

###### The review, consent, approval or acceptance, as applicable, of any submissions, permit applications, punch lists, other documents, certifications, or Design-Build Work of the Design-Builder or any Subcontractor by the City, the Owner Representative or any other person;

###### The review of (or failure to prohibit) any construction applications, means, methods, techniques, sequences, or procedures for the Design-Build Work by the City, the Owner Representative or any other person;

###### The entry at any time on the Project Site (including any area in which the Design-Build Work is being performed) by the City, the Owner Representative or any other person;

###### Any observation, inspection or testing of (or failure to observe, inspect or test) any Design-Build Work (whether finished or in progress) by the City, the Owner Representative or any other person;

###### The failure of the City, the Owner Representative or any other person to respond in writing to any notice or other communication of the Design-Builder; or

###### Any other exercise of rights or failure to exercise rights by the City hereunder.

## CHANGES IN STAGE 2 DESIGN-BUILD PRICE.

### Determination of Base Guaranteed Maximum Price Adjustment.  Without limiting any requirement of Article 14, any Base Guaranteed Maximum Price Adjustment included in a Change Order or Work Change Directive shall be determined as follows:

###### Where unit prices set forth in the Contract Documents are applicable to the Stage 2 Design-Build Work that is the subject of the Change Order or Work Change Directive, by application of such unit prices to the quantities of the items involved;

###### To the extent unit prices are not applicable, by a mutually agreed lump sum; and

###### To the extent unit prices are not applicable and the parties are unable to reach agreement on a lump-sum value, on the basis of the actual cost of performing the applicable Stage 2 Design-Build Work (subject to Cost Substantiation and excluding any cost attributable to Design-Builder Fault), plus the Design-Builder Fee and a Subcontractor mark-up determined in accordance with this Section.

### Design Professional Services.  Without limiting anything in subsection (C) of this Section and subject to any unit rates specified in the Contract Documents, for purposes of determining the amount payable for Design Professional Services included in any Change Order or Work Change Directive, the rates payable for Design-Builder personnel and personnel of Subcontractors providing Design Professional Services shall not exceed their then currently applicable rates for similar services on projects of similar size and scope to the Stage 2 Design-Build Work.  The Design-Builder shall use commercially reasonable efforts to use available Design-Builder personnel for additional work hereunder before using Subcontractors.

### Construction Subcontractor’s Maximum Mark-Up on Subcontracted Construction Work.  The price payable to all Subcontractors for work performed under Construction Subcontracts, including Construction Subcontractor overhead and mark-ups for risk and profit, shall be commercially reasonable.  A Change Order or Work Change Directive may provide for a mark-up payable to Construction Subcontractors for their Subcontractor risk, profit, administration, and all other overhead where Construction work that is the subject of the Change Order or Work Change Directive is performed through such Construction Subcontractors.  Any such Construction Subcontractor mark-up shall not exceed 15% of the costs incurred by such Construction Subcontractor in respect of labor, materials, equipment, supplies and any lower-tier Construction Subcontract.

## COST SUBSTANTIATION.

### Required Substantiation.  Without limiting anything in Appendix 8, the Design-Builder shall substantiate any costs for which it claims compensation hereunder, other than (1) the Design-Builder Fee and (2) the General Conditions Fee, each of which was proposed and negotiated on a percentage basis, and any other costs that are part of a negotiated lump sum price.  In incurring costs which are or may be subject to Cost Substantiation, the Design-Builder shall utilize competitive practices to the maximum reasonable extent (including, where practicable, obtaining three competing bids, quotes, proposals or estimates for costs expected to be in excess of $50,000), and shall enter into Subcontracts on commercially reasonable terms and prices in light of the work to be performed and the City’s potential obligation to pay for it.

### Cost Substantiation Certificate.  Any Payment Request for compensation relating to costs requiring Cost Substantiation shall be accompanied by a certificate stating that the Stage 2 Design-Build Costs or other costs being invoiced (1) are properly payable under this Design-Build Contract, and specifying the provisions of this Design-Build Contract under which compensation is due; and (2) are equal to amounts paid by the Design-Builder for Design-Build Work that has been properly performed.  The Cost Substantiation certificate shall describe the competitive or other process utilized by the Design-Builder to obtain the commercially reasonable price, and shall state that such services and materials are reasonably required pursuant to this Design-Build Contract.  Each Cost Substantiation certificate shall be accompanied by copies of all documentation reasonably necessary to demonstrate that the Stage 2 Design-Build Costs have been paid and are reasonable.  Such documentation shall be in a format and level of detail reasonably acceptable to the City.  To the extent reasonably necessary to confirm the payment of costs that are subject to Cost Substantiation, copies of timesheets, invoices, canceled checks, expense reports, receipts and other documents, as appropriate, shall be provided.

## INTEREST ON OVERDUE OBLIGATIONS.

Except as otherwise provided for herein, all amounts due hereunder, whether as damages, credits, revenue, charges or reimbursements, that are not paid when due shall bear interest at the rate of interest which is the Overdue Rate, on the amount outstanding from time to time, on the basis of a 365-day year, counting the actual number of days elapsed, and such interest accrued at any time shall, to the extent permitted by Applicable Law, be deemed added to the amount due as accrued.

## RETENTION AND AUDIT OF BOOKS AND RECORDS.

### Books and Records.  The Design-Builder shall, and shall cause its Subcontractors to, prepare and maintain proper, accurate and complete books and records regarding the Contract Obligations and all transactions related thereto, including all books of account, bills, vouchers, invoices, personnel rate sheets, cost estimates and bid computations and analyses, Subcontracts, time books, daily job diaries and reports, correspondence, and any other documents showing all acts and transactions in connection with or relating to or arising by reason of the Contract Obligations, any Subcontract or any operations or transactions in which the City has or may have a financial or other material interest hereunder (collectively, “Books and Records”).  The Design-Builder and its Subcontractors shall produce such Books and Records for inspection, audit and reproduction within 15 days of request by the City.  All financial records of the Design-Builder and its Subcontractors shall be maintained in accordance with generally accepted accounting principles and generally accepted auditing standards.  The Design-Builder and its Subcontractors shall maintain such Books and Records in accordance with subsection (E) of this Section.  The provisions of this Section shall survive termination of this Design-Build Contract.

### City Rights to Audit and Examine Payments.  All payments whatsoever by the City to the Design-Builder and all Contract Obligations shall be subject to audit at any time by the City.  The Design-Builder shall provide all evidence necessary to support Cost Substantiation as required under this Design-Build Contract, and allow the City access to the Design-Builder’s Books and Records.  The Design-Builder shall require all Subcontractors to comply with the provisions of this Section and include the requirements hereof in the written contract between the Design-Builder and the Subcontractor.  The Design-Builder shall also require all Subcontractors to include the requirements of this Section in any lower tier Subcontracts relating to the Project.

### Notice and Process.  Upon written notice by the City, the Design-Builder shall, and shall cause its Subcontractors to, promptly (in no event later than 15 days following the notice) make available at its office at all reasonable times the Books and Records for examination, audit, or reproduction.  Notice shall be in writing, delivered by hand or by certified mail, and shall provide not fewer than five days’ prior notice of the examination or audit.  The City may take possession of such Books and Records by reproducing such Books and Records for off-site review or audit.  When requested in the City’s written notice of examination or audit, the Design-Builder shall provide the City with copies of electronic and electronically stored Books and Records in a reasonably usable format that allows the City to access and analyze all such Books and Records.  For Books and Records that require proprietary software to access and analyze, the Design-Builder shall provide the City with two licenses with maintenance agreements authorizing the City to access and analyze all such Books and Records.  If the Design-Builder is unable to provide the licenses, the Design-Builder shall provide the City with access to the Design-Builder’s accounting system whereby the City can obtain applicable Books and Records, including job cost reports, material distribution reports, labor cost reports, labor productivity reports, standard time/overtime analysis reports, man-hour reports, and the like.

### Selection of Auditor or Examiner and Determination of Scope.  The City has discretion as to the selection of an examiner or auditor and the scope of the examination or audit.

### Preservation of Books and Records.  The Design-Builder shall preserve all of its Books and Records, and the City may examine, audit, or reproduce Books and Records, from the Contract Date until the later of four years after:

###### Final payment under this Design-Build Contract;

###### Final settlement of a termination for convenience under Section 12.6; or

###### The final resolution of any dispute.

The failure by the Design-Builder to make available to the City Books and Records in accordance with this Section or the Design-Builder’s refusal to cooperate with a notice of audit or examination shall be deemed a material breach of this Design-Build Contract and grounds for termination.

### Overpayment.  In the event an audit by the City determines that the Design-Builder cannot document a cost or expense for which payment has been made, or that the City has overpaid the Design-Builder, the Design-Builder, upon demand, shall refund to the City the amounts overpaid or undocumented.  If the overpayment exceeds 1% of the total amount that should have been properly paid by the City during the period audited, then the Design-Builder shall, in addition, reimburse the City for any and all fees and costs incurred in connection with the inspection or audit.  Payments to the Design-Builder, or approval by the City of any requisition for payment submitted by the Design-Builder, shall in no way affect the Design-Builder’s obligation hereunder or the right of the City to obtain a refund of any payment to the Design-Builder which is in excess of that to which it was lawfully entitled.

# PROJECT WARRANTIES

## PROJECT WARRANTIES.

### Project Warranties Defined.  The Design-Builder warrants to the City that the Design-Build Work, including all completed materials, equipment, systems and structures comprising the Project, shall: (i) be new, of recent manufacture and of good quality; (ii) conform to the requirements of the Contract Documents; (iii) be free of material faults or defects; and (iv) be suitable for its intended purposes, as established by the Contract Documents (the “Project Warranties”).  The Project Warranties are further subject to the following:

###### Inclusions.  The Project Warranties include remedy for damage or defect caused by Substantial Completion Test performed by the Design-Builder or performed by the City as directed by the Design-Builder.

###### Exclusions.  The Project Warranties exclude remedy for damage or defect caused by capital modifications not undertaken or executed by the Design-Builder under this Design-Build Contract.  In addition, except as provided in Item (1), above, the Project Warranties exclude remedy for damage or defect caused by improper or insufficient maintenance, improper operation, or normal wear and tear under normal usage.

### Term of the Project Warranties.  The Project Warranties set forth in this Article shall be in full force and effect for the period of time beginning on the Substantial Completion Date and, subject to (D), continuing for one year following the Substantial Completion Date (the “Warranty Period”).

## WARRANTY WORK.

### “Call-Back” Obligations.  If, at any time during the Warranty Period, the Project or any of the Design-Build Work is found to be malfunctioning, defective or otherwise not in accordance with the requirements of the Project Warranties, the Design-Builder shall correct the condition promptly after receipt of written notice from the City to do so.  The City shall provide such notice promptly after discovery of the condition.  The Design-Builder shall respond to critical or emergency service calls from the City within four hours and to non-critical or non-emergency calls within eight hours.  Such response shall require that a competent representative or representatives of the Design-Builder familiar with the Project, including its specific equipment, design and operational requirements, inspect the Project and, while on site, either correct the problem or initiate a course of action that will fully correct the problem within a reasonable period of time in accordance with Good Engineering and Construction Practice and the specific requirements of this subsection (A).  In critical or emergency situations, the correction shall be made the minimum amount of time required in accordance with Good Engineering and Construction Practice.

### Right of the City to Proceed with Corrective Action; Design-Builder Liability.  If the Design-Builder fails to commence and complete the steps set forth in subsection (A) of this Section within the required time frames, in addition to any other remedies provided under this Design-Build Contract, the Security Instruments or Applicable Law, the City may commence and complete the correction of such nonconforming Design-Build Work with its own forces or with third party contractors.  If the City does perform such corrective work, the Design-Builder shall be responsible for all costs reasonably incurred in performing such correction.  The City shall have the right to charge any cost reasonably incurred by the City in performing corrective action pursuant to this subsection (B) against the funds retained to secure the Warranty Work pursuant to (F); provided, however, that the amount retained by the City pursuant to (F) shall in no way be deemed to constitute a limit of liability to the Design-Builder for the performance of Warranty Work, and the Design-Builder shall be required to reimburse the City for all costs reasonably incurred in performing corrective action pursuant to this subsection (B) to the extent such costs exceed the retained funds.

### No Period of Limitation on Other Obligations.  Nothing contained in this Section shall be construed to establish a period of limitation with respect to other obligations that the Design-Builder has under this Design-Build Contract or under Applicable Law with respect to the Design-Build Work, including warranties and obligations with respect to latent defects.  The Warranty Period relates only to the specific obligations of the Design-Builder to respond to notices from the City under the Project Warranties, and has no relationship to the time within which the obligation of the Design-Builder to comply with this Design-Build Contract may be enforced, nor the time within which proceedings may be commenced to establish the Design-Builder’s liability with respect to its obligations under this Design-Build Contract.

### Extension of Warranties.  The “call-back” obligations set forth in this Section shall apply to all Design-Build Work re-done or corrected pursuant to this Design-Build Contract.  The “call-back” obligations for re-done or corrected elements of the Design-Build Work shall extend beyond the Warranty Period, if necessary, to provide a minimum one-year period following acceptance by the City of such re-done or corrected Design-Build Work; provided, however, that in no event shall such “call-back” obligations extend beyond one year following the expiration of the Warranty Period.

### Manufacturers’ Warranties.  During the Warranty Period, the Design-Builder (or the City) shall be permitted to enforce all warranties provided by manufacturers, suppliers and other third parties with respect to the Design-Build Work.  However, as provided in (A), no such warranty shall relieve the Design-Builder of any obligation with respect to the Project Warranties.

### Performance of Warranty Work.  The Design-Builder acknowledges that time is of the essence in the performance of all Warranty Work required under this Section in light of the Project’s essential public purpose.  Accordingly, all Warranty Work shall be performed in accordance with the Contract Standards and within the minimum amount of time required in accordance with Good Engineering and Construction Practice.  The Design-Builder shall perform or cause to be performed all Warranty Work performed under this Section in a manner that will minimize interference with the ongoing operations of the Project and the City Distribution System.  The Design-Builder shall provide a written plan for all proposed Warranty Work (unless expressly waived by the City).

### Responsibility for Costs.  The Design-Builder shall be fully responsible for the costs associated with all Warranty Work, and shall reimburse the City for its costs resulting from a breach of the Project Warranties, subject to the terms and conditions of this Design-Build Contract.

## PROJECT WARRANTIES NOT EXCLUSIVE.

The Design-Builder acknowledges and agrees that the Project Warranties are in addition to, and not in limitation of, any other warranties, rights and remedies available under this Design-Build Contract or Applicable Law, and shall not limit the Design-Builder’s liability or responsibility imposed by this Design-Build Contract or Applicable Law with respect to the Design-Build Work, including liability for design defects, latent construction defects, strict liability, negligence or fraud.  The provisions of this Section shall survive the termination of this Design-Build Contract.

## MANUFACTURERS’ WARRANTIES.

### Manufacturers’ Warranties Generally.  Without limiting any of the Project Warranties, the Design-Builder shall, for the protection of the City, obtain from all Subcontractors (including vendors, suppliers and other persons from which the Design-Builder procures structures, improvements, fixtures, machinery, equipment and materials) such warranties and guarantees as are normally provided with respect thereto and as may be specifically required by the Contract Standards, each of which is hereby assigned to the City to the full extent of the terms thereof.  No such warranty or guarantee shall relieve the Design-Builder of any obligation hereunder, and no failure of any warranted or guaranteed structures, improvements, fixtures, machinery, equipment or material shall be the cause for any increase in the Guaranteed Maximum Price or otherwise excuse the Design-Builder from the performance of any Design-Build Work or Warranty Work obligations, unless such failure is itself attributable to an Uncontrollable Circumstance.

### No Limitation on Third Party Warranties.  Nothing in this Design-Build Contract is intended to limit any third party warranty that provides the City with greater warranty rights than those provided under the Project Warranties, as set forth in this Design-Build Contract.

# DISPUTE RESOLUTION

## DISPUTE RESOLUTION PROCEDURES.

### Generally.  Except as provided in subsection (G) of this Section, each party shall follow the dispute resolution procedures set forth in this Section to attempt to resolve and settle disputes between themselves concerning the rights, obligations and liabilities of the parties.  The dispute resolution procedures set forth in this Section are intended to encourage a negotiated resolution of disputes in a prompt and efficient manner without resort to litigation, which should be a last resort.

### Informal Negotiations.  Representatives of the City and the Design-Builder with day-to-day involvement in the administration of this Design-Build Contract and the performance of the Contract Obligations shall initially and promptly enter into negotiations to attempt to address and resolve any disputes that may arise concerning this Design-Build Contract.  In connection with such negotiations, the party asserting the dispute shall provide the other with a written description of the nature of the dispute, along with reasonable supporting documentation.  The parties shall consider involving senior representatives and other upper management personnel of each party in the informal negotiation process, as well as other representatives of the parties not actively involved in the day-to-day activities associated with the dispute who might be able to take a broader look at the dispute in the context of the overall objectives of the Project and this Design-Build Contract.  At the City’s request, the Design-Builder shall involve senior representatives of any of its Subcontractors in such negotiations.  Upon the expenditure of reasonable efforts towards resolution of a dispute through such informal negotiations without reaching agreement, a party may declare that the informal negotiations have been exhausted and such party may request Non-Binding Mediation or request a the City Contract Representative’s Final Decision in accordance with this Section.

### City Contract Representative’s Final Decision.  If a dispute has not been resolved through direct, informal negotiations as provided in subsection (B) of this Section, then, upon the written request of the Design-Builder, the City Contract Representative or his or her designee (other than any personnel assigned to the Project) shall review the dispute and issue his or her determination of the dispute (the “City Contract Representative’s Final Decision”).  The City Contract Representative’s Final Decision shall be issued in writing within 30 days following the date of the request for review.  If the Design-Builder disagrees with the City Contract Representative’s Final Decision, or if the City Contract Representative fails to issue a the City Contract Representative’s Final Decision within such 30-day period, then the Design-Builder shall have the right to initiate Legal Proceedings concerning the dispute, subject to Section 11.2.  If the Design-Builder fails to initiate Legal Proceedings concerning the dispute within 60 days following the earlier to occur of the issuance of the City Contract Representative’s Final Decision or the expiration of the 30-day period specified above in this subsection (C), then the Design-Builder shall:

###### Be deemed to have accepted the City Contract Representative’s Final Decision;

###### Shall have waived its rights to any further relief for the matters covered by such the City Contract Representative’s Final Decision; and

###### Shall have waived its rights to initiate Legal Proceedings in accordance with Section 11.2 and in accordance with this Design-Build Contract for the matters in dispute between the parties.

### Rights to Request and Decline Non-Binding Mediation.  Subject to the requirements of subsection (B) of this Section, either party may request Non-Binding Mediation of any dispute arising under this Design-Build Contract, whether technical or otherwise.  Non-Binding Mediation is voluntary and will not be a condition precedent to initiating the institution of Legal Proceedings by either party.  The non-requesting party may decline the request in its sole discretion.  If there is concurrence that any particular matter shall be mediated, the provisions of this Section shall apply.  The costs of such Non-Binding Mediation shall be divided equally between the City and the Design-Builder.

### Procedure.  The Mediator shall be a professional engineer, attorney or other professional mutually acceptable to the parties who has no current or on-going relationship to either party.  The Mediator shall have full discretion as to the conduct of the mediation.  Each party shall participate in the Mediator’s program to resolve the dispute until and unless the parties reach agreement with respect to the disputed matter or one party determines in its sole discretion that its interests are not being served by the mediation.

### Non-Binding Effect.  Mediation is intended to assist the parties in resolving disputes over the correct interpretation of this Design-Build Contract.  No Mediator shall be empowered to render a binding decision.

### Relation to Judicial Legal Proceedings.  Except as provided in subsection (C) of this Section with respect to the City Contract Representative’s Final Decision, nothing in this Section shall operate to limit, interfere with or delay the right of either party under this Article to commence judicial Legal Proceedings upon a breach of this Design-Build Contract by the other party, whether in lieu of, concurrently with, or at the conclusion of any Non-Binding Mediation.

## FORUM FOR DISPUTE RESOLUTION.

It is the express intention of the parties that all Legal Proceedings related to this Design-Build Contract or to the Project or to any rights or any relationship between the parties arising therefrom shall be solely and exclusively initiated and maintained in State or federal courts located in Pierce County, Washington, having appropriate jurisdiction therefor.  The Design-Builder and the City each irrevocably consents to the jurisdiction of such courts in any such Legal Proceeding and waives any objection it may have to the laying of the jurisdiction of any such Legal Proceeding.

## CONTINUANCE OF PERFORMANCE DURING DISPUTE.

Unless otherwise directed in writing by the City, at all times during the course of any dispute resolution procedure or Legal Proceeding, the Design-Builder shall continue with the performance of the Contract Obligations in a diligent manner and in accordance with the applicable provisions of this Design-Build Contract.  The City shall continue to satisfy its uncontested payment obligations to the Design-Builder during the pendency of any such dispute, subject to the terms and conditions of this Design-Build Contract.  Records of the Contract Obligations performed during such time shall be kept in accordance with the applicable provisions of this Design-Build Contract.

# BREACH, DEFAULT, REMEDIES AND TERMINATION

## REMEDIES FOR BREACH.

### Generally.  The parties agree that, except as otherwise provided in this Section, in the event that either party breaches this Design-Build Contract, the other party may exercise any legal rights it may have under this Design-Build Contract and under Applicable Law.  Neither party shall have the right to terminate this Design-Build Contract except as expressly provided in this Article.

### No Effect On Contract Obligations.  The exercise by the City of any of its rights under this Article shall not reduce or affect in any way the Design-Builder’s responsibility hereunder to perform the Contract Obligations.

### No Duplicative Recovery; Express Remedies.  Every right to claim compensation, indemnification or reimbursement under this Design-Build Contract shall be construed so that recovery is without duplication to any other amount recoverable under this Design-Build Contract. Without prejudice to any legal right or entitlement of the Design-Builder to specific performance or injunctive relief, the Design-Builder’s sole remedy in relation to matters for which an express right or remedy is stated in this Design-Build Contract shall be that express right or remedy, and the Design-Builder shall have no additional right or remedy arising by common law, in equity, by statute or otherwise.

## EVENTS OF DEFAULT BY THE DESIGN-BUILDER.

### Events of Default Not Requiring Previous Notice or Cure Opportunity for Termination.  Each of the following shall constitute an Event of Default by the Design-Builder upon which the City, by notice to the Design-Builder, may terminate this Design-Build Contract without any requirement of having given notice previously or of providing any further cure opportunity:

###### Failure to Achieve Substantial Completion.  Except to the extent excused due to the occurrence of Uncontrollable Circumstances, the failure of the Design-Builder to achieve Substantial Completion prior to the end of the Extension Period;

###### Failure to Achieve Final Completion.  Except to the extent excused due to the occurrence of Uncontrollable Circumstances, the failure of the Design-Builder to achieve Final Completion by the date set forth in (A);

###### Security for Performance.  The failure of the Design-Builder to obtain and maintain in full force and effect in accordance with the requirements of this Design-Build Contract any Security Instrument required by Article 16 as security for the performance of this Design-Build Contract;

###### Required Insurance.  The failure of the Design-Builder to obtain and maintain in full force and effect in accordance with the requirements of this Design-Build Contract any Required Insurance required by Article 13 and Appendix 10;

###### Assignment or Transfer Without Consent.  The Design-Builder assigns or transfers this Design-Build Contract or any right or interest therein without the City’s prior written consent;

###### Insolvency.  The insolvency of the Design-Builder as determined under the Bankruptcy Law;

###### Voluntary Bankruptcy.  The filing by the Design-Builder of a petition of voluntary bankruptcy under the Bankruptcy Law; the consenting of the Design-Builder to the filing of any bankruptcy or reorganization petition against the Design-Builder under the Bankruptcy Law; or the filing by the Design-Builder of a petition to reorganize the Design-Builder pursuant to the Bankruptcy Law;

###### Involuntary Bankruptcy.  The issuance of an order of a court of competent jurisdiction appointing a receiver, liquidator, custodian or trustee of the Design-Builder or of a major part of the property of the Design-Builder or the filing against the Design-Builder of a petition to reorganize the Design-Builder pursuant to the Bankruptcy Law, which order shall not have been discharged or which filing shall not have been dismissed within 90 days after such issuance or filing; or

###### Abandonment.  The Design-Builder suspends, ceases, stops or abandons the Design-Build Work or fails to continuously and diligently prosecute the Design-Build Work, exclusive of work stoppages due to an Uncontrollable Circumstance.

### Events of Default Requiring Previous Notice and Cure Opportunity for Termination.  It shall be an Event of Default by the Design-Builder upon which the City may terminate this Design-Build Contract, by notice to the Design-Builder and subject to the Design-Builder’s cure rights set forth in subsection (C) of this Section, if:

###### Any representation or warranty in this Design-Build Contract made by the Design-Builder, or in any certificate, schedule, report, instrument, agreement or other document delivered by or on behalf of Design-Builder to the City pursuant to this Design-Build Contract, is false, misleading or inaccurate in any material respect when made or omits material information when made;

###### The Design-Builder fails, refuses or otherwise defaults in its duty to pay any amount required to be paid to the City under this Design-Build Contract within 60 days following the due date for such payment;

###### The Design-Builder fails to resume performance of the Design-Build Work which has been suspended or stopped within a reasonable time after receipt of notice from the City to do so or (if applicable) after cessation of the event preventing performance;

###### The Design-Builder fails materially to comply with any Applicable Law or fails unreasonably to comply with the instructions of the City consistent with this Design-Build Contract; or

###### The Design-Builder commits a material breach of this Design-Build Contract or otherwise fails to perform any other material obligation under this Design-Build Contract (unless such breach or failure is excused by an Uncontrollable Circumstance as and to the extent provided herein).

### Notice and Cure Opportunity.  The Design-Builder acknowledges that the City has an immediate termination right upon the occurrence of any of the defaults listed in subsection (A) of this Section and that the Design-Builder has no further right of notice or cure in such circumstances of default.  Conversely, no default listed in subsection (B) of this Section shall constitute an Event of Default giving the City the right to terminate this Design-Build Contract for cause under this Section unless:

###### The City has given prior written notice to the Design-Builder stating that a specified default has occurred which gives the City a right to terminate this Design-Build Contract for cause under this Section, and describing the default in reasonable detail; and

###### The Design-Builder has not initiated within a reasonable time (in any event not more than 10 days from the initial default notice) and continued with due diligence to carry out to completion all actions reasonably necessary to correct the default and prevent its recurrence.

If the Design-Builder shall have initiated and continued with due diligence to carry out to completion all actions required under item (2), above, the default shall not constitute an Event of Default during such period of time (in any event not more than 60 days from the initial default notice) as the Design-Builder shall continue with due diligence to carry out to completion all such actions.

### Other Remedies Upon Design-Builder Event of Default.  The right of termination provided under this Section upon an Event of Default by the Design-Builder is not exclusive.  If this Design-Build Contract is terminated by the City for an Event of Default by the Design-Builder, the City shall have the right to pursue a cause of action for actual damages and to exercise all other remedies which are available to it under this Design-Build Contract, under the Security Instruments and under Applicable Law.  The Design-Builder shall not be entitled to any compensation for services provided subsequent to receiving any notice of termination for an Event of Default under this Section.

### Relationship to Liquidated Damages.  Termination by the City pursuant to this Section shall not relieve the Design-Builder or its Surety from liability for the liquidated damages provided for under this Design-Build Contract.  The parties acknowledge and agree that such liquidated damages are intended solely to compensate the City for costs and expenses associated with unexcused delay in the specific circumstances identified in the specific provisions providing for such liquidated damages and are not intended to liquidate all damages that the City is likely to suffer in the event of a Design-Builder Event of Default under this Article.  Accordingly, except with respect to damages relating solely to the specific circumstances of unexcused delay for which liquidated damages are provided under this Design-Build Contract, the payment of any such liquidated damages by the Design-Builder shall not serve to limit or otherwise affect the City’s right to pursue and recover damages under subsection (D) of this Section.

## LIMITATION ON DESIGN-BUILDER LIABILITY.

### Design-Builder Liability Limit.  Subject to subsection (B) of this Section, the Design-Builder’s aggregate liability under this Design-Build Contract with respect to damages of any kind payable to the City arising out of the performance or unexcused nonperformance of the Design-Build Work as a consequence of a claim or suit initiated by the City shall not exceed an amount equal to: (1) the aggregate value of Early Work Package Prices for all Early Work Packages and the Stage 1 Preliminary Services Fee, during the period commencing on the Contract Date and ending on the GMP Amendment Date; and (2) the sum of (i) the Stage 1 Preliminary Services Fee, (ii) amounts paid by the City for Early Work Packages and (iii) the Guaranteed Maximum Price commencing on the GMP Amendment Date and at all times thereafter.

### Liquidated Damages Sub-Limit.  The aggregate liability of the Design-Builder, with respect to any liquidated damages payable pursuant Section 8.3(C), shall not exceed an amount equal to 10% of the Guaranteed Maximum Price.  The payment by the Design-Builder of any such liquidated damages shall reduce commensurately the liability limit set forth in subsection (A) of this Section.

## APPLICABILITY AND INTERPRETATION OF THE LIMITATION ON LIABILITY.

The limitation on Design-Builder liability provided for in Section 12.3 applies solely to the liability of the Design-Builder for damages to the City arising out of the performance or unexcused nonperformance of this Design-Build Contract as a consequence of a contract claim initiated by the City.  The limitation on liability provided for in Section 12.3 shall not apply in the event the Design-Builder abandons the Project, and does not apply to any other liability, loss, damage, cost or expense that may be incurred by the Design-Builder in connection with this Design-Build Contract, including any of the following liabilities, losses, damages, costs or expenses:

###### Any loss, cost or expense incurred by any Design-Builder Person in the performance of the Design-Build Work or in seeking to cure or prevent any breach of this Design-Build Contract by the Design-Builder;

###### Any fines or penalties levied or imposed by any Governmental Body;

###### Any indemnity payment (resulting from third party claims) made by the Design-Builder to the City;

###### Payment of any defense costs, including attorney’s fees, to, for, or on behalf of the City with respect to any third party claim;

###### Any payments made in connection with any Required Insurance under this Design-Build Contract, including the proceeds of Required Insurance and the payment of any deductible or self-insured retention; and

###### Any claims, losses, penalties or settlement payments paid to the City in connection with any tort claim by the City against the Design-Builder based on negligence, willful misconduct, fraud, misrepresentation or false claims.

## EVENTS OF DEFAULT BY THE CITY

### Events of Default Permitting Termination.  The failure, refusal or other default by the City in its duty to pay any undisputed amount required to be paid to the Design-Builder under this Design-Build Contract within 30 days following the due date for such payment shall constitute an Event of Default by the City upon which the Design-Builder, by notice to the City, may terminate this Design-Build Contract, subject to the terms and conditions of this Section.

### Notice and Cure Opportunity.  No such default described in subsection (A) of this Section shall constitute an Event of Default giving the Design-Builder the right to terminate this Design-Build Contract for cause under this subsection (B) unless:

###### The Design-Builder has given prior written notice to the City stating that a specified default has occurred which gives the Design-Builder a right to terminate this Design-Build Contract for cause under this Section, and describing the default in reasonable detail; and

###### The City has neither challenged in an appropriate forum the Design-Builder’s conclusion that such default has occurred nor initiated within a reasonable time (in any event not more than 30 days from the initial default notice) and continued with due diligence to carry out to completion all actions reasonably necessary to correct the default and prevent its recurrence.

If the City shall have initiated and continued with due diligence to carry out to completion all actions required under item (2), above, the default shall not constitute an Event of Default during such period of time (in any event not more than 60 days from the initial default notice) as the City shall continue with due diligence to carry out to completion all such actions.

### Other City Breaches Constituting Uncontrollable Circumstances.  Except for the City Events of Default described in subsection (A) of this Section, the failure of the City to perform any other material obligation under this Design-Build Contract (unless such default is the due to Design-Builder Fault or excused by an Uncontrollable Circumstance as and to the extent provided herein), shall constitute an Uncontrollable Circumstance as and to the extent provided in Article 14, and the Design-Builder shall have no right to terminate this Design-Build Contract.

### Effect of Termination.  If this Design-Build Contract is terminated by the Design-Builder for cause as a result of an Event of Default by the City, the City shall pay the Design-Builder the same amount which would be payable under Section 12.6 if this Design-Build Contract were terminated at the election of the City for convenience and without cause based on the date of termination.  The City shall have no further liability to the Design-Builder for any Event of Default or termination under this Section.

## CITY CONVENIENCE TERMINATION RIGHTS.

### Convenience Termination Right and Payment.  The City shall have the right at any time following the Contract Date, exercisable in its discretion for any reason (including the failure to agree to a GMP Amendment) upon 30 days’ written notice to the Design-Builder, to terminate this Design-Build Contract.

### Convenience Termination Payment for Stage 1 Preliminary Services.  In the event of a convenience termination pursuant to this Section of the Stage 1 Preliminary Services, the Design-Builder shall not be entitled to a convenience termination settlement payment, but shall be entitled to payment of that portion of the Stage 1 Preliminary Services Fee that has been earned by the terms hereof as of the Termination Date but not yet paid by the City.  No other compensation shall be payable by the City on account of the City’s convenience termination of the Stage 1 Preliminary Services.

### Convenience Termination Payment for Stage 2 Design-Build Work.  In the event of a convenience termination pursuant to this Section of the Stage 2 Design-Build Work (including Design-Build Work performed pursuant to an Early Work Package Amendment), the Design-Builder shall be entitled to a convenience termination settlement payment in an amount equal to the sum of:

###### The difference between, (a) the value of all such Stage 2 Design-Build Work performed up to the Termination Date, and (b) all payments already made to the Design-Builder pursuant to this Design-Build Contract for Stage 2 Design-Build Work; and

###### Subject to subsection (E) of this Section, the reasonable costs incurred by the Design-Builder in connection with the termination, including all actual and reasonable demobilization costs and amounts due in settlement of terminated Subcontracts.

In the event of a termination for convenience under this Section, the Design-Builder acknowledges and agrees that it shall not be entitled to any compensation in excess of the value of the Stage 2 Design-Build Work performed plus its settlement and closeout costs.  Under no circumstances shall the Design-Builder or any Subcontractor be entitled to anticipatory or unearned profits, unabsorbed overhead, opportunity costs, or consequential or other damages as a result of a termination for convenience under this Section.

### Early Work Packages.  If the parties have entered into any Early Work Package Amendment prior to any convenience termination pursuant to this Section, the City shall have the right to:

###### Terminate the Design-Builder’s right to perform any Design-Build Work authorized by any such Early Work Package Amendment and, at the City’s option, require the Design-Builder to assign any Subcontracts to the City; or

###### Require the Design-Builder to complete performance of such Design-Build Work in accordance with the applicable Early Work Package Amendment.

If the City elects to terminate such Design-Build Work pursuant to clause (1) of this subsection (D), the Design-Builder shall be entitled to a termination settlement payment associated solely with the terminated Early Work Package Design-Build Work, as and to the extent provided in subsection (C) of this Section.  Nothing in this subsection (D) shall provide grounds for adjustment of any applicable Early Work Package Price or limit the City’s rights to convenience terminate Design-Build Work authorized by an Early Work Package Amendment without terminating the Stage 1 Preliminary Services or the Stage 2 Design-Build Work.

### Settlement of Subcontracts.  The obligation of the City to pay amounts due in settlement of Subcontracts under subsection (C) of this Section shall be limited to the reasonable costs incurred by the Design-Builder in settling and closing out Subcontracts that the City does not elect to have assigned to it pursuant to Section 12.7 and shall be subject to Cost Substantiation.  Any convenience termination settlement payment under any Subcontract shall be calculated in the same manner as provided in subsection (C) of this Section with respect to the convenience termination settlement payment to the Design-Builder.  In no event shall the City be responsible for anticipatory or unearned profits, unabsorbed overhead, opportunity costs, or consequential or other damages payable to any Subcontractor as a result of the termination of any Subcontract.

### Payment of Amounts Due as a Result of Convenience Termination.  The Design-Builder shall submit a termination for convenience claim, in the form and with the certification prescribed by the City, promptly following the Termination Date but in any event not later than 60 days following the Termination Date.  In the event of a failure of the Design-Builder to submit a termination for convenience claim within the time allowed pursuant to this subsection (F), the City may determine, on the basis of information available to the City, the amount, if any, due to the Design-Builder by reason of the convenience termination and shall thereupon pay to the Design-Builder the amount so determined, if any.  In no event shall the amount payable to the Design-Builder pursuant to this Section exceed the Guaranteed Maximum Price as reduced by the amount of payments otherwise made.  In addition, any amount payable to the Design-Builder pursuant to this Section shall be reduced in the amount of (1) any claim the City may have against the Design-Builder under this Design-Build Contract, and (2) the fair value, as determined by the City, of property which is destroyed, lost, stolen or damaged so as to become undeliverable to the City, excluding normal spoilage and except to the extent that the City shall have otherwise expressly assumed the risk of loss with respect to such property hereunder.  Any payment required to be made to the Design-Builder pursuant to this Section shall be made within 120 days following the Termination Date, subject to compliance by the Design-Builder with its obligations under Section 12.7.  Any payment required to be made by the Design-Builder to the City pursuant to this Section shall be made within 120 days following the Termination Date.  In the event of a dispute between the parties as to the amount of any payment required to be made pursuant to this Section, either party may elect to initiate dispute resolution procedures in accordance with Section 11.1.

### Completion or Continuance by the City.  Without limiting any other the City right or remedy provided for under this Design-Build Contract, after the date of any termination under this Section, the City may at any time (but without any obligation to do so) take any and all actions necessary or desirable to continue and complete the Contract Obligations so terminated, including entering into contracts with other contractors.

### Convenience Termination Rights as Consideration.  The right of the City to terminate this Design-Build Contract for its convenience and in its sole discretion in accordance with this Section constitutes an essential part of the overall consideration for this Design-Build Contract, and, except with respect to the determination as to the amount due the Design-Builder pursuant to this Section, the Design-Builder hereby waives any right it may have under Applicable Law to assert that the City owes the Design-Builder a duty of good faith dealing in the exercise of such right.  The only compensation payable by the City upon the exercise of its convenience termination option shall be any amounts specified herein in connection therewith.

## OBLIGATIONS OF THE DESIGN-BUILDER UPON TERMINATION.

Upon any termination of the Design-Builder’s right to perform this Design-Build Contract, the Design-Builder shall, as applicable and subject to any written directions provided by the City:

###### Stop any further Contract Obligations at the Project Sites or otherwise in connection with the Project;

###### Cease incurring any further obligations or liabilities pertaining to the Contract Obligations;

###### Promptly take all action as necessary to protect and preserve all materials, equipment, tools, facilities, and other property pertaining to the Project;

###### Vacate possession of the Project Sites and turn possession of the Project Sites over to the City;

###### Clean up and remove all debris and trash from the Project Sites;

###### Promptly remove from the Project Sites all equipment, tools, or material owned by the Design-Builder, or its Subcontractors, agents or representatives;

###### Promptly deliver a list of all suppliers, materials, machinery, equipment, property or other pending items being fabricated or on order for delivery to the Project but not yet delivered to the Project Sites or incorporated into the Design-Build Work, and comply with the written instructions of the City with respect to such matters;

###### Deliver a complete copy of all books, notes, and records of the Design-Builder pertaining to Design-Build Contract performance or planned construction or design activities;

###### Promptly provide a list of (and make available to the City for review or copying) all files pertaining to the Design-Build Work, including any and all access and security codes, and including instructions and demonstrations that show how to open and modify such codes;

###### Promptly deliver complete copies of all Subcontracts to the City, together with a detailed report on the status of such Subcontracts (status of orders and work performed and not performed or delivered under each Subcontract); a record of proposals made and balances due under each Subcontract; any cancellation penalties pertaining thereto; and any further information required by the City, and furthermore assist the City in contacting such Subcontractors to verify such information or answer any questions of the City;

###### Assign to the City any Subcontract that the City elects in writing, in its discretion, to have assigned to it, with the City assuming, and the Design-Builder being relieved of, all obligations under the Subcontract from the date of the assignment;

###### Cancel or terminate all Subcontracts that the City does not elect to have assigned to the City, in accordance with the written instructions of the City;

###### Promptly assign and transfer to the City all right, title, and interest of Design-Builder to any items ordered for the Contract Obligations (but not yet delivered to the Project Sites or incorporated into the Project), as requested by the City in its discretion; provided the City (or Surety) assumes responsibility for payment thereof;

###### Promptly deliver and assign to the City all warranties or guarantees by any vendor, supplier, manufacturer, or subcontractor pertaining to the Project;

###### Promptly notify the City (in writing) of any pending or threatened Legal Proceedings against the Design-Builder;

###### Make arrangements with its employees to avoid any “successor clauses” or other similar provisions with respect to salaries or benefits, to allow the City to enter into new employment or independent contractor agreements with employees of the Design-Builder deemed available or necessary by the City to complete (or correct defects) in the Design-Build Work; and

###### Promptly take such other action and execute such documents as requested by the City, and to assist in the transition of the Contract Obligations to the Surety or the City, or as reasonably deemed necessary or appropriate by the City, and avoid any action or conduct that would increase any expense or cost that would become an obligation or liability to the City unless requested or directed by the City Contract Representative in writing.

With respect to any of the foregoing obligations that cannot reasonably be completed by the Termination Date, the Design-Builder shall complete such obligations as promptly as is practicable, but in no event later than 30 days following the Termination Date.  Compliance with these obligations shall be conditions precedent to the payment of any sums otherwise due the Design-Builder by reason of the termination.  If any Subcontracts are assigned to the City under this Section, the City shall not be directly liable to any Subcontractors for amounts owed to such parties for Design-Build Work performed prior to termination, and the Design-Builder shall remain liable to any such parties for such amounts.

## NO WAIVERS.

No action of the City or the Design-Builder pursuant to this Design-Build Contract (including any investigation or payment), and no failure to act, shall constitute a waiver by either party of the other party’s compliance with any term or provision of this Design-Build Contract.  No course of dealing, failure or delay by the City or the Design-Builder in exercising any right, power or remedy under this Design-Build Contract shall operate as a waiver thereof or otherwise prejudice such party’s rights, powers and remedies.  No single or partial exercise of (or failure to exercise) any right, power or remedy of the City or the Design-Builder under this Design-Build Contract shall preclude any other or further exercise thereof or the exercise of any other right, power or remedy.  No waiver of any breach of any provision of this Design-Build Contract will be deemed to be a waiver of any subsequent breach of that provision or of any similar provision.

## WAIVER OF CONSEQUENTIAL AND PUNITIVE DAMAGES.

To the fullest extent permitted by law, and notwithstanding any other provision of the Contract Documents, in no event, whether arising out of contract, breach of warranty (express or implied), tort (including negligence), strict liability, or any other cause of or form of action whatsoever, shall either party be liable to the other for any consequential damages (including damages for loss of use, loss of profits or anticipated profits, loss of revenue, and loss of business opportunity) or punitive damages arising out of or in connection with the performance or non-performance of its obligations under this Design-Build Contract; provided, however, that, except as provided in the next sentence, the waiver of the foregoing damages under this Section is intended to apply only to disputes and claims as between the City and the Design-Builder and, with respect to damages payable by the Design-Builder, the waiver of consequential or punitive damages applies only to the extent such damages are in excess of consequential or punitive damages covered or required to be covered by insurance.  Nothing in this Section shall limit the indemnification obligations of the Design-Builder hereunder for any consequential or punitive damages payable to third parties resulting from any act or circumstance for which the Design-Builder is obligated to indemnify the City or the City Indemnitees hereunder.  In addition, the Design-Builder acknowledges and agrees that the foregoing waiver shall not apply to, serve as a limitation or defense in respect of, or otherwise limit any right of recovery the City may have respecting:

#### Any damage, cost, loss or expense (including defense costs) to the extent (a) covered or required to be covered by the proceeds of Required Insurance, or (b) covered by the proceeds of insurance actually carried by or insuring Design-Builder under policies solely with respect to the Project, regardless of whether required to be carried pursuant to Appendix 10; and

#### The Design-Builder’s obligation to pay any liquidated damages specifically provided for under this Design-Build Contract.

# INSURANCE

## INSURANCE.

### Required Insurance.  At all times during the Term, the Design-Builder shall obtain, maintain and comply with the terms and conditions of the Required Insurance in accordance with Appendix 10 and shall pay all premiums with respect thereto as the same become due and payable.  The Required Insurance shall be provided concurrently with the execution and delivery of this Design-Build Contract (or as otherwise specified in Appendix 10) and remain in effect for the periods specified in Appendix 10.  The Design-Builder’s liability insurance, including professional liability, shall not include any design-build or similar exclusions that would compromise coverages because of the design-build nature of the work to be performed pursuant to this Design-Build Contract.  Appendix 10 also includes notice and reporting requirements for the Required Insurance, including the required workers’ compensation insurance.

### Insurers, Deductibles and the City Rights.  All insurance required by this Section shall be obtained and maintained from insurance companies, firms or entities that comply with the applicable requirements specified in Appendix 10.  The insurers shall be selected by the Design-Builder with the consent of the City, which consent shall not be unreasonably withheld, and authorized to write such insurance in the State.  All deductibles or self-insured retention amounts included in the Required Insurance coverage shall be subject to the reasonable approval of the City.  The Design-Builder shall be responsible for the payment of any deductible amounts.  The Design-Builder shall also be responsible for all self-insured retentions contained in its insurance coverages, as well as any excluded losses if such losses are within the liability of the Design-Builder hereunder.  All policies evidencing such insurance shall provide for:

###### Payment of the losses to the City, and to the Design-Builder as their respective interests may appear;

###### At least 30 days’ prior written notice of the cancellation thereof to the City (except for cancellation resulting from non-payment of premium); and

###### At least 10 days’ prior written notice of cancellation thereof to the City in the event of cancellation resulting from non-payment of premium.

All policies of insurance provided by or on behalf of the Design-Builder shall be primary and non-contributory with respect to any insurance or self-insurance carried by the City.  The City shall have the right to fully participate in all insurance claim settlement negotiations and to approve all final insurance settlements, which approval shall not be unreasonably withheld.

### Certificates, Policies and Notice.  The Required Insurance, including any renewals thereof, shall be evidenced by certificates of insurance as provided herein and in Appendix 10.  No later than 30 days prior to the issuance date of each policy of Required Insurance, including any renewals thereof, the Design-Builder shall provide the City with a draft certificate of insurance for review and approval, and shall deliver the final, approved certificate of insurance to the City promptly following its issuance.  All policies of Required Insurance shall be made available for review by the City’s outside legal counsel, who will conduct the review solely for the purposes of providing the City legal advice as to whether the Design-Builder’s policies meet Required Insurance requirements hereunder.  The Design-Builder shall certify to the City that the policies being provided for review are a complete, true and correct compilation of all relevant policies evidencing insurance required under Appendix 10, recognizing that the City and its designated representatives will rely on such certification.  The City agrees that it shall instruct and require that its outside legal counsel will not disclose or provide to the City access to such insurance policies or the specific terms or conditions thereof, without the express prior written consent of the Design-Builder.  The City’s outside legal counsel’s legal advice shall be limited to only confirming whether such policies of insurance comply with the insurance requirements in this Design-Build Contract, or generally describing the nature of any deficiency observed in such policies. In its submission, the Design-Builder may claim confidentiality with respect to its insurance policies to protect the same against disclosure under the Public Information Act, and in such event the City will take reasonable action (up to seeking an attorney general opinion regarding exceptions that may apply) to seek to preserve the confidentiality of the information about the Design-Builder’s insurance policies in the possession of the City’s outside legal counsel, pursuant to the attorney client privilege and any other applicable exception to disclosure under the Public Information Act that the City in its sole discretion determines to assert.  In addition, upon conducting such review, if the City’s outside legal counsel determines that policies of Required Insurance contain deficiencies that cause such policies not to comply with the requirements of this Design-Build Contract, the Design-Builder shall remedy the defect and, without limiting any other the City right or remedy provided for under this Design-Build Contract, in the event of a failure of compliance with the Required Insurance, the Design-Builder shall reimburse the City for the cost and expense incurred by the City in connection with the City’s outside legal counsel attempting to resolve such policy deficiencies by modification or endorsement thereof to achieve compliance with the requirements hereunder.

### Subcontractors.  Whenever a Subcontractor is utilized, the Design-Builder shall either obtain and maintain or require the Subcontractor to obtain and maintain insurance in accordance with the applicable requirements of Appendix 10.

### Maintenance of Insurance Coverage.  If the Design-Builder fails to pay any premium for Required Insurance, or if any insurer cancels any Required Insurance policy and the Design-Builder fails to obtain replacement coverage so that the Required Insurance is maintained on a continuous basis, then, at the City’s election (but without any obligation to do so), the City, following notice to the Design-Builder, may pay such premium or procure similar insurance coverage from another company or companies and upon such payment by the City the amount thereof shall be immediately reimbursed to the City by the Design-Builder.  The Design-Builder shall not perform Design-Build Work during any period when any policy of Required Insurance is not in effect.  The Design-Builder shall comply with all Insurance Requirements and take all steps necessary to assure that the Project remains continuously insured in accordance with the requirements of this Design-Build Contract.  The failure of the Design-Builder to obtain and maintain any Required Insurance shall not relieve the Design-Builder of its liability for any losses intended to be insured thereby.  Should any failure to provide continuous insurance coverage occur, the Design-Builder shall indemnify, defend and hold harmless the City Indemnitees in accordance with and to the extent provided in Article 15 from and against all Loss-and-Expense arising out of such failure.  The purchase of the Required Insurance to satisfy the Design-Builder’s obligations under this Section shall not be a satisfaction of any Design-Builder liability under this Design-Build Contract or in any way limit, modify or satisfy the Design-Builder’s indemnity obligations hereunder.

### Compliance with Insurer Requirements.  The Design-Builder shall comply promptly with the requirements of all insurers providing the Required Insurance pertaining to the Project. The Design-Builder shall not knowingly do or permit anything to be done that results in the cancellation or the reduction of coverage under any policy of Required Insurance.

### Reductions for Insurance Proceeds.  Whenever this Design-Build Contract obligates the City to pay any amount to the Design-Builder in respect of an event or circumstance for which, or with respect to the consequences of which, an insurance claim may be made by the Design-Builder under the Required Insurance, the amount which the City is obligated to pay will be reduced by the amount of insurance proceeds which the Design-Builder recovers or would have been entitled to recover if it had complied with the requirements of this Design-Build Contract or any policy of Required Insurance.

# UNCONTROLLABLE CIRCUMSTANCES

## UNCONTROLLABLE CIRCUMSTANCES GENERALLY.

### Extent of Relief Available to the Design-Builder.  If an Uncontrollable Circumstance occurs, the Design-Builder may be entitled to relief from its obligations, extensions of time and compensation, as and to the extent provided in this Article.  Such relief shall be available irrespective of whether an obligation of this Design-Build Contract expressly states that it is excused by Uncontrollable Circumstances.

### Mitigation Given Effect.  Any relief to which the Design-Builder is entitled under this Article on account of Uncontrollable Circumstances shall be adjusted to account for the effect of the mitigation measures which were or should have been taken by the Design-Builder in compliance with its duty to mitigate under Section 17.10.

### Applicable Law Compliance.  Nothing in this Article shall be interpreted as relieving the Design-Builder of its obligation, following any and all Uncontrollable Circumstances, to perform its obligations under this Design-Build Contract in compliance with Applicable Law.

### Contract Obligations Not Affected; Resumption of Performance.  The occurrence of an Uncontrollable Circumstance shall not excuse the Design-Builder from performing any obligation hereunder not directly affected by the occurrence of the Uncontrollable Circumstance.  Upon the occurrence of an Uncontrollable Circumstance, the Design-Builder shall promptly use all reasonable efforts to eliminate the cause thereof and resume performance of the affected Contract Obligations.

## UNCONTROLLABLE CIRCUMSTANCE CLAIM PROCEDURES.

### Notice and Written Report.  In order to assert an entitlement based on the occurrence of an Uncontrollable Circumstance, the Design-Builder shall give notice of the occurrence of the Uncontrollable Circumstance to the City as soon as practicable, and in any event within 14 days of the date the Design-Builder has knowledge that the Uncontrollable Circumstance has caused or is likely to cause an entitlement under this Design-Build Contract.  The Design-Builder’s notice shall include a written report:

###### Describing the Uncontrollable Circumstance and the cause thereof, to the extent known;

###### Stating the date on which the Uncontrollable Circumstance began and its estimated duration, to the extent known;

###### Summarizing the consequences of the Uncontrollable Circumstance and the expected impact on the performance of the Design-Builder’s obligations under this Design-Build Contract; and

###### Indicating the nature and scope of the Design-Builder’s potential entitlement to relief.

### Updates.  The Design-Builder shall provide the City with periodic updates, together with further details and supporting documentation, as it receives or develops additional information pertaining to the Uncontrollable Circumstance and the matters described in subsection (A) of this Section.  In particular, the Design-Builder shall notify the City as soon as the Uncontrollable Circumstance has ceased and of the time when performance of its affected obligations can be resumed.

### Submittal of Relief Request.  The Design-Builder shall submit to the City a further notice making its request for specific relief, the basis therefor and the event giving rise to the requested relief (the “Relief Request Notice”), promptly after becoming aware of such occurrence, but not more than 30 days after the City’s receipt of the notice required under subsection (A) of this Section; provided that, if the specific relief cannot reasonably be ascertained within such period, the Design-Builder shall furnish the Relief Request Notice within such longer period as is reasonably necessary to detail the event and ascertain such relief; however, in any event, such Relief Request Notice shall be submitted to the City not more than 60 days after the City’s receipt of the notice required under subsection (A) of this Section.  Each Relief Request Notice shall include all information required in this Article with respect to the specific relief being requested.

### Delay in Notification.  The Design-Builder acknowledges that any delay by the Design-Builder in submitting to the City any Uncontrollable Circumstance notice or any information required under this Section, beyond the applicable time period required under this Section may adversely affect the City, and agrees that the relief to be provided in respect of any Uncontrollable Circumstance shall be reduced or limited to the extent of any such adverse effect, as reasonably determined by the City.  The Design-Builder shall be deemed to have become aware of the occurrence of an Uncontrollable Circumstance if such occurrence could reasonably have been known, identified, discovered or observed by the Design-Builder through the employment of procedures consistent with Good Engineering and Construction Practice.  Without limiting any of the foregoing, if the Design-Builder fails to submit a Relief Request Notice within 60 days after the City’s receipt of the notice required under subsection (A) of this Section or to notify the City of the occurrence of an Uncontrollable Circumstance within 60 days following the occurrence, then the Design-Builder shall be deemed to have irrevocably and forever waived and released any and all claim or right with respect to the subject Uncontrollable Circumstance.

### Multiple and Overlapping Claims.  The Design-Builder may make multiple but not duplicative claims with respect to an Uncontrollable Circumstance.

### Burden of Proof and Mitigation.  The Design-Builder shall bear the burden of proof in establishing the occurrence of an Uncontrollable Circumstance and the entitlement to relief based thereon, and shall demonstrate that the Design-Builder complied with its mitigation obligations under Section 17.10.

### City Response.  The City may, but shall have no obligation to, respond to the Design-Builder’s initial notice concerning the occurrence of an Uncontrollable Circumstance under subsection (A) of this Section.  Within 30 days after receipt of a Relief Request Notice pursuant to subsection (C) of this Section, the City shall issue a written determination as to the extent, if any, to which it concurs with the Design-Builder’s request and the reasons therefor.

### Agreement or Dispute.  The agreement of the parties as to the specific relief to be given the Design-Builder on account of an Uncontrollable Circumstance shall be evidenced by a Change Order, a Contract Amendment or other written agreement between the parties.  Either party may refer any dispute for resolution in accordance with Section 11.1.

### Certifications.  Each submittal made under this Section by the Design-Builder shall be accompanied by a certification of the Design-Builder Contract Representative that the submittal is made in good faith; that the supporting data are complete and accurate at the time of the submittal to the best knowledge of the Design-Builder; and that the requested relief accurately reflects the relief to which the Design-Builder reasonably believes it is entitled hereunder.  The Design-Builder shall have no entitlement to relief for uncertified claims.

## UNCONTROLLABLE CIRCUMSTANCES RELIEF.

If and to the extent that an Uncontrollable Circumstance interferes with, delays or increases the cost to the Design-Builder performing the Design-Build Work in accordance herewith, the Design-Builder shall, subject to Section 14.4, be entitled to:

###### Relief from its performance obligations;

###### An adjustment to the Scheduled Substantial Completion Date;

###### An adjustment to the Contract Compensation for such costs (except as otherwise expressly provided herein); or

###### A Base Guaranteed Maximum Price Adjustment (except as and to the extent provided in this Section, Section 14.2 and Article 15);

or any combination thereof, each of which properly reflects the interference with performance, the time lost as a result thereof, or the amount of the increased cost, in each case only to the minimum extent necessary to compensate the Design-Builder or provide performance or schedule relief and only to the extent directly attributable to the Uncontrollable Circumstance.  Any cost reduction achieved, or which should have been achieved, through the mitigation measures undertaken by the Design-Builder pursuant to Section 17.10 shall be reflected in a reduction of the amount of the additional Contract Compensation or Base Guaranteed Maximum Price Adjustment as appropriate to reflect such mitigation measures.  The Design-Builder shall not be entitled to any price relief on account of any costs incurred as the result of Design-Builder Fault or an act, event or circumstance that the Design-Builder is obligated to insure against under Article 13, irrespective of any limits of coverage and of any deductible applicable under any policy of insurance maintained or required to be maintained thereunder.

## SCHEDULE RELIEF AND RELATED PRICE RELIEF.

### Conditions to Schedule Relief.

#### Float in the Stage 2 Design-Build Work Schedule.  The parties acknowledge and agree that “float” in the Stage 2 Design-Build Work Schedule:

##### Means the amount of time that any given activity or logically connected sequence of activities shown on the Stage 2 Design-Build Work Schedule may be delayed before it delays the occurrence of a scheduled completion milestone; and

##### Is an expiring resource available to the Project for the benefit of both parties, available to each of them as needed to absorb delays in achieving the scheduled completion milestones, whether such delays are caused by Uncontrollable Circumstances or otherwise.

#### Required Demonstration for Schedule Relief.  Without limiting any other requirement of this Article, the Design-Builder shall not be entitled to any adjustment to the Scheduled Substantial Completion Date, the number of days allowed for the achievement of Final Completion or any other schedule adjustment under this Design-Build Contract, unless the Design-Builder demonstrates:

##### That an Uncontrollable Circumstance has occurred and, subject to the time impact analysis requirements of Appendix 5, that the Uncontrollable Circumstance impacts one or more critical path activities in the Stage 2 Design-Build Work Schedule, as updated, maintained and revised by the Design-Builder in accordance with the Contract Standards, such that the Uncontrollable Circumstance will consume all available float and extend the time required to achieve the scheduled milestone from which relief is being sought;

##### The Design-Builder, in view of all circumstances, exercised reasonable efforts to avoid the delay; and

##### The delay was not caused by the Design-Builder or any other Design-Builder Person.

### Compensable Uncontrollable Circumstance Delay.  The Design-Builder shall be entitled to schedule relief but shall not be entitled to price relief for schedule delays due to unanticipated weather conditions or delays in the receipt of Governmental Approvals or Non-Governmental Crossing Approvals that constitute Uncontrollable Circumstances.  Price relief for schedule delays caused by other Uncontrollable Circumstances shall be limited to a reasonable and equitable Base Guaranteed Maximum Price Adjustment, which shall not exceed a reasonable daily value (to be based on the Design-Builder’s General Conditions Costs that are directly related to demobilization and remobilization for the Design-Build Work, temporary services, equipment rental which cannot be practically suspended and temporary protection measures which are unusual but necessary) multiplied by the number of days of compensable Uncontrollable Circumstance delay.

### Concurrent Delay.  The Design-Builder’s entitlement to price relief for Uncontrollable Circumstance delays under subsection (B) of this Section shall be limited to the extent of any concurrent delay by the Design-Builder or to the extent performance was, or would have been, suspended, delayed, or interrupted by another cause for which the Design-Builder is responsible.

## UNUSUALLY SEVERE AND ABNORMAL CLIMACTIC EVENTS.  If the Design-Builder intends to seek Uncontrollable Circumstance schedule relief on the basis of unusually severe and abnormal climactic events, the Design-Builder shall, in addition to fulfilling all other requirements of this Article, demonstrate that the actual weather encountered was unusually severe and abnormal compared with the five-year average weather statistics compiled by the United States National Oceanic and Atmospheric Administration for the time of year and locality of the Project Sites.

## RELEASE.

The Design-Builder’s acceptance of any performance, price or schedule adjustment under this Article shall be construed as a release of the City by the Design-Builder (and all persons claiming by, through or under the Design-Builder) from any and all losses or expenses resulting from, or otherwise attributable to, the event giving rise to the adjustment claimed.

## UNIT PRICING.  [NOTE: Parties to negotiate per unit charge for treatment/disposal of contaminated material that would constitute an Uncontrollable Circumstance as part of the GMP Amendment.]

# INDEMNIFICATION

## DESIGN-BUILDER’S OBLIGATION TO INDEMNIFY.

The Design-Builder shall indemnify, defend and hold harmless the City and the City, and their respective elected officials, trustees, members, appointed officers, employees, representatives, agents, attorneys, financial advisors, and contractors, including the Owner Representative (each a “the City Indemnitee”), from and against (and pay the full amount of) any and all Loss-and-Expense that any the City Indemnitee may sustain in connection with any claim made by one or more third parties (including claims for loss of or physical damage to property or assets), or any claim for, or in respect of, the death, personal injury, disease or illness of any person, including any the City Indemnitee, arising by reason of (or alleged to result from or in connection with) any:

###### Design-Builder Fault;

###### Non-compliance by the Design-Builder or any Design-Builder Person with any of the provisions of this Design-Build Contract or any Subcontract or any document, instrument or agreement delivered to the City as required under this Design-Build Contract;

###### Activities on the Project Sites, as and to the extent provided in (C);

###### Non-compliance with Applicable Law, as provided in (C);

###### Release of Regulated Substances by the Design-Builder or any Design-Builder Person, as provided in (A);

###### Labor disputes, as provided in (B);

###### Subcontractor claims, as provided in (I);

###### Design-Builder Employee claims, as provided in Section 7.3(K);

###### Intellectual Property claims, as provided in (A);

###### Failure by the Design-Builder to advise the City of any potential infringement or unauthorized use resulting from a the City-directed Change Order, as provided in (C);

###### Any claims of harassment arising from the conduct of the Design-Builder or any Design-Builder Person;

###### Breach by the Design-Builder or any Design-Builder Person of, or non-compliance by the Design-Builder or any Design-Builder Person with, any Governmental Approval or Applicable Law, or the failure of the Design-Builder or any Design-Builder Person to obtain all necessary Governmental Approvals in accordance with this Design-Build Contract; or

###### Any other act, event or circumstance as to which the Design-Builder is obligated to provide an indemnity hereunder;

except to the extent caused by the City Fault or the negligence or willful misconduct of a Separate Contractor.  The Design-Builder’s indemnity obligations under this Section shall not be limited by any coverage exclusions or other provisions in any policy of Required Insurance or other insurance maintained by the Design-Builder which is intended to respond to such events.  Notwithstanding the foregoing, the City Indemnitees’ right to indemnification pursuant to this Section shall be reduced by all insurance, settlement proceeds or third party indemnification proceeds actually received by the City Indemnitees.  This Section may be relied upon by the City Indemnitees and may be enforced directly by any of them against the Design-Builder in the same manner and for the same purpose as if pursuant to a contractual indemnity directly between them and the Design-Builder.

## INDEMNIFICATION PROCEDURES.

### Notice.  If a the City Indemnitee receives any notice, demand, letter or other document concerning any claim for which it appears that the City Indemnitee is, or may become entitled to, indemnification or compensation under this Design-Build Contract in respect of the entire claim, the City Indemnitee shall give notice in writing to the Design-Builder as soon as reasonably practicable.

### Consolidation of Claims.  If a notice of claim is given pursuant to subsection (A) of this Section by more than one the City Indemnitee relating to the same facts or circumstances, the Design-Builder may, in its discretion, require the consolidated administration and coordination of all such noticed claims by common counsel.

### Design-Builder Right to Dispute Claim.  If notice is given as provided in subsection (A) of this Section, the Design-Builder shall be entitled to dispute the claim in the name of the City Indemnitee at the Design-Builder’s own expense and take conduct of any defense, dispute, compromise, or appeal of the claim and of any incidental negotiations. The City Indemnitee will give the Design-Builder all reasonable cooperation, access and assistance for the purposes of considering and resisting such claim.

### Rights and Duties of the Parties.  With respect to any claim conducted by the Design-Builder pursuant to subsection (C) of this Section:

###### The Design-Builder shall keep the City Indemnitee fully informed and consult with it about material elements of the conduct of such defense;

###### The Design-Builder shall demonstrate to the City Indemnitee, at the reasonable request of the City Indemnitee, that the Design-Builder has sufficient means to pay all costs and expenses that it may incur by reason of conducting such defense; and

###### The Design-Builder shall have full control of such defense and proceedings, including any compromise or settlement thereof; provided, however, that any such compromise or settlement involving non-monetary obligations of the City, or otherwise having a direct effect upon its continuing operations, shall (1) contain a full release of the City and (2) be subject to the consent of the City, which consent shall not be unreasonably withheld, conditioned or delayed.  If requested by the Design-Builder, the City (with the approval of the Board of Trustees, given in its discretion) shall, at the sole cost and expense of the Design-Builder, cooperate with the Design-Builder and its counsel in contesting any claim which the Design-Builder elects to contest.

### The City Indemnitee Rights to Conduct Defense.  A the City Indemnitee may take conduct of any defense, dispute, compromise or appeal of any claim subject to the Design-Builder’s indemnification obligations hereunder, including any incidental negotiations, if

###### The Design-Builder fails to notify the City Indemnitee of its intention to take conduct of the relevant claim within 14 days of the notice from the City Indemnitee under subsection (A) of this Section or notifies the City Indemnitee that it does not intend to take conduct of the claim; or

###### The City Indemnitee reasonably determines that a conflict exists between it and the Design-Builder which prevents or potentially prevents the Design-Builder from presenting a full and effective defense

###### The Design-Builder fails to comply in any material respect with subsection (D) of this Section.

### Transfer of Conduct of Claim to the City Indemnitee.  A the City Indemnitee may at any time, give notice to the Design-Builder that it is retaining or taking over, as the case may be, the conduct of any defense, dispute, compromise, settlement or appeal of any claim, or of any incidental negotiations, to which subsection (E) of this Section applies.  On receipt of such notice the Design-Builder will promptly take all steps necessary to transfer the conduct of such claim to the City Indemnitee, and will provide to the City Indemnitee all reasonable cooperation, access and assistance for the purposes of considering and resisting such claim.

### Design-Builder Responsibility for Costs.  If the City Indemnitee is entitled and elects to conduct its own defense pursuant to subsection (E) of this Section, all Fees and Costs incurred by the City Indemnitee in investigating, defending and conducting the claim for which it is entitled to indemnification hereunder shall constitute an indemnified loss subject to the Design-Builder’s indemnification obligations hereunder.

# SECURITY FOR PERFORMANCE

## BONDS.

### Performance and Payment Bonds.  Performance Bonds and Payment Bonds for the Design-Build Work shall be provided as follows:

#### Early Work Packages Bonds.  If the City authorizes an Early Work Package, then the Design-Builder shall provide to the City, on or before the Early Work Package Amendment Date, a Performance Bond and a Payment Bond covering the Design-Builder’s faithful performance of such Early Work Package Amendment and the payment of its obligations arising thereunder.  The penal sum of each such bond shall be in an amount equal to the Early Work Package Price applicable to the Early Work Package. Such bonds shall be in the forms set forth in Transaction Forms C and D and shall be issued by a Surety meeting the requirements set forth in subsection (E) of this Section.  If the City authorizes additional Early Work Packages, then the Design-Builder shall, on or before each subsequent Early Work Package Amendment Date, provide to the City, for each subsequent Early Work Package, an amendment to the above-referenced Performance Bond and Payment Bond, executed by both the Design-Builder and the Surety, that: (a) increases the penal sum of each bond by an amount equal to the Early Work Package Price of such Early Work Package; and (b) affirmatively states that the obligations under such bonds encompass the Design-Builder’s performance and payment obligations under each Early Work Package Amendment.

#### Amendment of Early Work Package Bonds on GMP Amendment Date.  If Performance and Payment Bonds have been provided pursuant to item (1) above, then the Design-Builder shall, on or before the GMP Amendment Date, provide to the City an amendment to the Performance Bond and the Payment Bond, executed by both Design-Builder and the Surety, that: (a) increases the penal sum of each bond to an amount equal to the Base Guaranteed Maximum Price; and (b) affirmatively states that such bonds cover faithful performance of this Design-Build Contract and payment of obligations arising thereunder.

#### New Design-Build Work Performance and Payment Bonds on GMP Amendment Date.  If the Performance Bond and the Payment Bond have not been provided pursuant to item (1) above, then the Design-Builder shall, on or before the GMP Amendment Date, provide to the City a Performance Bond and a Payment Bond that are in the penal sum of an amount equal to the Base Guaranteed Maximum Price and cover faithful performance of this Design-Build Contract and payment of obligations arising hereunder.  The forms of such bonds are set forth in Transaction Forms E and D and shall be issued by a Surety meeting the requirements set forth in subsection (E) of this Section.

#### Example Penal Sum Determination.  The following example is intended to illustrate the operation of the above, on the assumption that there are two Early Work Package Amendments before the GMP Amendment:

##### The parties enter into an Early Work Package Amendment for Scope X with a lump sum price of $1 million.  The Performance Bond and the Payment Bond will each have a penal sum of $1 million, and such bonds will cover the performance and payment obligations of the Design-Builder for Scope X.

##### The parties enter into another Early Work Package Amendment for Scope Y with a lump sum price of $1.5 million.  The Performance Bond and the Payment Bond will be amended to have a penal sum of $2.5 million, and such bonds will cover the performance and payment obligations of Design-Builder for Scope X and Y.

##### The parties enter into the GMP Amendment, with a Base Guaranteed Maximum Price of $10 million, inclusive of the lump sum pricing for Scopes X and Y.  The Performance Bond and the Payment Bond will be amended to have a penal sum of $10 million, and such bonds will cover all performance and payment obligations of the Design-Builder under this Design-Build Contract, inclusive of Scope X, Y and all other Design-Build Work under this Design-Build Contract.

#### Base Guaranteed Maximum Price Adjustments.  The amount of the Performance Bond and the Payment Bond shall be increased by the Design-Builder to reflect any Base Guaranteed Maximum Price Adjustments at the time such adjustment is implemented by the parties and as a condition to its entitlement to the adjustment.

#### Term of Bonds.  The Payment Bond shall be security for the payment of all persons supplying labor and material in the prosecution of the Design-Build Work and shall remain open until Final Completion.  The Performance Bond shall secure the performance of the Design-Build Work and shall remain open until Final Completion.

### Bond Forms.  Each bond given or tendered to the City pursuant to this Design-Build Contract must be on the City forms  (Transaction Forms B through F), with no changes made by the Design-Builder or the Surety, and must be dated, executed, and accompanied by a power of attorney stating that the attorney in fact executing the bond has requisite authority to execute such bond.  The bonds must be dated and must be no more than 30 days old when delivered to the City.

### Payment Bond Information.  The Design-Builder shall furnish information to a Payment Bond beneficiary.

### Delivery of Bonds.  The Design-Builder shall deliver required bonds to the City within the time limits specified in this Section.

### Surety Requirements.  The bonds required to be provided pursuant to this Section shall be issued by a Surety:

###### Approved by the City having a rating of A- or better in the latest revision of the A.M. Best Company’s Insurance Report;

###### Listed in the United States Treasury Department’s Circular 570, “Companies Holding Certificates of Authority as Acceptable Sureties on Federal Bonds and as Acceptable Reinsurance Companies”;

###### Holding a certificate of authority to transact surety business in the State; and

###### In compliance with the requirements of State law.

If a bond is given or tendered to the City pursuant to this Design-Build Contract in an amount greater than 10 percent of Surety’s capital and surplus, the Surety shall provide certification that the Surety has reinsured that portion of the risk that exceeds 10 percent of the Surety’s capital and surplus.  The reinsurance must be with one or more reinsurers who are duly authorized, accredited, or trusted to do business in the State.  The amount reinsured by any reinsurer may not exceed 10 percent of the reinsurer’s capital and surplus.  The amount of allowed capital and surplus must be based on information received from the State Board of Insurance.

### Monitoring of Sureties.  The Design-Builder shall be responsible throughout the Term for monitoring the financial condition of any Surety issuing bonds under this Design-Build Contract and for making inquiries no less often than annually to confirm that each such Surety maintains at least the minimum rating level specified in this Section.  In the event the rating of any issuing Surety falls below such minimum level, or if any surety company is declared bankrupt or becomes insolvent or has the rights to do business in the State terminated, the Design-Builder shall promptly notify the City of such event and shall promptly take steps to ensure continued compliance with this Section by furnishing or arranging for the furnishing of a substitute or additional bond of a surety company whose rating and other qualifications satisfy all above requirements, unless the City agrees to accept the surety company that no longer satisfies the minimum rating level specified above, or agrees to an alternative method of assurance.  Upon such notice by the Design-Builder of such an event, the City shall not unreasonably withhold its approval of such assurance.

### Completion of Work.  Without limiting any other right or remedy provided for under the Performance Bond, if this Design-Build Contract is terminated by the City for an Event of Default and the Surety fails to pursue completion of the Contract Obligations with reasonable speed, the City may arrange for completion of the Contract Obligations and deduct the cost thereof from any amount otherwise due to the Design-Builder under this Design-Build Contract, including the cost of additional the City administration and consultant services made necessary by such default or neglect.  In such event, no further payment shall then be made by the City until all costs of completing the Contract Obligations shall have been paid.

# MISCELLANEOUS PROVISIONS

## OWNERSHIP OF THE PROJECT.

The Project shall be owned by the City at all times.  The Design-Builder shall perform the Contract Obligations provided for herein as an independent contractor and shall not have any legal, equitable, tax beneficial or other ownership or leasehold interest in the Project.  The Design-Builder shall not use the Project for any purpose other than the purposes contemplated by this Design-Build Contract or to serve or benefit any person other than the City.

## RELATIONSHIP OF THE PARTIES.

The Design-Builder is an independent contractor of the City and the relationship between the parties shall be limited to performance of this Design-Build Contract in accordance with its terms.  Neither party shall have any responsibility with respect to the services to be provided or contractual benefits assumed by the other party.  Nothing in this Design-Build Contract shall be deemed to constitute either party a partner, agent or legal representative of the other party.  No liability or benefits, such as workers compensation, pension rights or liabilities, or other provisions or liabilities arising out of or related to a contract for hire or employer/employee relationship shall arise or accrue to any party’s agent or employee as a result of this Design-Build Contract or the performance thereof.

## AFFILIATE TRANSACTIONS.

If any costs to be reimbursed by the City to the Design-Builder under this Design-Build Contract arise from a transaction between the Design-Builder and any Affiliate of the Design-Builder, the Design-Builder shall notify the City of the specific nature of the contemplated transaction, including the identity of the Affiliate, the nature of the work to be performed by the Affiliate and the anticipated cost to be incurred, before any such transaction is consummated or cost incurred.  The Design-Builder shall not enter into any such transaction, nor incur any such cost, absent the written approval of the City in its sole discretion.

## CONTRACT ADMINISTRATION.

### Administrative Communications.  The parties recognize that a variety of contract administrative matters will routinely arise throughout the performance of this Design-Build Contract.  These matters will by their nature involve requests, notices, questions, assertions, responses, objections, reports, claims, and other communications made personally, in meetings, by phone, by mail and by electronic and computer communications. The purpose of this Section is to set forth a process by which the resolution of the matters at issue in such communications, once resolution is reached, can be formally reflected in the common records of the parties so as to permit the orderly and effective administration of this Design-Build Contract.

### Contract Administration Memoranda.  The principal formal tool for the administration of routine matters arising under this Design-Build Contract between the parties that do not require a Contract Amendment shall be a “Contract Administration Memorandum.”  A Contract Administration Memorandum shall be prepared, once all preliminary communications have been concluded, to evidence the resolution reached by the City and the Design-Builder as to matters of interpretation and application arising during the course of the performance of their obligations hereunder. Such matters may include, for example:

###### Issues as to the meaning, interpretation or application of this Design-Build Contract in particular circumstances or conditions;

###### Calculations required to be made;

###### Notices, waivers, releases, satisfactions, confirmations, further assurances, consents and approvals given hereunder; and

###### Other similar routine contract administration matters.

### Procedure.  Either party may request the execution of a Contract Administration Memorandum.  When resolution of the matter is reached, a Contract Administration Memorandum shall be prepared by or at the direction of the City reflecting the resolution.  Contract Administration Memoranda shall be serially numbered, dated, signed by the Design-Builder Contract Representative and the City Contract Representative, and, at the request of the City, co-signed by a Senior Supervisor for the Design-Builder.  The City and the Design-Builder each shall maintain a parallel, identical file of all Contract Administration Memoranda, separate and distinct from the Contract Amendments and all other documents relating to the administration and performance of this Design-Build Contract.

### Effect.  Executed Contract Administration Memoranda shall serve to guide the ongoing interpretation and application of the terms and conditions of this Design-Build Contract.  Any material change, alteration, revision or modification of this Design-Build Contract, however, shall be effectuated only through a formal Contract Amendment in accordance with Section 17.5.

## CONTRACT AMENDMENTS.

### Amendments Generally.  Notwithstanding the provisions of Section 17.4 but without limiting any approval authority delegated to the City Contract Representative pursuant to (B), no material change, alteration, revision or modification of the terms and conditions of this Design-Build Contract shall be made except through a written amendment to this Design-Build Contract (a “Contract Amendment”), duly authorized, approved or ratified by the City Council and duly authorized by the Design-Builder.

### Procedure.  Contract Amendments shall be serially numbered, dated and signed by a Senior Supervisor for the Design-Builder and by the City Contract Representative or an authorized signatory of the City for the City, as determined in accordance with (B).  The City and the Design-Builder each shall maintain a parallel, identical file of all Contract Amendments, separate and distinct from the Contract Administration Memoranda and all other documents relating to the administration and performance of this Design-Build Contract.

## CONTRACT REPRESENTATIVES.

### Design-Builder Contract Representative and Senior Supervisors.  The Design-Builder shall appoint and inform the City in writing from time to time of the identity of  (1) the individual with the responsibility and power from time to time to administer this Design-Build Contract and to bind the Design-Builder with respect to any Contract Administration Memorandum, Change Order and Contract Amendment (which may be the same or different individual with respect to the Stage 1 Preliminary Services and the Stage 2 Design-Build Work) (the “Design-Builder Contract Representative”), and (2) the corporate officials of the Design-Builder with senior supervisory responsibility for the Project and the performance of this Design-Build Contract (the “Senior Supervisors”).  The Design-Builder shall promptly notify the City in writing of the appointment of any successor Senior Supervisors.  The Senior Supervisors shall cooperate with the City in any reviews of the performance of the Project Manager and the Design-Builder Contract Representative which the City may undertake from time to time, and shall give full consideration to any issues raised by the City in conducting such performance reviews.

### City Contract Representative.  The City shall appoint an individual or individuals to act as the “City Contract Representative” for this Design-Build Contract.  Such appointment shall be in writing and include a specific description of the extent of the City Contract Representative’s power to administer this Design-Build Contract, including specific dollar limitations of his or her authority.  The Design-Builder shall be entitled to a copy of any such written appointment.  The Design-Builder understands and agrees that any delegation to the City Contract Representative may provide only limited authority with respect to the implementation of this Design-Build Contract, which may or may not include the authority to bind the City with respect to any Change Order, Work Change Directive or Contract Amendment.  Within such limitations, the Design-Builder shall be entitled to rely on the written directions of any the City Contract Representative.  The City Contract Representative shall have the right at any time to issue the Design-Builder a written request for information relating to this Design-Build Contract.  Any written request designated as a “priority request” shall be responded to by the Design-Builder within three Business Days.

### City Approvals and Consents.  When this Design-Build Contract requires any approval or consent by the City to a Design-Builder submission, request or report, the approval or consent shall, within the limits of the authority of subsection (B) of this Section, be given by the City Contract Representative in writing and such writing shall be conclusive evidence of such approval or consent, subject only to compliance by the City with the Applicable Law that generally governs its affairs.  Unless expressly stated otherwise in this Design-Build Contract, and except for requests, reports and submittals made by the Design-Builder that do not, by their terms or the terms of this Design-Build Contract, require a response or action, if the City does not find a request, report or submittal acceptable, it shall provide written response to the Design-Builder describing its objections and the reasons therefor within 30 days of the City’s receipt thereof.  If no response is received, the request, report or submittal shall be deemed rejected unless the City’s approval or consent may not be unreasonably delayed by the express terms hereof, and the Design-Builder may resubmit the same, with or without modification.  Requests, reports and submittals that do not require a response or other action by the City pursuant to some specific term of this Design-Build Contract shall be deemed acceptable to the City if the City shall not have objected thereto within 30 days of the receipt thereof.

## PROPERTY RIGHTS.

### Protection from Infringement.  The Design-Builder shall pay all royalties and license fees in connection with the Contract Obligations during the Term.  Except as provided in subsection (C) of this Section, the Design-Builder shall indemnify, defend and hold harmless the City Indemnities in accordance with and to the extent provided in Section 15.1 from and against all Loss-and-Expense arising out of or related to the infringement or unauthorized use of any patent, trademark, copyright or trade secret relating to, or for the Contract Obligations.  The Design-Builder’s indemnity pursuant to this Section shall apply only when infringement occurs or is alleged to occur from the intended use for which the Deliverable Material, process or equipment was provided by the Design-Builder pursuant to this Design-Build Contract.

### Substitutes for Deliverable Material, Process or Equipment.  Except as provided in subsection (C) of this Section, in the event the Design-Builder or the City is enjoined from using any Deliverable Material, process or equipment, the Design-Builder, at its sole cost and expense, shall:

###### Acquire the right to legally use such infringing Deliverable Material, process or equipment (or any affected Design-Build Work) under infringed patents or copyrights; or

###### Modify or replace such Deliverable Material, process or equipment (or any affected Design-Build Work) with un-infringed Deliverable Material, process or equipment (or any affected Design-Build Work) equivalent in quality, performance, useful life and technical characteristics and development; provided, however, that any such modification or replacement shall be subject to the City’s approval, which shall not be unreasonably withheld or delayed.

### Exceptions to Infringement Protection.  Unless otherwise agreed to by the parties, the Design-Builder’s obligations under this Section shall not apply to:

###### Infringement resulting from the City-directed Change Orders and Work Change Directives issued under (C) or Section 6.11;

###### Infringement resulting from unauthorized additions, changes or modifications to the Deliverable Material, process or equipment made or caused to be made by the City subsequent to delivery by the Design-Builder; or

###### Any claimed infringement which is settled without the consent of the Design-Builder.

The Design-Builder shall promptly advise the City as to whether any the City-directed Change Order or Work Change Directive issued under (C) or Section 6.11 may result in any infringement or unauthorized use and, in the event of any failure by the Design-Builder to so advise the City, the Design-Builder will indemnify the City for any Loss-and-Expense resulting from any such infringement or unauthorized use.

### Pre-Existing Intellectual Property.  The City acknowledges and agrees that in the performance of Contract Obligations under this Design-Build Contract, the Design-Builder may use proprietary algorithms, software, hardware, databases, other background technology, and other proprietary information that the Design-Builder developed or licensed from third parties prior to the Contract Date (“Pre-Existing Intellectual Property”).  Without limiting the City’s rights with respect to the Deliverable Material, the Design-Build Work or the Project, the Design-Builder will retain all right, title, and interest in such Pre-Existing Intellectual Property.  However, the City shall have the irrevocable, perpetual, and unrestricted right from and after the Contract Date to use (or permit use of) all Pre-Existing Intellectual Property incorporated in the Deliverable Material, the Design-Build Work or the Project, all oral information received by the City in connection with the Design-Build Work, and all ideas or methods represented by Pre-Existing Intellectual Property incorporated in the Deliverable Material or the Project, in each case without additional compensation. The Design-Builder hereby licenses such irrevocable, perpetual, and unrestricted rights to the City.  The City’s use of such license rights for any purpose other than the Project shall be at its own risk, and the Design-Builder shall have no liability for or relating to any such use.

### Protection of Proprietary Rights of the City.  The Design-Builder agrees and covenants to protect any and all proprietary rights of the City in any material provided to the Design-Builder.  Such protection of proprietary rights by the Design-Builder shall include the insertion in any copy intended for publication of a copyright mark reserving all rights to the City in any such material provided by the City to the Design-Builder.  Additionally, any materials provided to the Design-Builder by the City shall not be released to any third party without the written consent of the City and shall be returned intact to the City upon completion or termination of this Design-Build Contract.  The provisions of this subsection shall not apply to material in the public domain on the Contract Date or material that subsequently comes into the public domain by other than an unauthorized disclosure.

## SBE/LEAP REQUIREMENTS.

### Small Business Enterprise (SBE).  The City of Tacoma’s Small Business Enterprise program (SBE) offers contracting of services to qualified small businesses interested in doing work in the City.  The goal of the SBE program is to facilitate a substantial procurement, education, and small business assistance program designed to promote equitable participation by historically underutilized businesses in the provision of services to the City.  The City plans to establish a SBE goal for the Project that will range between 8% - 15% to be met during Construction.  The Design-Builder shall use all reasonable efforts to meet the SBE goal set by the City.

### Local Employment and Apprenticeship Training Program  (LEAP).  The Local Employment and Apprenticeship Training program (LEAP) has been adopted to counteract economic and social ills, which accompany high rates of unemployment within the City.  The Tacoma City Council established the LEAP for Public Works Contracts pursuant to City of Tacoma ordinance No. 27815.  The primary goal for this Program is to provide an opportunity for City residents to enter apprenticeship programs, acquire skills, and perform work that will provide living wages.  The Design-Builder shall comply with all City LEAP regulations in connection with the Construction of the Project.

## AFFIRMATIVE ACTION REQUIREMENTS.    Applicable Law.  The Design-Builder shall comply at all times with the affirmative action requirements of RCW 35.22.650 and the anti-discrimination requirements of Chapter 1.29 of the Tacoma Municipal Code.

### Affirmative Action Statement.  The Design-Builder shall actively solicit the employment of minority group members.  The Design-Builder shall actively solicit bids for the subcontracting of goods or services from qualified minority businesses.  The Design-Builder shall furnish evidence of the Design-Builder’s compliance with these requirements of minority employment and solicitation.  The Design-Builder further agrees to consider the grant of subcontracts to said minority bidders on the basis of substantially equal proposals in the light most favorable to said minority businesses.  As used in this section, the term “minority business” means a business at least fifty-one percent of which is owned by minority group members.  Minority group members include, but are not limited to, blacks, women, native Americans, Asians, Eskimos, Aleuts, and Hispanics.  The Design-Builder and all subcontractors shall also comply with the City’s Non-discrimination provisions, codified in Chapters 1.29 of the Tacoma Municipal Code.  The Design-Builder agrees to take all steps necessary to comply with all federal, state and City laws and policies regarding non-discrimination and equal employment opportunities.  The Design-Builder, and all of its subcontractors, shall not discriminate in any employment action because of race, religion, color, national origin or ancestry, sex, gender identity, sexual orientation, age, marital status, familial status or the presence of any sensory, mental, or physical handicap.  In the event of non-compliance by the Design-Builder or its subcontractors with any of the non-discrimination provisions of this Contract, the City, shall be deemed to have cause to terminate this Agreement, in whole or in part.  The Design-Builder shall comply with all Federal and State laws, regulations and policies against discrimination.

### Subcontracts.  The Design-Builder further agrees that the affirmative action statement in subsection (B) of this Section shall be incorporated in all Subcontracts with all labor organizations furnishing skilled, unskilled and union labor, or who may perform any such labor or services in connection with this Design-Build Contract.

## GENERAL DUTY TO MITIGATE.

### Mitigation by the Design-Builder.  In all cases where the Design-Builder is entitled to receive any relief from the City or exercise any rights, including the right to receive any payments, costs, damages or extensions of time, whether on account of Uncontrollable Circumstance or otherwise, the Design-Builder shall use all reasonable efforts to mitigate such amount required to be paid by the City to the Design-Builder under this Design-Build Contract, or the length of the extension of time.  Upon request from the City, the Design-Builder shall promptly submit a detailed description, supported by all such documentation as the City may reasonably require, of the measures and steps taken by the Design-Builder to mitigate and meet its obligations under this Section.

### Mitigation by the City.  In all cases where the City is entitled to receive from the Design-Builder any compensation, costs or damages, but not in any other cases, the City shall use all reasonable efforts to mitigate such amount required to be paid by the Design-Builder to the City under this Design-Build Contract, provided that such obligation shall not require the City to:

###### Take any action which is contrary to the public interest, as determined by the City in its discretion;

###### Undertake any mitigation measures that might be available arising out of its status as a Governmental Body, but which measure would not normally be available to a private commercial party; or

###### Alter the amount of liquidated damages it is entitled to receive hereunder.

the City shall have no obligation to mitigate, implied or otherwise, except as set forth in this Section or as expressly provided in this Design-Build Contract.  Upon request by the Design-Builder, the City shall promptly submit a detailed description, supported by all such documentation as the Design-Builder may reasonably require, of the measures and steps taken by the City to mitigate and meet its obligations under this Section.

## ASSIGNMENT OF ANTI-TRUST CLAIMS.

Upon Final Completion, the Design-Builder agrees to assign to the City all rights, title and interest in and to all causes of action it may have under Section 4 of the Clayton Act (15 U.S.C. Sec. 15) arising from purchases of goods, services, or materials pursuant to this Design-Build Contract.

## ACTIONS OF CITY IN ITS GOVERNMENTAL CAPACITY.

Nothing in this Design-Build Contract shall be interpreted as limiting the rights and obligations of the City under Applicable Law in its governmental capacity (including police power actions to protect health, safety and welfare or to protect the environment), or as limiting the right of the Design-Builder to bring any action against the City, not based on this Design-Build Contract, arising out of any act or omission of the City in its governmental capacity.

## ASSIGNMENT.

### By the Design-Builder.  The Design-Builder shall not assign, transfer, convey, lease, encumber or otherwise dispose of this Design-Build Contract, its right to execute the same, or its right, title or interest in all or any part of this Design-Build Contract or any monies due hereunder whatsoever prior to their payment to the Design-Builder, whether legally or equitably, by power of attorney or otherwise, without the prior written consent of the City.  Any such approval given in one instance shall not relieve the Design-Builder of its obligation to obtain the prior written approval of the City to any further assignment.  Any such assignment of this Design-Build Contract which is approved by the City, shall require the assignee of the Design-Builder to assume the performance of and observe all obligations, representations and warranties of the Design-Builder under this Design-Build Contract which shall remain in full force and effect during this Design-Build Contract.  The approval of any assignment, transfer or conveyance shall not operate to release the Design-Builder in any way from any of its obligations under this Design-Build Contract unless such approval specifically provides otherwise.  In the event of any assignment or subletting without the prior written approval of the City, the City may, in addition to any other remedy provided herein, withhold any further payment of Contract Compensation.

### By the City.  The City may not assign its rights or obligations under this Design-Build Contract without the prior written consent of the Design-Builder, which may be given or withheld in the Design-Builder’s reasonable discretion.  The City may, however, assign its rights and obligations under this Design-Build Contract, without the consent of the Design-Builder, to another Governmental Body if such assignee assumes, and is legally capable of discharging the duties and obligations of the City hereunder.

## CONFIDENTIALITY.

### Confidential Nature of Information.  The Design-Builder shall treat all confidential information obtained from the City in the performance of this Design-Build Contract as confidential and proprietary to the City to the extent permitted by law.  “Confidential Information”, for purposes of this covenant, means any information and materials which is clearly identified or marked as being “confidential” or “proprietary” or otherwise marked in accordance with applicable federal law by the disclosing party.  Confidential Information does not include information which: (1) was in the public domain at the time of a disclosing party’s communication thereof to the receiving party; (2) entered the public domain through no fault of the receiving party subsequent to the time of the disclosing party’s communication thereof to the receiving party; (3) was in the receiving party’s possession free of any obligation of confidence at the time of the disclosing party’s communication thereof to the receiving party, as evidenced in the receiving parties records; (4) was rightfully communicated by a third party to a receiving party free of any obligation of confidence subsequent to the time of the disclosing party’s communication thereof to the receiving party; (5) was developed by employees or agents of the receiving party independently of and without reference to any proprietary information or other information that the disclosing party has disclosed in confidence to the receiving party; (6) is approved for release by written authorization of the disclosing party; or (7) the receiving party reasonably believes on advice of legal counsel it is legally obligated to disclose by law, rule, regulation, court order, or other compulsory process of a court or other governmental body, provided, however, that in such case, the receiving party shall immediately notify the disclosing party of its intention to disclose (unless the receiving party reasonably believes based on the advice of legal counsel that providing such notice would violate applicable law, rule, regulation, court order, or other compulsory process of a court or other governmental body) so that the disclosing party can take such legal action as it deems necessary or appropriate to prevent such disclosure.

### Limitation on Use and Disclosure.  The Design-Builder shall not use any Confidential Information obtained as a consequence of the performance of the Contract Obligations for any purpose other than the performance of the Contract Obligations in accordance with this Design-Build Contract.  The Design-Builder shall not disclose any information obtained from the City or obtained as a consequence of the performance of the Contract Obligations to any person other than its own employees, agents or Subcontractors who have a need for the information for the performance of work under this Design-Build Contract, unless such disclosure is specifically approved in writing by the City, which approval may be withheld in the sole and absolute discretion of the City.

## LIMITED RECOURSE TO CITY.  No recourse shall be had to the general fund or general credit of the City for the payment of any amount due the Design-Builder hereunder, whether on account of the Stage 2 Design-Build Price or for any Loss-and-Expense or payment or claim of any nature arising from the performance or non-performance of the City’s obligations hereunder.  The sole recourse of the Design-Builder for all such amounts shall be to the revenues of the City’s Wastewater/Stormwater Enterprise Fund.  All such revenues shall be held for the uses permitted and required thereby and by the City Charter and other Applicable Law, and no such amounts shall constitute property of the Design-Builder.

## BINDING EFFECT.

This Design-Build Contract shall inure to the benefit of and shall be binding upon the City and the Design-Builder and any assignee acquiring an interest hereunder consistent with Section 17.13.

## AMENDMENT AND WAIVER.

### Contract Amendments.  This Design-Build Contract may not be amended except by a written agreement signed by the parties in accordance with Section 17.5.

### Waiver.  Any of the terms, covenants, and conditions of this Design-Build Contract may be waived at any time by the party entitled to the benefit of such term, covenant or condition if such waiver is in writing and executed by the party against whom such waiver is asserted.

## NOTICES.

### Procedure.  All notices, consents or approvals or written communications (unless otherwise provided in the communication plan required to be developed pursuant to Appendix 2) given pursuant to the terms of this Design-Build Contract shall be:

###### In writing and delivered in person;

###### Transmitted by certified mail, return, receipt requested, postage prepaid or by overnight courier utilizing the services of a nationally-recognized overnight courier service with signed verification of delivery; or

###### Given by email transmission, if a signed original of the emailed letter or other communication is deposited in the United States Mail within two days after transmission.

Notices shall be deemed given only when actually received at the address first given below with respect to each party; provided, however, that email transmissions shall be deemed given only when the signed original of the emailed letter or other communication is received at such address.  Either party may, by like notice, designate further or different addresses to which subsequent notices shall be sent.

### City Notice Address.  Notices required to be given to the City shall be addressed as follows:

City of Tacoma Environmental Services Department 326 East D Street Tacoma, Washington 98421-2711 Attn: Kristy Beardemphl Email: kbeardemphl@cityoftacoma.org

with a copy to:

City of Tacoma Legal Department 747 Market Street Suite 1120 Tacoma, Washington Attn: City Attorney Facsimile No.: (253) 591-5755

### Design-Builder Notice Address.  Notices required to be given to the Design-Builder shall be addressed as follows:

[_______________] [_______________] [_______________] Attn: [_______________] Telephone No.: [_______________] Email: [_______________]

With a copy to:

[_______________] [_______________] [_______________] Attn: [_______________] Telephone No.: [_______________] Email: [_______________]

## NOTICE OF LITIGATION.

In the event the Design-Builder or the City receives notice of or undertakes the defense or the prosecution of any Legal Proceedings in connection with the Project, the party receiving such notice or undertaking such defense or prosecution shall give the other party timely notice of such proceedings and shall inform the other party in advance of all hearings regarding such proceedings.  For purposes of this Section only, “timely notice” shall be deemed given if the receiving party has a reasonable opportunity to provide objections or comments or to proffer to assume the defense or prosecution of the matter in question, given the deadlines for response established by the relevant rules of procedure.

## FURTHER ASSURANCES.

The City and Design-Builder each agree to execute and deliver such further instruments and to perform any acts that may be necessary or reasonably requested in order to give full effect to this Design-Build Contract. The City and the Design-Builder, in order to carry out this Design-Build Contract, each shall use all commercially reasonable efforts to provide such information, execute such further instruments and documents and take such actions as may be reasonably requested by the other and not inconsistent with the provisions of this Design-Build Contract and not involving the assumption of obligations or liabilities different from or in excess of or in addition to those expressly provided for herein.

[Signature Page Follows]

IN WITNESS WHEREOF, the parties have caused this Design-Build Contract to be executed by their duly authorized representatives as of the day and year first above written.

| CITY OF TACOMA, a municipal corporation _________________________________________ [Name], City Manager | [NAME OF DESIGN-BUILDER] By: ________________________________________ [Name] [Title] |
| --- | --- |
| _________________________________________ [Name], Environmental Services Department Director |  |
| _________________________________________ [Name], Finance Director |  |
| _________________________________________ [Name], Risk Manager |  |
| Approved as to form: |  |
| _________________________________________ [Name], Assistant City Attorney |  |
| ATTEST: | ATTEST: |
| _________________________________________ [Name], City Clerk | _________________________________________ Printed Name: |

TRANSACTION FORMS

TO THE
DESIGN-BUILD CONTRACT
FOR THE

JEFFERSON & HOOD STREET SURFACE

WATER INTERCEPTOR PROJET



between



THE CITY OF TACOMA

and



[NAME OF DESIGN-BUILDER]

Dated

[___________, 2017]

[This Page Intentionally Left Blank]

TRANSACTION FORM A

[RESERVED]

TRANSACTION FORM B

FORM OF PERFORMANCE BOND

(EARLY WORK PACKAGE AMENDMENT)

[This Page Intentionally Left Blank]

FORM OF PERFORMANCE BOND (EARLY WORK PACKAGE AMENDMENT)

BOND NO._______________

BOND AMOUNT:  $_______________

KNOW ALL MEN BY THESE PRESENTS:

THAT WE, _________________, as Principal (“Design-Builder”), and _________________, a corporation duly organized and existing under the laws of the State of _________________, with its principal place office in the City of _________________, and authorized under the laws of the State of Washington to act as surety on bonds for principals (“Surety”), do hereby acknowledge ourselves to be held and firmly bound to the City of Tacoma, Washington (“the City”), acting by and through its President and CEO, or his or her authorized representative, in the sum of _________________ Dollars ($_________________) (“Penal Sum”) for the payment of which sum, well and truly to be made to the City, its successors and assigns, Design-Builder and Surety do bind themselves, their heirs, executors, administrators, successors and assigns, jointly and severally. The obligation of the Surety hereunder shall not exceed the Penal Sum.

WHEREAS, Design-Builder has entered into a Design-Build Contract for the Jefferson & Hood Street Surface Water Interceptor Project dated _________________ (“Design-Build Contract”), which Design-Build Contract is hereby referred to and made a part hereof as fully and completely as if set out in full herein, and initially capitalized terms not otherwise defined herein shall have the meanings set forth in the Design-Build Contract; and

WHEREAS, Design-Builder and the City have entered into an Early Work Package Amendment dated _______________ (“Early Work Package Amendment [1]”), with an Early Work Package Price of ________________ ($_____________); and

WHEREAS, one of the conditions of the Design-Build Contract is that Design-Builder provide this duly executed instrument (“Bond”) for Early Work Package Amendment [1]; and

WHEREAS, for purposes of this Bond, the term “Work” refers to all of Design-Builder’s obligations under the Design-Build Contract to perform Early Work Package Amendment [1].

NOW THEREFORE, THE CONDITIONS OF THIS OBLIGATION ARE SUCH, that if Design-Builder shall faithfully and strictly perform the Work in accordance with the Design-Build Contract, then this obligation shall become null and void and shall have no further force and effect; otherwise the same is to remain in full force and effect.  Should the Design-Builder fail to faithfully and strictly perform the Work in accordance with the Design-Build Contract, including but not limited to the indemnifications under the Design-Build Contract, the Surety shall be liable for all damages, losses, expenses and liabilities that the City may suffer in consequence thereof, as more fully set forth herein, provided, however, that the Surety’s obligations to the City shall not be greater than the Design-Builder’s obligations to the City under the Design-Build Contract.

It is further understood and agreed that the Surety does hereby relieve the City or its representatives from the exercise of any diligence whatever in securing compliance on the part of the Design-Builder with the terms of the Design-Build Contract, and the Surety hereby waives any notice to it of any default, or delay by the Design-Builder in the performance of the Work and agrees that it, the Surety, shall be bound to take notice of and shall be held to have knowledge of all acts or omissions of the Design-Builder in all matters pertaining to the Work.  The Surety understands and agrees that the provision in the Design-Build Contract that the City will retain certain amounts due the Design-Builder is intended for the City’s benefit, and the City will have the right to pay or withhold such retained amounts or any other amount owing under the Design-Build Contract without changing or affecting the liability of the Surety hereon in any degree.

It is further expressly agreed by Surety that the City or its representatives are at liberty at any time, without notice to the Surety, to make any change in the Work, as provided in the Design-Build Contract, and in the terms and conditions thereof, or to make any change in, addition to, or deduction from the Work, and that such changes, if made, shall not in any way vitiate the obligation in this Bond and undertaking or release the Surety therefrom.

If the City gives Surety notice of Design-Builder’s default, Surety shall, within 45 days, take one of the following actions:

1.	arrange for Design-Builder, with consent of the City, to perform and complete the Work;

2.	take over and assume completion of the Work itself, through its agents or through independent contractors; or

3.	waive its rights under Paragraphs 1 and 2 above, and reimburse the City the amount of its reasonable costs to complete the Work and pay the City any other amount for which the Surety is liable under this Bond.

If the Surety fails to take either of the actions set out above, it shall, after receipt of notice as set forth above, be deemed to have waived its right to perform and complete the Work and receive payment of any monies under the Design-Build Contract, and the City shall be entitled to enforce any remedies available at law, including but not limited to completing the Work itself and recovering its damages and any other relief from the Surety.

This Bond and all obligations created hereunder shall be performed in Pierce County, Washington.  This Bond is given in compliance with the provisions of Section 39.10.330 of the Revised Code of Washington, as amended, which incorporated herein by this reference.  However, all of the express provisions hereof shall be applicable whether or not within the express provisions of said statute.

Notices required or permitted hereunder shall be in writing and shall be deemed delivered when actually received or, if earlier, on the third day following deposit in a United States Postal Service post office or receptacle, with proper postage affixed (certified mail, return receipt requested), addressed to the respective other party at the address prescribed in the Design-Build Contract, or at such other address as the receiving party may hereafter prescribe by written notice to the sending party.

The Surety’s obligations under this Bond will be maintained, and shall remain in full force and effect, until Final Completion.

IN WITNESS THEREOF, Design-Builder and Surety have signed and sealed this instrument on the respective dates written below their signatures and have attached current Power of Attorney.

[This Page Intentionally Left Blank]

TRANSACTION FORM C

FORM OF PAYMENT BOND

[This Page Intentionally Left Blank]

FORM OF PAYMENT BOND

BOND NO._______________

BOND AMOUNT:  $_______________

KNOW ALL MEN BY THESE PRESENTS:

THAT WE, _________________, as Principal (“Design-Builder”), and _________________, a corporation duly organized and existing under the laws of the State of _________________, with its principal place office in the City of _________________, and authorized under the laws of the State of Washington to act as surety on bonds for principals (“Surety”), do hereby acknowledge ourselves to be held and firmly bound to the City of Tacoma (“the City”), acting by and through its President and CEO, or his or her authorized representative, in the sum of _________________ Dollars ($_________________) (“Penal Sum”) for the payment of which sum, well and truly to be made to the City, its successors and assigns, Design-Builder and Surety do bind themselves, their heirs, executors, administrators, successors and assigns, jointly and severally. The obligation of the Surety hereunder shall not exceed the Penal Sum.

WHEREAS, Design-Builder has entered into a Design-Build Contract for the Jefferson & Hood Street Surface Water Interceptor Project dated _________________ (“Design-Build Contract”), which Design-Build Contract is hereby referred to and made a part hereof as fully and completely as if set out in full herein, and initially capitalized terms not otherwise defined herein shall have the meanings set forth in the Design-Build Contract; and

NOW, THEREFORE, THE CONDITION OF THIS OBLIGATION IS SUCH, that if Design-Builder shall pay all claimants supplying labor and materials to Design-Builder or a Subcontractor in the prosecution of the work provided for in the Design-Build Contract, then, this obligation shall be void; otherwise to remain in full force and effect.

PROVIDED, HOWEVER, that this bond is executed pursuant to the provisions of Section 39.10.330 of the Revised Code of Washington, as amended, and all liabilities on this bond shall be determined in accordance with the provisions of this Section, to the same extent as if it were copied at length herein.

Surety, for value received, stipulates and agrees that no change, extension of time, or other waiver or amendment of the terms of the Design-Build Contract or to the work to be performed thereunder, nor any change in the method nor any change in the method or amount of payments stipulated to be made by the City under the Design-Build Contract, shall relieve Surety of its obligations hereunder, and Surety hereby waives notice of any such change, extension of time, waiver or amendment of the terms of the Design-Build Contract or to the work to be performed thereunder.  This bond shall be automatically extended in time, without formal and separate amendment, to cover full and faithful performance of the Design-Build Contract in the event of modification of the Design-Build Contract, regardless of the length of time involved.

IN WITNESS THEREOF, Design-Builder and Surety have signed and sealed this instrument on the respective dates written below their signatures and have attached current Power of Attorney.

[This Page Intentionally Left Blank]

TRANSACTION FORM D

FORM OF PERFORMANCE BOND

(GMP AMENDMENT)

[This Page Intentionally Left Blank]

FORM OF PERFORMANCE BOND (GMP AMENDMENT)

BOND NO._______________

BOND AMOUNT:  $_______________

KNOW ALL MEN BY THESE PRESENTS:

THAT WE, _________________, as Principal (“Design-Builder”), and _________________, a corporation duly organized and existing under the laws of the State of _________________, with its principal place office in the City of _________________, and authorized under the laws of the State of Washington to act as surety on bonds for principals (“Surety”), do hereby acknowledge ourselves to be held and firmly bound to the City of Tacoma (“the City"), acting by and through its President and CEO, or his or her authorized representative, in the sum of _________________ Dollars ($_________________) (“Penal Sum”) for the payment of which sum, well and truly to be made to the City, its successors and assigns, Design-Builder and Surety do bind themselves, their heirs, executors, administrators, successors and assigns, jointly and severally. The obligation of the Surety hereunder shall not exceed the Penal Sum.

WHEREAS, Design-Builder has entered into a Design-Build Contract for the Jefferson & Hood Street Surface Water Interceptor Project dated _________________ (“Design-Build Contract”), which Design-Build Contract is hereby referred to and made a part hereof as fully and completely as if set out in full herein, and initially capitalized terms not otherwise defined herein shall have the meanings set forth in the Design-Build Contract; and

WHEREAS, Design-Builder and the City have entered into a GMP Amendment dated _______________, with a Base Guaranteed Maximum Price of ________________ ($_____________); and

WHEREAS, one of the conditions of the Design-Build Contract is that Design-Builder provide this duly executed instrument (“Bond”) for the GMP Amendment; and

WHEREAS, for purposes of this Bond, the term “Work” refers to all of Design-Builder’s obligations under the Design-Build Contract to perform Design-Build Work.

NOW THEREFORE, THE CONDITIONS OF THIS OBLIGATION ARE SUCH, that if Design-Builder shall faithfully and strictly perform the Work in accordance with the Design-Build Contract, then this obligation shall become null and void and shall have no further force and effect; otherwise the same is to remain in full force and effect.  Should the Design-Builder fail to faithfully and strictly perform the Work in accordance with the Design-Build Contract, including but not limited to the indemnifications under the Design-Build Contract, the Surety shall be liable for all damages, losses, expenses and liabilities that the City may suffer in consequence thereof, as more fully set forth herein, provided, however, that the Surety’s obligations to the City shall not be greater than the Design-Builder’s obligations to the City under the Design-Build Contract.

It is further understood and agreed that the Surety does hereby relieve the City or its representatives from the exercise of any diligence whatever in securing compliance on the part of the Design-Builder with the terms of the Design-Build Contract, and the Surety hereby waives any notice to it of any default, or delay by the Design-Builder in the performance of the Work and agrees that it, the Surety, shall be bound to take notice of and shall be held to have knowledge of all acts or omissions of the Design-Builder in all matters pertaining to the Work.  The Surety understands and agrees that the provision in the Design-Build Contract that the City will retain certain amounts due the Design-Builder is intended for the City’s benefit, and the City will have the right to pay or withhold such retained amounts or any other amount owing under the Design-Build Contract without changing or affecting the liability of the Surety hereon in any degree.

It is further expressly agreed by Surety that the City or its representatives are at liberty at any time, without notice to the Surety, to make any change in the Work, as provided in the Design-Build Contract, and in the terms and conditions thereof, or to make any change in, addition to, or deduction from the Work, and that such changes, if made, shall not in any way vitiate the obligation in this Bond and undertaking or release the Surety therefrom.

If the City gives Surety notice of Design-Builder’s default, Surety shall, within 45 days, take one of the following actions:

1.	arrange for Design-Builder, with consent of the City, to perform and complete the Work;

2.	take over and assume completion of the Work itself, through its agents or through independent contractors; or

3.	waive its rights under Paragraphs 1 and 2 above, and reimburse the City the amount of its reasonable costs to complete the Work and pay the City any other amount for which the Surety is liable under this Bond.

If the Surety fails to take either of the actions set out above, it shall, after receipt of notice as set forth above, be deemed to have waived its right to perform and complete the Work and receive payment of any monies under the Design-Build Contract, and the City shall be entitled to enforce any remedies available at law, including but not limited to completing the Work itself and recovering its damages and any other relief from the Surety.

This Bond and all obligations created hereunder shall be performed in Pierce County, Washington.  This Bond is given in compliance with the provisions of Section 39.10.330 of the Revised Code of Washington, as amended, which incorporated herein by this reference.  However, all of the express provisions hereof shall be applicable whether or not within the express provisions of said statute.

Notices required or permitted hereunder shall be in writing and shall be deemed delivered when actually received or, if earlier, on the third day following deposit in a United States Postal Service post office or receptacle, with proper postage affixed (certified mail, return receipt requested), addressed to the respective other party at the address prescribed in the Design-Build Contract, or at such other address as the receiving party may hereafter prescribe by written notice to the sending party.

The Surety’s obligations under this Bond will be maintained, and shall remain in full force and effect, until Final Completion.

IN WITNESS THEREOF, Design-Builder and Surety have signed and sealed this instrument on the respective dates written below their signatures and have attached current Power of Attorney.

[This Page Intentionally Left Blank]